## Sheet1
Project Title | Charter | Document Type | Start Date | ECD-DA Was | ECD-DA Is Now | Total Estimated Time to Complete (in months) | ECD-DA Change in Months | Confirm when these books will be completed | Should Project Be Continued or Closed?
Cross Support Service Management: Planning Data Formats | 3.03 Cross Support Service Management Working Group | Blue | 2013-11-15 | 2016-03-30 | 2017-03-30 | 40 | 12 | Resource issues have emerged; best estimate at this time for ECD-DA is 30 June 2017 | Continued.
Cross Support Service Management: File Transfer, Ground Segment, Recommended Profile | 3.03 Cross Support Service Management Working Group | Blue | 2015-10-26 | 2017-01-30 | 2017-11-01 | 24 | 9 | 01 November 2017 is still best estimate at this time. | Continued.