## Slide 1
Action Items and Resolutions from the CMC’s 15-17 June 2021 Meeting
CMC Spring 2021 Meeting
17 June 2021
Notes: 1
1
1

## Slide 2: CMC-A-2021-06-01
  The CMC asks that CCSDS’s Liaison to the IOAG inquire about the dates for the next IOAG meeting and provide them to the CMC once the dates have been finalized.
  Due Date: 15 October 2021

## Slide 3: CMC-A-2021-06-02
  The CMC directs the Secretariat to confirm with the chair of the Wireless Working Group that the patent considerations statement in CCSDS 883.0-R-1, Spacecraft Onboard Interface Services—High Data Rate Wireless Proximity Network Communications, meets the expected use case of adopters.
  Due Date: 1 July 2021

## Slide 4: CMC-A-2021-06-03
  The CMC directs the Secretariat to begin a poll on behalf of CNES asking:
  Does your agency's current travel policy allow its members to attend the Fall 2021 Tech Plenary, CESG, and CMC meetings scheduled for 18-28 October in Toulouse (France)?
  Due Date: 25 June 2021

## Slide 5: CMC-A-2021-06-04
  The CMC directs the Secretariat to begin a poll for selecting the dates of the spring 2022 CMC meeting hosted by JAXA in Tokyo, Japan.
  Due Date: 25 June 2021

## Slide 6: CMC-A-2021-06-05
  The CMC directs the Secretariat to update the contact information for all CCSDS Associates as listed on the CCSDS public website. The Secretariat should also record a sponsoring agency for each Associate.
  Due Date: 15 October 2021

## Slide 7: CMC-A-2021-06-06
  The CMC directs the Secretariat to update the CCSDS public website and CWE with the new SIS and SLS Area Directors
  Due Date: 1 July 2021

## Slide 8: CMC-A-2021-06-07
  The CMC directs the Secretariat to produce an example of the CCSDS organizational chart including Deputy Area Directors and Deputy Working Group Chairs. Once the CMC and CESG have reviewed, they will choose a layout for the chart.
  Due Date: August 2021CMC Midterm Meeting

## Slide 9: CMC-A-2021-06-08
  The CMC directs the Secretariat to start a poll for selecting the best date for a CMC midterm meeting. The Secretariat should include the proposed time of the meeting in UTC format.
  Due Date: 25 June 2021

## Slide 10: CMC-R-2020-12-07
  The CCSDS Management Council,
  Considering that the CMC member agencies are responsible for appointing Area Directors; and
  Recognizing that Mr. Gian Paolo Calzolari (ESA) has informed the CMC of his planned retirement; and
  Recognizing that Mr. Ignacio Aguilar Sanchez (ESA) has been nominated to serve as SLS Area Director; and
  Noting that this appointment constitutes the best staffing approach for the health of the CESG and the CCSDS as a whole;
  Approves the appointment of Mr. Ignacio Aguilar Sanchez as the new SLS Area Director effective immediately.

## Slide 11: CMC-R-2020-12-08
  The CCSDS Management Council,
  Considering that the CMC member agencies are responsible for appointing Area Directors; and
  Recognizing that Mr. Scott Burleigh (NASA) has informed the CMC of his retirement; and
  Recognizing that Mr. Tomaso de Cola (DLR) has been nominated to serve as SIS Area Director; and
  Noting that this appointment constitutes the best staffing approach for the health of the CESG and the CCSDS as a whole;
  Approves the appointment of Mr. Tomaso de Cola as the new SIS Area Director effective immediately.

## Slide 12: CMC-R-2020-12-09
  The CCSDS Management Council,
  Recognizes Mr. Wallace Tai for his service as CESG Deputy Chair and thanks him for the many years he has contributed to CCSDS.