## Sheet1
Action No. | Area | Action item | Action | Actionee | Status: 15 November 2021
AI/F20-1 | SOIS | Relations with Wi-Fi Alliance (WFA) | The SOIS Area shall nominate a person to be the CCSDS Liaison point of contact | JW | Closed. Chatwin Landsdowne nominated.
AI/S20-2 | SOIS | Proximity Wireless Network Comms | Check poll conditions to “Proximity Wireless Network Communications” and provide answers accordingly. Poll results were communicated with e-mail on 17th April 2020. | JW | Closed. Book is under Agency Review.
AI/F20-2 | SLS | Orange books - shall they be fully in line with CCSDS standards? | CESG Chair will issue the Terms of Reference of the Task Force as well as the nominations, and will schedule the meeting(s). | MdG | Closed. The Task Force has later been turned into two ad-hoc meetings, with participation as above, which took place in the February/March 2021 time frame.)
AI/F20-3 | CSS | Maintenance approach of databases in SANA | The CSS Area , with support from the SSG (SANA Steering Group) and any involved CESG members, will make an assessment and shall propose an approach by the CESG Spring 2021 meeting | EB, CH, PS | In progress. Splinter session will be organised by E. Barkley re. this. - closed.
AI/F20-4 | SEA | Related to the CCSDS – ISO TC20/SC14 liaison work, particularly on common terminology, the SEA proposes to now formally instantiate the Terminology Expert Group already defined in the CCSDS Registry Management Policy (RMP), 313.1-Y-2 | A.I. SEA AD: propose to CESG extensions to the existing SANA terminology registry to accommodate ISO TC20 SC14 shared use of this registry. | PS | Closed. Liaison agreement in place and meeting with experts have been done and more will come. Follow-on activities will come though. - closed.
AI/F20-5 | SEA | Terminology Expert Group members | A.I. SEA AD : request from CESG candidates for the TEG | PS | Pending. P. Shames to call the other Area directors for nominations.
AI/F19-4 | SOIS | Assessment of data representation aspects (e.g. MIB) in different CCSDS domains | To call a Telecon involving SOIS, SIS, CSS to assess data representation aspects (e.g. MIB) in different CCSDS domains, and brainstorm about commonalities. Outcome to be presented at CESG Mid-term Telecon. | JW | On-going. See E. Barkley report. Status Spring 2020: on going. An e-mail from Holger Dreihahn on 12th Feb 2020 re. harmonization of information models provided a preliminary proposal about the work to be done jointly. Activity will be resumed at next face-to-face meeting. Status Fall 2020: So far, only the commonality of data structures between SOIS and SIS has been assessed. CSS and SOIS have scheduled an introductory session.
AI/S19-8 | MOIMS | Mapping/interfacing of one MO service to one on-board service | Develop one example of mapping/interfacing of one MO service to one on-board service. JW to propose one on-board SOIS service (e.g one instrument on a subnet, described by EDS's), MOIMS and SOIS to develop the relevant mapping example. Status: during joint MOIMS/SOIS session examples to demonstrate mappings/interfacing were agreed . Also, the mapping/interfacing of MO service(s) to the on-board RT service(s), according to the three architectural scenarios identified at Spring Meeting, were outlined via diagrams. A demonstrator will be developed, to proof the mapping of MO services to on-board architectures, and potentially how the different CCSDS Areas could be connected via tooling. | MM/JW | On-going. M. Merri: integration of s/w on OPSSAT almost done, but requires debugging, with on-site presence at ESOC, to access the OPSSAT flatsat and subsequent testing with SOIS. J. Wilmot reported that he had problems in finding resources and JW will interact with MM to find a solution. Status Spring 2020: Action is on-going . Some progress done by MOIMS/SOIS, resources available and assigned to this task. Work in progress. Status Fall 2020: Following the establishment of a concept paper, three approaches have been defined for the MO/SOIS integration. The Demo focuses on two of the three: • Interfacing the on-board device and provisioning of its capabilities to the ground through MO M&C Services. • Wrapping the on-board functionality and providing it as an application level service to the ground. Status of demonstrator : • For this demo the iADCS device of OPSSAT has been used. • The EDS has been retroactively generated from the device ICD. • The resulting EDS has been used to auto-generate code • From the equivalent MO ADCS service specification (XML), an MO service code has been generated. • The integration of MO with EDS is on-going. • For now, approach (1) is being taken. A set of actions and a set of parameters were already defined and will be glued to the corresponding EDS auto-generated code methods. An early prototype is intended to be running soon on the FlatSat to discover potential problems. This early prototype makes simple calls to the driver and just logs them. • The gluing is done manually. Summary: all steps are completed. The integration and testing are not performed yet. Status Fall 2021: Ongoing
AI/F19-5 | CSS | RID template | CH to distribute the link to the RID tool package | CH | Closed. Status Spring 2020: action on-going. Status Fall 2020: no progress.
AI/F19-6 | All | Assessment of RID template tool | All Areas Directors to assess the suitability of the tool by Mid-term Telecon. | CESG All | On-going. Area Directors to review the tool. C. Haddow: tool being used in CSS already. E. Barkley: tool suitable. Availability of tool to be advertised to Technical Working Group Chairs and Deputy Chairs via cesg-all mailing list, and tool to be made available on CWE website by C. Haddow. Action now closed. Status Fall 2020: no progress, linked to AI/F19-5.
AI/S20-5 | SEA | UN registry of 'objects in space': "proposal to suggest adoption of the SANA registries by UNOOSA and Artemis Program" | CESG agrees that this makes sense and to present this proposal to CMC as a strategic activity. PS will then establish the working relations with Artemis Program, UN and UNOOSA. | PS | On-going. P. Shames to find way to accommodate this into the international Artemis gateway programme. Status Fall 2021: canceled