## SC14Database
Project # | Part # | Ed. | Project Title | Limit Dates | Project Lead | PL Country | Last completed action | Completion Date | Next Action | Next Action Due Date | Action Assigned To | WG Number | Notes | 2016-02-11
10784 | -1 | 1 | Space systems — Early operations — Part 1: Spacecraft initialization and commissioning | PUBLISHED | Slane, Frederick | USA | International Standard published | 2011-12-01 | Initiate member body review | 2016-12-01 | Central Secretariat | 2 Interfaces
10784 | -2 | 1 | Space systems — Early operations — Part 2: Initialization plan | PUBLISHED | Slane, Frederick | USA | International Standard published | 2011-12-01 | Initiate member body review | 2016-12-01 | Central Secretariat | 2 Interfaces
10784 | -3 | 1 | Space systems — Early operations — Part 3: Commissioning report | PUBLISHED | Slane, Frederick | USA | International Standard published | 2011-12-01 | Initiate member body review | 2016-12-01 | Central Secretariat | 2 Interfaces
10785 |  | 1 | Space systems — Bellows — Design and operation | PUBLISHED | Watanabe, Makoto | Japan | International Standard published | 2011-10-01 | Initiate member body review | 2016-10-01 | Central Secretariat | 1 Design Engineering
10786 |  | 1 | Space Systems — Structural components and assemblies | PUBLISHED | Ikeuchi, Masayuki & Chang, James B. | Japan, USA | International Standard published | 2011-07-15 | Initiate member body review | 2016-07-15 | Central Secretariat | 1 Design Engineering
10788 |  | 1 | Space systems — Lunar simulants | PUBLISHED | Slane, Frederick | USA | International Standard published | 2014-05-15 | Initiate member body review | 2019-05-15 | Central Secretariat | 4 Space Environments | Reinstated
10789 |  | 1 | Space systems — Programme management — Information and documentation management | PUBLISHED | Bonk, Stephan | Germany | International Standard published | 2011-09-15 | Initiate member body review | 2016-09-15 | Central Secretariat | 5 Program Management
10794 |  | 1 | Space systems — Programme management — Material, mechanical parts and processes | PUBLISHED | Kikuchi, Satoshi | Japan | International Standard published | 2011-08-01 | Initiate member body review | 2016-08-01 | Central Secretariat | 5 Program Management
10795 |  | 1 | Space systems — Programme management and quality — Vocabulary | PUBLISHED | Carneiro, Maria Alice | Brazil | International Standard published | 2011-08-15 | Initiate member body review | 2016-08-15 | Central Secretariat | 5 Program Management
10830 |  | 1 | Space systems — Non-destructive testing — Method of automatic ultrasonic inspection of graphite ingot for solid rocket motor | PUBLISHED | Sato, Eiichi | Japan | International Standard published | 2011-07-15 | Initiate member body review | 2016-07-15 | Central Secretariat | 6 Materials and Processes
10905 |  | 1 | Space environment (natural and artificial) — Lunar dust creation, suspension and transport | CANCELLED | Spitale, Guy | USA | Project deleted |  |  |  |  | 4 Space Environments
11221 |  | 1 | Space systems — Space solar panels — Spacecraft charging induced electrostatic discharge test methods | PUBLISHED | Cho, Mengu | Japan | International Standard published | 2011-08-01 | Initiate member body review | 2016-08-01 | Central Secretariat | 1 Design Engineering
11225 |  | 1 | Space environment (natural and artificial) — Guideline to reference and standard atmosphere models [Tech Rpt] | PUBLISHED | Vaughan, William W. | USA | International Tech Rpt published | 2012-10-03 | SC 14 Review | 2014-05-31 | SC 14 Members | 4 Space Environments | Reinstated. Technical Report
11227 |  | 1 | Space systems — Test procedures to evaluate spacecraft material ejecta upon hypervelocity impact | PUBLISHED | Kitazawa, Mandeville, Akahoshi, Matsumoto | France, Japan | International Standard published | 2012-09-15 | Initiate member body review | 2017-09-15 | Central Secretariat | 7 Orbital Debris | Transferred from WG6 to WG7 (Resolution 363)
11229 |  | 1 | Requirements for manufacturing and procurement of threaded fasteners | CANCELLED | Turzo, Guy | France | Project deleted |  |  |  |  | 6 Materials and Processes
11230 |  | 1 | Standard methods for mechanical testing of metallic materials | CANCELLED | Turzo, Guy | France | Project deleted |  |  |  | Central Secretariat | 6 Materials and Processes
11231 |  | 1 | Space systems — Probabilistic Risk Assessment (PRA) | PUBLISHED | Homayoon, Dezfuli | USA | Results of SR submitted to WG Convenor | 2015-12-17 | WG recommendation | 2016-06-01 | WG Convenor | 5 Program Management
11232 |  | 1 | Space systems — Spacecraft to launch vehicle interfaces | CANCELLED |  |  | Project deleted | 2010-02-05 |  |  | Secretariat | 2 Interfaces | Redundant project
11233 |  | 1 | Space systems — Orbit determination and estimation — Process for describing techniques [Tech Rpt] | PUBLISHED | Finkleman, Dave | USA | International Tech Rpt published | 2014-04-15 | Initiate WG/SC review | 2015-04-15 | Secretariat | 3 Operations | Reinstated. Technical Report
11892 |  | 1 | Space systems — Subsystems/units to spacecraft interface control document | PUBLISHED | Okamoto, Akira | Japan | International Standard published | 2012-03-01 | Initiate member body review | 2017-03-01 | Central Secretariat | 2 Interfaces
11893 |  | 1 | Space systems — Programme management — Project organization | PUBLISHED | Drogoul, Severin | France | International Standard published | 2011-04-13 | Initiate member body review | 2016-04-13 | Central Secretariat | 5 Program Management
12077 |  | 1 | Space environment (natural and artificial) — Trapped electron flux model for Geostationary Earth Orbits (GEO) | CANCELLED | Dinguirard, Magdeleine | France | Project deleted |  | Resolution by SC 14 | 2012-05-17 | SC 14 Members | 4 Space Environments
12208 |  | 1 | Space environment (natural and artificial) — Observed proton fluences over long duration at GEO and guideline for selection of confidence level in statistical model of solar proton fluences [Tech Spec] | PUBLISHED | Goka, Tateo | Japan | Technical Specification published | 2011-09-15 |  |  |  | 4 Space Environments | Reaff: 2014; CIB: Converted to IS (12/4/2014); see separate item below
12208 |  | 1 | Space environment (natural and artificial) — Observed proton fluences over long duration at GEO and guideline for selection of confidence level in statistical model of solar proton fluences | DIS - 12/8/2016 Pub - 12/8/2017 | Goka, Tateo | Japan | Pub text submitted to ISO/CS | 2015-07-21 | Publication | 2015-09-30 | Central Secretariat | 4 Space Environments
14200 |  | 1 | Space environment (natural and artificial) — Guide to process-based implementation of meteoroid and debris environmental models (orbital altitudes below GEO+2000km) | PUBLISHED | Kitazawa, Yukihito | Japan | International Standard published | 2012-11-13 | Initiate member body review | 2017-11-13 | Central Secretariat | 4 Space Environments
14222 |  | 1 | Space environment (natural and artificial) — Earth upper atmosphere | PUBLISHED | Rees, David | United Kingdom | International Standard published | 2013-09-15 | Initiate member body review | 2018-09-15 | Central Secretariat | 4 Space Environments
14300 | -1 | 2 | Space systems — Program management — Structuring of a project | PUBLISHED | Deak, Thomas | ESA | International Standard published | 2011-07-15 | Initiate member body review | 2016-07-15 | Central Secretariat | 5 Program Management
14300 | -2 | 2 | Space systems — Product assurance — Policy and principles | PUBLISHED | Drogoul, Severin | France | International Standard published | 2011-09-15 | Initiate member body review | 2016-09-15 | Central Secretariat | 5 Program Management | Reinstated
14302 |  | 1 | Space systems — Electromagnetic compatibility requirements | PUBLISHED | Trout, Dawn | USA | International Standard confirmed | 2013-08-26 | Initiate member body review | 2018-08-26 | Central Secretariat | 1 Design Engineering | Pub: 2002; Reaff: 2008, 2013
14303 |  | 1 | Space systems — Spacecraft to launch vehicle interfaces | PUBLISHED | Boland, Philippe | France | International Standard confirmed | 2013-08-26 | Initiate member body review | 2018-08-26 | Central Secretariat | 2 Interfaces | Pub: 2002; Reaff: 2008, 2013
14619 |  | 1 | Space systems — Space experiments — General requirements | PUBLISHED | Fomitchev, Gregori | RUSSIA | International Standard confirmed | 2014-07-31 | Initiate member body review | 2019-07-31 | Central Secretariat | 3 Operations | Reaff: 2014
14620 | -1 | 2 | Space systems — Safety requirements — Part 1: System safety | DIS - 10/30/2016 Pub - 10/30/2017 | Bonk, Stephan | Germany | Results of SR issued | 2014-10-29 | CD registration | 2015-04-30 | Project Leader | 5 Program Management | Transferred from WG3 to WG5 (Resolution 359)
14620 | -2 | 2 | Space systems — Safety requirements — Part 2: Launch site operations | PUBLISHED | Vergnault, Emmanuelle | France | International Standard published | 2011-08-15 | Initiate member body review | 2016-08-15 | Central Secretariat | 5 Program Management | Transferred from WG3 to WG5 (Resolution 359)
14620 | -3 | 1 | Space systems — Safety requirements — Part 3: Flight safety systems | PUBLISHED | Vergnault, Emmanuelle | France | International Standard confirmed | 2013-08-26 | Initiate member body review | 2018-08-26 | Central Secretariat | 5 Program Management | Pub: 2005; Reaff: 2008, 2013; transferred from WG3 to WG5 (Resolution 359)
14621 | -2 | 1 | Space systems — Electrical, electronic, and electromagnetic (EEE) parts — Control program requirements | PUBLISHED | Folco, Yves | France | Results of SR submitted to WG Convenor | 2014-08-01 | WG recommendation | 2014-11-30 | WG Convenor | 1 Design Engineering
14621 | -1 | 1 | Space systems — Electrical, electronic, and electromagnetic (EEE) parts — Parts management | PUBLISHED | Ingram-Cotton, John B. | USA | Results of SR submitted to WG Convenor | 2014-08-01 | WG recommendation | 2014-11-30 | WG Convenor | 1 Design Engineering
14622 |  | 1 | Space systems — Structural design — Loads and induced environment | PUBLISHED | Blanchard, Patrice | France | Systematic Review issued: 5 months | 2016-01-15 | National Votes Due | 2016-06-15 | SC 14 Members | 1 Design Engineering | Pub: 2000
14623 |  | 1 | Space systems — Pressure vessels and pressurized structures — Design and operation | PUBLISHED | Chang, James B. | USA | International Standard confirmed | 2014-07-31 | Initiate member body review | 2019-07-31 | Central Secretariat | 1 Design Engineering | Reaff: 2014
14624 | -1 | 2 | Space systems — Safety and compatibility of materials — Part 1: Test method for upward flammability of materials | CANCELLED | Davis, Eddie | USA | International Standard for revision | 2011-10-03 | WG recommendation | 2015-06-30 | WG Convenor | 6 Materials and Processes | See Resolution 309 (Berlin 2011); SC 14 N771; extended 1 yr
14624 | -2 | 2 | Space systems — Safety and compatibility of materials — Part 2: Test method for electrical wires and accessories | CANCELLED | Davis, Eddie | USA | International Standard for revision | 2011-10-03 | WG recommendation | 2015-06-30 | WG Convenor | 6 Materials and Processes | See Resolution 309 (Berlin 2011); SC 14 N772; extended 1 yr
14624 | -3 | 2 | Space systems — Safety and compatibility of materials — Part 3: Test method for off-gassed products from materials and assembled articles | CANCELLED | Davis, Eddie | USA | International Standard for revision | 2011-10-03 | WG recommendation | 2015-06-30 | WG Convenor | 6 Materials and Processes | See Resolution 309 (Berlin 2011); SC 14 N773; extended 1 yr
14624 | -4 | 1 | Space systems — Safety and compatibility of materials — Part 4: Test method for flammability of materials in gaseous oxygen | PUBLISHED | Davis, Eddie | USA | Systematic Review issued: 5 months | 2013-01-17 | National Votes Due | 2013-06-17 | SC 14 Members | 6 Materials and Processes | Pub: 2003; Reaff: 2008
14624 | -5 | 1 | Space systems — Safety and material compatibility — Part 5: Test method for determination of the reactivity of materials with aerospace hypergolic propellants | PUBLISHED | McClure, Mike | USA | International Standard for revision | 2014-07-31 | Committee draft (CD) registered | 2015-07-31 | Project Leader | 6 Materials and Processes
14624 | -6 | 1 | Space systems — Safety and material compatibility — Part 6: Test method for determining the reactivity of processing materials with aerospace fluids | PUBLISHED | Maes, Miguel | USA | International Standard for revision | 2014-07-31 | Committee draft (CD) registered | 2015-07-31 | Project Leader | 6 Materials and Processes
14624 | -7 | 1 | Space systems — Safety and compatibility of materials — Part 7: Test method for determining the permeability and penetration of materials to aerospace fluids | PUBLISHED | Maes, Miguel | USA | International Standard for revision | 2014-07-31 | Committee draft (CD) registered | 2015-07-31 | Project Leader | 6 Materials and Processes
14625 |  | 2 | Space systems — Ground support equipment for use at launch, landing, or retrieval sites — General requirements | PUBLISHED | Schultz, Larry | USA | International Standard confirmed | 2011-09-21 | Initiate member body review | 2016-09-21 | Central Secretariat | 3 Operations | Ed. 2 Pub:2007
14711 |  | 1 | Space systems — Unmanned mission operations concepts — Guidelines | PUBLISHED | Durham, David | USA | International Standard confirmed | 2013-08-26 | Initiate member body review | 2018-08-26 | Central Secretariat | 3 Operations | Pub: 2003; Reaff: 2008, 2013
14721 |  | 1 | Space systems — Archiving space data | CANCELLED |  |  | Project deleted |  |  |  |  | 3 Operations
14950 |  | 1 | Space systems — Unmanned spacecraft operability | PUBLISHED |  | Japan | International Standard confirmed | 2013-03-18 | Initiate member body review | 2018-03-18 | Central Secretariat | 3 Operations
14951 | Parts 1-13 | 1 | Space systems — Fluid characteristics — Parts 1-13 | CANCELLED | Schultz, Larry | USA | Project deleted |  |  |  |  | 3 Operations
14952 | -1 | 1 | Space systems — Surface cleanliness of fluid systems — Part 1: Vocabulary | PUBLISHED | Peralta, Stephen | USA | International Standard confirmed | 2014-08-08 | Initiate member body review | 2019-08-08 | Central Secretariat | 6 Materials and Processes
14952 | -2 | 1 | Space systems — Surface cleanliness of fluid systems — Part 2: Cleanliness levels | PUBLISHED | Peralta, Stephen | USA | International Standard confirmed | 2014-08-08 | Initiate member body review | 2019-08-08 | Central Secretariat | 6 Materials and Processes
14952 | -3 | 1 | Space systems — Surface cleanliness of fluid systems — Part 3: Analytical procedures for the determination of non volatile residues and particulate contamination | PUBLISHED | Peralta, Stephen | USA | International Standard confirmed | 2014-08-08 | Initiate member body review | 2019-08-08 | Central Secretariat | 6 Materials and Processes
14952 | -4 | 1 | Space systems — Surface cleanliness of fluid systems — Part 4: Rough cleaning processes | PUBLISHED | Peralta, Stephen | USA | International Standard confirmed | 2014-08-08 | Initiate member body review | 2019-08-08 | Central Secretariat | 6 Materials and Processes
14952 | -5 | 1 | Space systems — Surface cleanliness of fluid systems — Part 5: Processes for drying eqiupment | PUBLISHED | Peralta, Stephen | USA | International Standard confirmed | 2014-08-08 | Initiate member body review | 2019-08-08 | Central Secretariat | 6 Materials and Processes
14952 | -6 | 1 | Space systems — Surface cleanliness of fluid systems — Part 6: Precision cleaning processes | PUBLISHED | Peralta, Stephen | USA | International Standard confirmed | 2014-08-08 | Initiate member body review | 2019-08-08 | Central Secretariat | 6 Materials and Processes
14953 |  | 1 | Space systems — Structural design — Determination of loading levels for a static qualification test of launch vehicles | PUBLISHED | Blanchard, Patrice | France | Systematic Review issued: 5 months | 2016-01-15 | National Votes Due | 2016-06-15 | SC 14 Members | 1 Design Engineering | Pub: 2000
14954 |  | 1 | Space systems — Dynamic and static analysis — Exchange of mathematical models | PUBLISHED | Blanchard, Patrice | France | International Standard confirmed | 2013-08-26 | Initiate member body review | 2018-08-26 | Central Secretariat | 1 Design Engineering | Pub: 2005; Reaff: 2008, 2013
15387 |  | 1 | Space systems — Single-junction solar cells — Measurements and calibration procedures | PUBLISHED | Kiyota, Yoshiharu | Japan | International Standard confirmed | 2013-08-26 | Initiate member body review | 2018-08-26 | Central Secretariat | 1 Design Engineering | Pub: 2005; Reaff: 2008, 2013
15388 |  | 2 | Space systems — Contamination and cleanliness control | PUBLISHED | Baba, Naoko | Japan | International Standard published | 2012-02-14 | Initiate member body review | 2017-02-14 | Central Secretariat | 6 Materials and Processes
15389 |  | 1 | Space systems — Flight to ground umbilicals | PUBLISHED | Schultz, Larry | USA | International Standard confirmed | 2011-09-21 | Initiate member body review | 2016-09-21 | Central Secretariat | 3 Operations | Pub: 2001; Corrigendum 1 Published 2006-02-15
15389 | Amd1 | 1 | Space systems — Flight to ground umbilicals — Amendment 1: Add Annex A, Prevention of accidental cross connection | PUBLISHED | Tsukanov, Evgeny | Russia | International Standard confirmed | 2011-09-21 | Initiate member body review | 2016-09-21 | Central Secretariat | 3 Operations
15390 |  | 1 | Space environment (natural and artificial) — Models of galactic cosmic rays | PUBLISHED | Nymmik, Rikho | Russia | International Standard confirmed | 2013-03-19 | Initiate member body review | 2018-03-19 | Central Secretariat | 4 Space Environments | Pub: 2004; Reaff: 2007, 2013
15391 |  | 1 | Space environment (natural and artificial) — Probabilistic model of particle fluences and peak fluxes in solar cosmic rays | CANCELLED | Nymmik, Rikho | Russia | Project deleted by Central Secretariat due to lack of progress |  |  |  |  | 4 Space Environments
15392 |  | 1 | Space environment (natural and artificial) — Density of the upper atmosphere for altitudes below 2000 km | CANCELLED | Rees, David | United Kingdom | Project deleted by Central Secretariat due to lack of progress |  |  |  |  | 4 Space Environments
15856 |  | 1 | Space environment (natural and artificial) — Simulation guidelines for radiation exposure of non-metallic materials | PUBLISHED | Novikov, Lev | Russia | International Standard confirmed | 2015-12-17 | Initiate member body review | 2020-12-17 | Central Secretariat | 4 Space Environments | Pub: 2010; Reaff: 2015
15857 |  | 1 | Space environment (natural and artificial) — Method for estimation of future solar and geomagnetic activity used in determining earth orbital altitude density | CANCELLED | Shevirev, Alexander | Russia | Project deleted by Central Secretariat due to lack of progress |  |  |  |  | 4 Space Environments
15859 | -1 | 1 | Space systems — Fluid sampling and test methods — Part 1: Oxygen | PUBLISHED | Greene, Ben | USA | Results of SR issued | 2013-03-26 | Revision work registration | 2014-03-26 | Project Leader | 6 Materials and Processes | Pub: 2004; Reaff: 2007
15859 | -10 | 1 | Space systems — Fluid sampling and test methods — Part 10: Water | PUBLISHED | Greene, Ben | USA | Results of SR issued | 2013-03-26 | Revision work registration | 2014-03-26 | Project Leader | 6 Materials and Processes
15859 | -11 | 1 | Space systems — Fluid sampling and test methods — Part 11: Ammonia | PUBLISHED | Greene, Ben | USA | Results of SR issued | 2013-03-26 | Revision work registration | 2014-03-26 | Project Leader | 6 Materials and Processes
15859 | -12 | 1 | Space systems — Fluid sampling and test methods — Part 12: Carbon dioxide | PUBLISHED | Greene, Ben | USA | Results of SR issued | 2013-03-26 | Revision work registration | 2014-03-26 | Project Leader | 6 Materials and Processes
15859 | -13 | 1 | Space systems — Fluid sampling and test methods — Part 13: Breathing air | PUBLISHED | Greene, Ben | USA | Results of SR issued | 2013-03-26 | Revision work registration | 2014-03-26 | Project Leader | 6 Materials and Processes
15859 | -2 | 1 | Space systems — Fluid sampling and test methods — Part 2: Hydrogen propellant | PUBLISHED | Greene, Ben | USA | Results of SR issued | 2013-03-26 | Revision work registration | 2014-03-26 | Project Leader | 6 Materials and Processes
15859 | -3 | 1 | Space systems — Fluid sampling and test methods — Part 3: Nitrogen | PUBLISHED | Greene, Ben | USA | Results of SR issued | 2013-03-26 | Revision work registration | 2014-03-26 | Project Leader | 6 Materials and Processes
15859 | -4 | 1 | Space systems — Fluid sampling and test methods — Part 4: Helium propellant | PUBLISHED | Greene, Ben | USA | Results of SR issued | 2013-03-26 | Revision work registration | 2014-03-26 | Project Leader | 6 Materials and Processes
15859 | -5 | 1 | Space systems — Fluid sampling and test methods — Part 5: Nitrogen tetroxide propellant | PUBLISHED | Greene, Ben | USA | Results of SR issued | 2013-03-26 | Revision work registration | 2014-03-26 | Project Leader | 6 Materials and Processes
15859 | -6 | 1 | Space systems — Fluid sampling and test methods — Part 6: Monomethylhydrazine propellant | PUBLISHED | Greene, Ben | USA | Results of SR issued | 2013-03-26 | Revision work registration | 2014-03-26 | Project Leader | 6 Materials and Processes
15859 | -7 | 1 | Space systems — Fluid sampling and test methods — Part 7: Hydrazine propellant | PUBLISHED | Greene, Ben | USA | Results of SR issued | 2013-03-26 | Revision work registration | 2014-03-26 | Project Leader | 6 Materials and Processes
15859 | -8 | 1 | Space systems — Fluid sampling and test methods — Part 8: Kerosene propellant | PUBLISHED | Greene, Ben | USA | Results of SR issued | 2013-03-26 | Revision work registration | 2014-03-26 | Project Leader | 6 Materials and Processes
15859 | -9 | 1 | Space systems — Fluid sampling and test methods — Part 9: Argon | PUBLISHED | Greene, Ben | USA | Results of SR issued | 2013-03-26 | Revision work registration | 2014-03-26 | Project Leader | 6 Materials and Processes
15860 |  | 1 | Space systems — Gas contamination — Measurements methods for field tests | PUBLISHED | Tsukanov, Evgeny | Russia | International Standard confirmed | 2014-07-31 | Initiate member body review | 2019-07-31 | Central Secretariat | 3 Operations | Reaff: 2014
15861 |  | 1 | Space systems — Mobile space exploration robots — Design elements | CANCELLED | Moskowitz, Samuel | Israel | Project deleted |  |  |  |  | 3 Operations
15862 |  | 1 | Space systems — LV-SC flight environment requirements for telemetry data processing | PUBLISHED | Li, Guoai | China | International Standard confirmed | 2014-12-18 | Initiate member body review | 2019-12-18 | Central Secretariat | 2 Interfaces | Pub: 2009; Reaff: 2014
15863 |  | 1 | Space systems — Spacecraft to launch vehicle interface control document | PUBLISHED | Thiery, Jerome | France | International Standard confirmed | 2014-12-18 | Initiate member body review | 2019-12-18 | Central Secretariat | 2 Interfaces | Pub: 2003; Reaff: 2009, 2014
15864 |  | 1 | Space systems — General test methods for spacecraft, subsystems, and units | PUBLISHED | Okamoto, Akira | Japan | International Standard confirmed | 2013-08-26 | Initiate member body review | 2018-08-26 | Central Secretariat | 2 Interfaces | Pub: 2004; Reaff: 2008, 2013
15865 |  | 1 | Space systems — Qualification assessment | PUBLISHED | Ionov, Anton | Russia | International Standard confirmed | 2014-10-14 | Initiate member body review | 2019-10-14 | Central Secretariat | 5 Program Management | Pub: 2005; Reaff: 2008; Reaff: 2014
16091 |  | 1 | Space systems — Integrated logistic support | PUBLISHED | Drogoul, Severin | France | Systematic Review issued: 5 months | 2013-01-17 | National Votes Due | 2013-06-17 | SC 14 Members | 5 Program Management | Pub: 2002; Reaff: 2008
16126 |  | 1 | Space systems — Assessment of survivability of unmanned spacecraft against space debris and meteoroid impacts to ensure successful post-mission disposal | PUBLISHED | Stokes, Hedley | UK | International Standard published | 2014-04-01 | Initiate member body review | 2019-04-01 | Central Secretariat | 7 Orbital Debris | NWIP: N619; transferred from WG1 to WG7 (Resolution 353)
16127 |  | 1 | Space systems — Prevention of break-up of unmanned spacecraft | PUBLISHED | Gibbon, Dave | UK | International Standard published | 2014-02-15 | Initiate member body review | 2019-02-15 | Central Secretariat | 7 Orbital Debris | NWIP: N617; transferred from WG1 to WG7 (Resolution 353)
16157 |  | 1 | Space system — Human-life activity support systems and equipment integration in space flight — Techno-medical requirements for space vehicle human habitation environments | DIS - 3/27/2015 Pub - 3/27/2016 | Guzenberg, Arkadiy | Russia | Results of CD/V sent to PL | 2014-08-07 | DIS text needed from PL | 2014-10-31 | Project Leader | 6 Materials and Processes | NWIP: N620; new timeline given (mistakenly cancelled by ISO/CS)
16158 |  | 1 | Space systems — Avoiding collisions with orbiting objects [Tech Rep] | PUBLISHED | Finkleman, Dave & Oltrogge, Dan | USA | Technical Report published | 2013-12-01 | Initiate WG/SC review | 2014-12-01 | SC 14 Members | 3 Operations | Converted to Tech Rpt (SC 14 resolution 325)
16159 |  | 1 | Space systems — Launch pad and integration site — Analysis of failures | PUBLISHED | Tsukanov, Evgeny | Russia | International Standard published | 2012-08-15 | Initiate member body review | 2017-08-15 | Central Secretariat | 3 Operations
16164 |  | 1 | Space systems — Disposal of satellites operating in or crossing Low Earth Orbit | PUBLISHED | Cawthorne, Andrew | United Kingdom | International Standard published | 2015-07-01 | Initiate member body review | 2020-07-01 | Central Secretariat | 3 Operations | LDE request: 4/3/2013
16192 |  | 2 | Space systems —Experience gained in space projects (Lessons Learned) — Principles and guidelines | DIS - 12/17/2016 Pub - 12/17/2017 | Davey, John | UK | DIS text submitted to ISO/CS | 2016-01-13 | DIS circulation | 2016-04-30 | Central Secretariat | 5 Program Management | Pub: 2010; PL: Hannah Collins replaced by John Davey
16290 |  | 1 | Space systems — Definition of the Technology Readiness Levels (TRL) and their criteria of assessment | PUBLISHED | Safa, Frederic | ESA | International Standard published | 2013-11-01 | Initiate member body review | 2018-11-01 | Central Secretariat | 5 Program Management
16378 |  | 1 | Space systems — Measurements of thermo-optical properties of thermal control materials | PUBLISHED | Baba, Naoko | Japan | International Standard published | 2013-12-15 | Initiate member body review | 2018-12-15 | Central Secretariat | 6 Materials and Processes
16404 |  | 1 | Space systems — Programme management — Requirements management | PUBLISHED | Drogoul, Severin | France | International Standard published | 2013-11-15 | Initiate member body review | 2018-11-15 | Central Secretariat | 5 Program Management
16447 |  | 1 | Space systems — Selection of structural materials for space vehicles | CANCELLED | Menke, Manfred | Germany | Project deleted | 2001-12-01 |  |  |  | 1 Design Engineering
16448 |  | 1 | Space systems — Selection of production processes for space vehicles | CANCELLED | Menke, Manfred | Germany | Project deleted | 2000-05-18 |  |  |  | 1 Design Engineering | No longer in ISO database. Number assigned to another project (ISO/IEC).
16452 |  | 1 | Space systems — Thermal analysis — Exchange of mathematical models | CANCELLED | Fougeras, Jean | France | Project deleted | 2001-05-18 |  |  |  | 1 Design Engineering
16454 |  | 1 | Space systems — Structural design — Stress analysis requirements | PUBLISHED | Likhoded, Anatoly & Sidorov, Vladimir | Russia | International Standard confirmed | 2011-09-21 | Initiate member body review | 2016-09-21 | Central Secretariat | 1 Design Engineering
16456 |  | 1 | Space systems — Cables and wires — Arc tracking test | CANCELLED | Reher, Heinz-Joseph | Germany | Project deleted |  |  |  |  | 1 Design Engineering
16457 |  | 1 | Space environment (natural and artificial) — The Earth’s ionosphere model — International reference ionosphere (IRI) model and extensions to the plasmasphere | PUBLISHED | Bilitza, Dieter Gulyaeva, Tamara | USA, Russia | International Standard published | 2014-04-15 | Initiate member body review | 2019-04-15 | Central Secretariat | 4 Space Environments | Conversion of ISO/TS 16457 to an International Standard
16457 |  | 1 | Space environment (natural and artificial) — Earth's ionosphere and plasmasphere [Tech Spec] | PUBLISHED | Bilitza, Dieter | USA | TS published | 2009-02-03 | See new project (IS) above |  |  | 4 Space Environments | N811: Conversion to IS
16458 |  | 1 | Space systems — Unmanned spacecraft transportation — General requirements | PUBLISHED | Osipov, Sergei | Russia | International Standard confirmed | 2013-03-19 | Initiate member body review | 2018-03-19 | Central Secretariat | 3 Operations | Pub: 2004; Reaff: 2007
16679 |  | 1 | Space systems — Relative motion analysis elements after LV/SC separation | PUBLISHED | Qiang, Song | China | International Standard published | 2015-09-01 | Initiate member body review | 2020-09-01 | Central Secretariat | 3 Operations | Pub: 2015; NWIP: N778, N726
16691 |  | 1 | Space systems — Thermal control coatings for spacecraft — General requirements | PUBLISHED | Butrim, Victor | Russia | International Standard published | 2014-02-15 | Initiate member body review | 2019-02-15 | Central Secretariat | 6 Materials and Processes | NWIP: N719
16694 |  | 1 | Space systems — The measured parameters at firing bench and flight tests of liquid rocket engines | PUBLISHED | Vinogradov, Vladimir | Russia | International Standard published | 2015-03-01 | Initiate member body review | 2020-03-01 | Central Secretariat | 2 Interfaces | NWIP: N699
16695 |  | 1 | Space environment (natural and artificial) — Earth's internal magnetic reference field models | PUBLISHED | Maus, Stefan | USA | International Standard published | 2014-02-15 | Initiate member body review | 2019-02-15 | Central Secretariat | 4 Space Environments | NWIP: N701
16697 |  | 1 | Space systems — Safety and compatibility of materials — Method to determine the flammability thresholds of materials | PUBLISHED | Hirsch, David | USA | Systematic Review issued: 5 months | 2015-07-15 | National Votes Due | 2015-12-15 | SC 14 Members | 6 Materials and Processes | NWIP: N703; Tech Spec; Pub: 2012
16698 |  | 1 | Space environment (natural and artificial) — Methods for estimation of future geomagnetic activity | PUBLISHED | Iyemori, Toshihiko | Japan | International Standard published | 2013-05-01 | Initiate member body review | 2018-05-01 | Central Secretariat | 4 Space Environments | NWIP: N705
16699 |  | 1 | Space systems — Disposal of orbital launch stages | PUBLISHED | Finkleman, Dave | USA | International Standard published | 2015-11-01 | Initiate member body review | 2020-11-01 | Central Secretariat | 3 Operations | NWIP: N712; LDE request: 2/5/2015
16709 |  | 1 | Space environment (natural and artificial) — Realtime solar activity and space environment information for spacecraft operation | DIS - 10/5/2013 Pub - 10/5/2015 | Akioka, Maki | Japan | Results of DIS sent to PL | 2014-01-08 | CDV text needed from PL | 2014-06-30 | Project Leader | 4 Space Environments | NWIP: N615
16726 |  | 1 | Space systems — Human-life activity support systems and equipment integration in space flight — Techno-medical requirements for space vehicle human habitation environments — Requirements for the air quality affected by harmful chemical contaminants | DIS - 3/27/2015 Pub - 3/27/2016 | Guzenberg, Arkadiy | Russia | Results of CD/V sent to PL | 2014-08-07 | DIS text needed from PL | 2014-10-31 | Project Leader | 6 Materials and Processes | NWIP: N650; new timeline given (mistakenly cancelled by ISO/CS)
16749 |  | 1 | Space systems — Calculation for threaded fasteners | CANCELLED | Dacal, Rafael Bureo | ESA | Project deleted |  |  |  |  | 1 Design Engineering
16781 |  | 1 | Space systems — Simulation requirements for control system | PUBLISHED | Hongbo, Jin & Haitao, Tian | China | International Standard published | 2013-11-15 | Initiate member body review | 2018-11-15 | Central Secretariat | 1 Design Engineering | NWIP: N654
17255 |  | 1 | Space systems — Program management — Statement of work | PUBLISHED | Nan, Qiu & Guo, Jinyuan | China | International Standard published | 2014-05-15 | Initiate member body review | 2019-05-15 | Central Secretariat | 5 Program Management | NWIP: N751
17399 |  | 1 | Space systems — Man-systems integration | CANCELLED | Schultz, Larry | USA | International Standard Withdrawn | 2014-08-08 |  |  |  | 6 Materials and Processes | Formerly WG 3; Withdrawn via Systematic Review
17400 |  | 1 | Space systems — Launch and integration site general test requirements | PUBLISHED | Tsukanov, Evgeny | Russia | TR published | 2003-02-10 | Initiate WG/SC review | 2014-08-01 | Secretariat | 3 Operations
17401 |  | 1 | Space systems — Spacecraft interface requirements document for launch services | PUBLISHED | Boland, Philippe | France | International Standard confirmed | 2013-03-19 | Initiate member body review | 2018-03-19 | Central Secretariat | 2 Interfaces | Pub: 2004; Reaff: 2007
17520 |  | 1 | Space environment (natural and artificial) — Cosmic ray and solar energetic particle penetration inside the magnetosphere — Method of the effective vertical cut-off determination | DIS - 9/30/2015 Pub - 9/30/2016 | Nymmik, Rikho | Russia | Pub text submitted to ISO/CS | 2016-01-11 | Publication | 2016-03-31 | Central Secretariat | 4 Space Environments | Re-issue of N764 (PWI). NWIP: N953
17540 |  | 1 | Space systems — Liquid rocket engines and test stands — Terms and definitions | DIS - 10/5/2014 Pub - 10/5/2015 | Vinogradov, Vladimir & Makeev, Anton | Russia | FDIS text submitted to ISO/CS | 2015-12-16 | FDIS circulation | 2016-02-28 | Central Secretariat | 2 Interfaces | NWIP: N774; extended 1 yr
17546 |  | 1 | Space systems — Lithium ion battery for space vehicles — Design and verification requirements | DIS - 1/31/2015 Pub - 7/31/2016 | Kiyokawa, Takeshi | Japan | FDIS Ballot Concluded | 2016-01-18 | Publication | 2016-03-31 | Central Secretariat | 1 Design Engineering | NWIP: N775; extended 1 yr
17566 |  | 1 | Space systems — General test documentation | PUBLISHED | Haughton, Jim | USA | International Standard published | 2011-07-01 | Initiate member body review | 2016-07-01 | Central Secretariat | 2 Interfaces
17666 |  | 2 | Space systems — Program Management — Risk management | DIS - 6/22/2017 Pub - 6/22/2018 | Deak, Thomas | Canada | DIS initiated: 3 months | 2015-11-19 | National Votes Due | 2016-02-19 | SC 14 Members | 5 Program Management | Pub: 2003; Reaff: 2008
17689 |  | 1 | Space systems — Interface control documents between ground technological equipment, launch site systems and launch vehicle with payload | DIS - 9/19/2013 Pub - 3/19/2016 | Rulenkova, Anastasia & Rozhkov, Oleg | Russia | FDIS Ballot Concluded | 2015-08-10 | Publication | 2015-10-31 | Central Secretariat | 2 Interfaces | NWIP: N781
17761 |  | 1 | Space environment (natural and artificial) — Model of high energy radiation at low altitudes (300-600 km) | PUBLISHED | Mikhailov, Vladimir | Russia | International Standard published | 2015-11-15 | Initiate member body review | 2020-11-15 | Central Secretariat | 4 Space Environments | NWIP: N791
17762 |  | 1 | Space systems — Force limited vibration testing | DIS - 3/20/2015 Pub - 3/20/2016 | Bonk, Stephan | Germany | New project approved | 2012-03-19 | CD registration | 2013-03-19 | Project Leader | 2 Interfaces | NWIP: N790
17763 |  | 1 | Space systems — Human-life activity support systems and equipment integration in space flight | DIS - 3/20/2015 Pub - 3/20/2016 | Guzenberg, Arkadiy | Russia | Results of CD/V sent to PL | 2014-08-07 | DIS text needed from PL | 2014-10-31 | Project Leader | 6 Materials and Processes | NWIP: N789
17770 |  | 1 | Space systems — Cube satellites (CubeSats) | DIS - 3/20/2015 Pub - 3/20/2016 | Slane, Frederick | USA | DIS text submitted to ISO/CS | 2015-09-25 | DIS circulation | 2015-12-31 | Central Secretariat | 1 Design Engineering | NWIP: N788
17851 |  | 1 | Space systems — Space environment simulation for material tests — General principles and criteria | DIS - 3/11/2015 Pub - 3/11/2016 | Novikov, Lev; Butrim, Victor; & Kimoto, Yugo | Russia, Japan | Results of DIS sent to PL | 2016-01-13 | FDIS text needed from PL | 2016-02-29 | Project Leader | 4 Space Environments | N810: PWI; NWIP: N889
18146 |  | 1 | Space systems — Space debris mitigation design and operation guidelines for spacecraft [Tech Rpt] | PUBLISHED | Kato, Akira & Ikeuchi, Masayuki | Japan | International Tech Rpt published | 2015-10-01 | Initiate WG/SC review | 2016-10-01 | Secretariat | 7 Orbital Debris | Technical Report; NWIP: N817; formerly WG 3 project
18147 |  | 1 | Space environment (natural and artificial) — The method of the solar energetic protons fluences and peak fluxes determination [Tech Rpt] | PUBLISHED | Nymmik, Rikho | Russia | International Tech Rpt published | 2014-04-15 | Initiate WG/SC review | 2016-05-15 | Secretariat | 4 Space Environments | Technical Report (WG 4 resln); NWIP: N818
18197 |  | 1 | Space systems — Space based services requirements for centimeter class positioning | PUBLISHED | Furukawa, Toshio | Japan | International Standard published | 2015-05-01 | Initiate member body review | 2020-05-01 | Central Secretariat | 1 Design Engineering | NWIP: N825; Resln 322 conversion to TS; Resln 337 changed title & back to IS
18238 |  | 1 | Space systems — Closed loop problem solving management | PUBLISHED | Yuanying, Jiang | China | International Standard published | 2015-11-01 | Initiate member body review | 2020-11-01 | Central Secretariat | 5 Program Management | Pub: 2015; NWIP: N847
18257 |  | 1 | Space systems — Semiconductor integrated circuits for space applications — Design requirements | DIS - 7/23/2015 Pub - 7/23/2016 | Liu, Wenbao | China | Results of DIS sent to PL | 2015-04-28 | FDIS text needed from PL | 2015-06-30 | Project Leader | 1 Design Engineering | NWIP: N852
18322 |  | 1 | Space systems — General quality and safety requirements for space test centers | DIS - 5/17/2016 Pub - 5/17/2017 | Lino, Carlos | Brazil | Results of CD/V sent to PL | 2014-07-09 | DIS text needed from PL | 2014-08-31 | Project Leader | 2 Interfaces | NWIP: N853; formerly 18322-2
18667 |  | 1 | Space systems — Requirements for the management of capability-based Safety, Dependability, and Quality Assurance (SD&QA) programme | DIS - 3/11/2016 Pub - 3/11/2017 | Jackson, Tyrone | USA | Results of CD/V sent to PL | 2014-10-15 | DIS text needed from PL | 2015-12-31 | Project Leader | 5 Program Management | NWIP: N890
18676 |  | 1 | Space systems — Guidelines for the management of systems engineering | DIS - 3/11/2016 Pub - 3/11/2017 | Lahoz, Carlos | Brazil | CD/V initiated: 3 months | 2015-12-09 | National Votes Due | 2016-03-11 | SC 14 Members | 5 Program Management | NWIP: N891
18751 |  | 1 | Space systems — Safety and compatibility of materials — Method to determine the ignition susceptibility of materials and components to particle impact [Tech Spec] | DTS - 6/7/2015 Pub - 12/7/2015 | Peralta, Stephen | USA | New project approved | 2012-12-06 | DTS registration | 2013-09-30 | Project Leader | 6 Materials and Processes | Technical Specification; NWIP: N881
19473 |  | 1 | Space systems — Best practices for orbit elements at payload — LV separation [Tech Rpt] | PUBLISHED | Yu, Chunmei | China | International Standard published | 2015-09-01 | Initiate member body review | 2020-09-01 | Central Secretariat | 3 Operations | Re-issue of N902; Tech Rpt; NWIP: N984
19683 |  | 1 | Space systems — Design qualification and acceptance tests of lean satellites and units | DIS - 5/7/2016 Pub - 5/7/2017 | Cho, Mengu | Japan | CD/V initiated: 3 months | 2014-12-22 | National Votes Due | 2015-03-23 | SC 14 Members | 1 Design Engineering | Re-issue of N949; NWIP:1004; title change
19826 |  | 1 | Space systems — Programme management — Management of product characteristics | DIS - 6/10/2016 Pub - 6/10/2017 | Nan, Qiu | China | DIS initiated: 3 months | 2016-02-11 | National Votes Due | 2016-05-11 | SC 14 Members | 5 Program Management | Re-issue of N956 with revised title; NWIP: N1007
19923 |  | 1 | Space environment (natural and artificial) — Spacecraft potential estimation in worst case environment | DIS - 7/29/2016 Pub - 7/29/2017 | Toyoda, Kazuhiro | Japan | Results of CD/C sent to PL | 2015-12-05 | CDV text needed from PL | 2016-02-28 | Project Leader | 4 Space Environments | NWIP: N1021
19924 |  | 1 | Space systems — Acoustic testing | DIS - 7/29/2016 Pub - 7/29/2017 | Xiang, Shuhong | China | New project approved | 2014-07-28 | CD registration | 2015-07-31 | Project Leader | 2 Interfaces | NWIP: N1022
19933 |  | 1 | Space systems — Format for spacecraft launch environmental test report | PUBLISHED | Boland, Philippe | France | International Standard confirmed | 2015-12-17 | Initiate member body review | 2020-12-17 | Central Secretariat | 2 Interfaces | Pub: 2007; Reaff:2010, 2015
19971 |  | 1 | Space systems — Spacecraft and launch vehicle Combined Operation Plan (COP) at launch site — General format | DIS - 9/4/2016 Pub - 9/4/2017 | Shimizu, Masahiko & Schmitt, Denis | France, Japan | Results of CD/C sent to PL | 2016-01-11 | CDV text needed from PL | 2016-01-31 | Project Leader | 2 Interfaces | NWIP: 1025
20188 |  | 1 | Space systems — Product assurance requirements for commercial satellites | DIS - 12/8/2016 Pub - 12/8/2017 | Mori, Yasushi | Japan | CD/C initiated: 3 months | 2016-01-20 | National Comments Due | 2016-04-21 | SC 14 Members | 5 Program Management | NWIP: N1044
20584 |  | 1 | Space environment (natural and artificial) — Spacecraft charging — Earth orbit | DIS - 4/7/2017 Pub - 4/7/2018 | Ferguson, Dale | USA | New project approved | 2015-04-04 | CD registration | 2016-04-04 | Project Leader | 4 Space Environments | Re-issue of N1039. Project ISO/NP 20584. NWIP: N1100
20590 |  | 1 | Space systems — Debris mitigation design and operation manual for launch vehicle orbital stages [Tech Rpt] | DTR - 4/29/2016 Pub - 4/29/2018 | Kato, Akira & Aubin, Didier | Japan, France | New project approved | 2015-04-29 | DTR registration | 2016-04-29 | Project Leader | 7 Orbital Debris | Technical Report; NWIP: N1108
20780 |  | 1 | Space systems — Fiber optic components — Design and verification requirements | DIS - 7/31/2017 Pub - 7/31/2018 | Zhang, Bingxin & Chamayou, Bernard | China, France | CD/C initiated: 3 months | 2015-12-07 | National Comments Due | 2016-03-09 | SC 14 Members | 1 Design Engineering | NWIP: N1120
20891 |  | 1 | Space systems — Space batteries — Guidelines for easing in-flight health assessment [Tech Rpt] | DTR - 4/9/2018 Pub - 10/9/2018 | Barde, Henri | ESA | New project approved | 2015-10-01 | CD registration | 2016-09-30 | Project Leader | 1 Design Engineering | NWIP: N1136
20892 |  | 1 | Space systems — Launch complex — Modernization process: General requirements | DIS - 10/9/2017 Pub - 10/9/2018 | Rulenkova, Anastasia | Russia | New project approved | 2015-10-01 | CD registration | 2016-09-30 | Project Leader | 5 Program Management | NWIP: N1137
20893 |  | 1 | Space systems — Prevention of break-up of orbital launch stages | DIS - 10/2/2017 Pub - 10/2/2018 | Yanfeng, Gu | China | New project approved | 2015-10-01 | CD registration | 2016-09-30 | Project Leader | 7 Orbital Debris | NWIP: N1138
20907 |  | 1 | Space systems — General requirements for accreditation of space test centers and laboratories — Process | DIS - 7/8/2017 Pub - 7/8/2018 | Zhukov, Vladimir & Makeev, Anton | Russia | New project approved | 2014-07-11 | CD registration | 2015-07-11 | Project Leader | 2 Interfaces | Proposed as Part 1 in the ISO 18322 series; NWIP: N998; formerly 18322-1
20930 |  |  | Space systems — Calibration requirements for satellite-based passive microwave sensors | DIS: 12/7/2017 Pub: 12/7/2018 | Ishikawa, Takaaki | Japan | New project approved | 2015-12-05 | CD registration | 2016-12-05 | Project Leader | 1 Design Engineering | NWIP: N1142
20991 |  |  | Space systems — Requirements for small spacecraft | DIS: 12/7/2017 Pub: 12/7/2018 | Cho, Mengu & Benmeziane, Karim | Japan, France | New project approved | 2015-12-05 | CD registration | 2016-12-05 | Project Leader | 1 Design Engineering | NWIP: N1144
21095 |  |  | Space systems — Procedure for limiting risk of re-entering spacecraft and launch vehicle orbital stages | DIS: 12/7/2017 Pub: 12/7/2018 | Kato, Akira | Japan | New project approved | 2015-12-05 | CD registration | 2016-12-05 | Project Leader | 7 Orbital Debris | NWIP: N1152
21347 |  | 1 | Space systems — Fracture and damage control | PUBLISHED | Chang, James B. | USA | Results of SR submitted to WG Convenor | 2013-08-23 | WG recommendation | 2014-05-31 | WG Convenor | 1 Design Engineering | Pub: 2005; Reaff: 2008
21348 |  | 1 | Space environment (natural and artificial) — Solar irradiance determinations | PUBLISHED | Tobiska, Kent | USA | International Standard confirmed | 2015-12-17 | Initiate member body review | 2020-12-17 | Central Secretariat | 4 Space Environments | Pub:2007; Reaff: 2010, 2015
21349 |  | 1 | Space systems — Project reviews | PUBLISHED | Widmann, E. Richard | USA | Systematic Review issued: 5 months | 2016-01-15 | National Votes Due | 2016-06-15 | SC 14 Members | 5 Program Management | Pub: 2007
21350 |  | 1 | Space systems — Off-the-shelf item utilization | PUBLISHED | Widmann, E. Richard | USA | Systematic Review issued: 5 months | 2016-01-15 | National Votes Due | 2016-06-15 | SC 14 Members | 5 Program Management | Pub: 2007
21351 |  | 1 | Space systems — Functional and technical specifications | PUBLISHED | Drogoul, Severin | France | International Standard confirmed | 2013-08-26 | Initiate member body review | 2018-08-26 | Central Secretariat | 5 Program Management | Pub: 2005; Reaff: 2008, 2013
21648 |  | 1 | Space systems — Flywheel module design and test | PUBLISHED | Chang, James B. | USA | Revision Project Cancelled - Reinstatement planned | 2014-08-01 | Reinstatement | 2015-12-31 | Project Leader | 1 Design Engineering | Resolution for reinstatment needed + support of 4 P-members
22009 |  | 1 | Space environment (natural and artificial) — Model of Earth's magnetospheric magnetic field | PUBLISHED | Alexeev, Igor | Russia | International Standard confirmed | 2014-08-08 | Initiate member body review | 2019-08-08 | Central Secretariat | 4 Space Environments
22010 |  | 1 | Space systems — Mass properties control | PUBLISHED | MacNeil, Ian | USA | Revision Project Cancelled - Reinstatement planned | 2014-08-01 | Reinstatement | 2015-12-31 | Project Leader | 1 Design Engineering | Resolution for reinstatment needed + support of 4 P-members
22108 |  | 1 | Space systems — Non-flight items in flight hardware — Identification and control | PUBLISHED | Hobbs, Steven | UK | International Standard confirmed | 2011-09-19 | Initiate member body review | 2016-09-19 | Central Secretariat | 3 Operations
22538 | -1 | 1 | Space systems — Oxygen safety — Part 1: Hazards analysis for oxygen components and systems | PUBLISHED | Peralta, Stephen | USA | Systematic Review issued: 5 months | 2015-10-15 | National Votes Due | 2016-03-15 | SC 14 Members | 6 Materials and Processes | Pub: 2007
22538 | -2 | 1 | Space systems — Oxygen safety — Part 2: Selection of metallic materials for oxygen components and systems | PUBLISHED | Peralta, Stephen | USA | Systematic Review issued: 5 months | 2015-10-15 | National Votes Due | 2016-03-15 | SC 14 Members | 6 Materials and Processes | Pub: 2007
22538 | -3 | 1 | Space systems — Oxygen safety — Part 3: Selection of non-metallic materials for oxygen components and systems | PUBLISHED | Peralta, Stephen | USA | Systematic Review issued: 5 months | 2015-10-15 | National Votes Due | 2016-03-15 | SC 14 Members | 6 Materials and Processes | Pub: 2007
22538 | -4 | 1 | Space systems — Oxygen safety — Part 4: Design of oxygen components and systems | PUBLISHED | Peralta, Stephen | USA | Systematic Review issued: 5 months | 2015-10-15 | National Votes Due | 2016-03-15 | SC 14 Members | 6 Materials and Processes | Pub: 2007
22538 | -5 | 1 | Space systems — Oxygen safety — Part 5: Operational and emergency procedures | PUBLISHED | Peralta, Stephen | USA | Results of SR submitted to WG Convenor | 2015-10-01 | WG recommendation | 2015-11-30 | WG Convenor | 6 Materials and Processes | Pub: 2010
22538 | -6 | 1 | Space systems — Oxygen safety — Part 6: Facility planning and implementation | PUBLISHED | Peralta, Stephen | USA | International Standard confirmed | 2015-12-17 | Initiate member body review | 2020-12-17 | Central Secretariat | 6 Materials and Processes | Pub: 2010; Reaff: 2015
23038 |  | 2 | Space systems — Space solar cells — Electron and proton irradiation test methods | DIS - 11/13/2016 Pub - 11/13/2017 | Imaizumi, Mitsuru | Japan | CD/V initiated: 3 months | 2015-12-07 | National Votes Due | 2016-03-09 | SC 14 Members | 1 Design Engineering | Pub: 2006; Reaff:2014
23039 |  | 1 | Space systems — Multi-junction solar cells — Measurement and calibration procedures | CANCELLED | Bailey, Sheila | USA | New project rejected |  |  |  |  | 1 Design Engineering
23041 |  | 1 | Space systems — Unmanned spacecraft operational procedures — Documentation | PUBLISHED | Miyashita, Makoto | Japan | International Standard confirmed | 2011-09-21 | Initiate member body review | 2016-09-21 | Central Secretariat | 3 Operations
23339 |  | 1 | Space systems — Unmanned spacecraft residual propellant mass estimation for disposal manoeuvres | PUBLISHED | Funayama, Tomoe | Japan | Systematic Review issued: 5 months | 2015-11-15 | National Votes Due | 2016-03-15 | SC 14 Members | 3 Operations
23460 |  | 1 | Space systems — Programme management — Dependability assurance requirements | PUBLISHED | Vergnault, Emmanuelle | France | Systematic Review issued: 5 months | 2016-01-15 | National Votes Due | 2016-06-15 | SC 14 Members | 5 Program Management | Pub: 2011
23461 |  | 1 | Space systems — Programme management — Non conformance control system | PUBLISHED | Kikuchi, Satoshi | Japan | International Standard confirmed | 2015-10-01 | Initiate member body review | 2020-10-01 | Central Secretariat | 5 Program Management | Pub: 2010; Reaff: 2015
23462 |  | 1 | Space systems — Guidelines to define the management framework for a space project [Tech Rpt] | CANCELLED | Deak, Thomas | Netherlands | Converted to International Standard | 2014-04-15 |  |  |  | 5 Program Management | Superseded - Converted to IS (see below)
23462 |  | 1 | Space systems — Defining the management framework for a space project | PUBLISHED | Deak, Thomas | Netherlands | International Standard published | 2014-04-15 | Initiate member body review | 2019-04-15 | Central Secretariat | 5 Program Management | ISO/TR 23462 to ISO 23462; NWIP: N848
24113 |  | 2 | Space systems — Space debris mitigation requirements | PUBLISHED | Stokes, Hedley | UK | International Standard published | 2011-05-11 | Initiate member body review | 2016-05-11 | Central Secretariat | 7 Orbital Debris | FDIS circulated to incorporate corrections (considered 2nd ed); formerly WG 3 project
24637 |  | 1 | Space systems — Electromagnetic interference (EMI) test reporting requirements | PUBLISHED | Sargent, Noel | USA | International Standard confirmed | 2014-08-08 | Initiate member body review | 2019-08-08 | Central Secretariat | 1 Design Engineering
24638 |  | 1 | Space systems — Pressure components and pressure system integration | UNDER REVISION | Chang, James B. | USA | International Standard for revision | 2011-10-03 | Committee draft (CD) registered | 2014-06-30 | Project Leader | 1 Design Engineering | Under revision per SC 14 N795
24917 |  | 1 | Space systems — General test requirements for launch vehicles | PUBLISHED | Isaev, Alexander | Russia | Results of SR submitted to WG Convenor | 2015-12-17 | WG recommendation | 2016-06-01 | WG Convenor | 2 Interfaces | Pub: 2010
26869 |  | 1 | Space systems — Small auxiliary spacecraft (SASC) to launch vehicle interface control document | PUBLISHED | Umesato, Masahiro | Japan | International Standard published | 2012-04-01 | Initiate member body review | 2017-04-01 | Central Secretariat | 2 Interfaces | Do immediate Amd to Ed1 to incorporate DIN/DE cmts?
26870 |  | 1 | Space systems — Launch pad and integration site operational documents | PUBLISHED | Tsukanov, Evgeny | Russia | International Standard confirmed | 2014-08-08 | Initiate member body review | 2019-08-08 | Central Secretariat | 3 Operations
26871 |  | 1 | Space systems — Explosive systems and devices | PUBLISHED | Chamayou, Bernard | France | International Standard published | 2012-12-01 | Initiate member body review | 2017-12-01 | Central Secretariat | 1 Design Engineering
26872 |  | 1 | Space systems — Disposal of satellites operating at geosynchronous altitude | PUBLISHED | Ailor, Bill | USA | Results of SR submitted to WG Convenor | 2015-12-17 | WG recommendation | 2016-06-01 | WG Convenor | 3 Operations | Pub: 2010
26885 |  | 1 | Space systems — Process for orbital information exchange | CANCELLED | Finkleman, Dave | USA | Project deleted |  |  |  |  | 3 Operations | Project transferred to CCSDS per WG 3 decision (Rome '08)
26900 |  | 1 | Space data and information transfer systems — Orbit data messages | PUBLISHED | CCSDS Nav WG | CCSDS | International Standard published | 2012-07-15 | Initiate member body review | 2017-07-15 | Central Secretariat | 3 Operations | Joint project with SC13/CCSDS [CCSDS 502.0-B-2]; re-issued 10/12 w/ CCSDS Corr (5/12); formerly ISO 22644
27025 |  | 1 | Space systems — Programme management — Quality assurance requirements | PUBLISHED | Drogoul, Severin | France | Results of SR submitted to WG Convenor | 2015-06-17 | WG recommendation | 2015-11-06 | WG Convenor | 5 Program Management | Pub: 2010
27026 |  | 1 | Space systems — Programme management — Project breakdown structures | PUBLISHED | Widmann, E. Richard | USA | Systematic Review issued: 5 months | 2016-01-15 | National Votes Due | 2016-06-15 | SC 14 Members | 5 Program Management | Pub: 2011; Correction issued 5/1/2011
27852 |  | 2 | Space systems — Estimation of orbit lifetime | DIS - 2/16/2017 Pub - 2/16/2018 | Oltrogge, Dan | USA | FDIS Ballot Concluded | 2016-01-30 | Publication | 2016-03-31 | Central Secretariat | 3 Operations | CIB Results: Revise at DIS stage.
27875 |  | 1 | Space systems — Re-entry risk management for unmanned spacecraft and launch vehicle orbital stages | PUBLISHED | Kato, Akira | Japan | International Standard published | 2010-03-01 | Initiate member body review | 2020-12-31 | Central Secretariat | 3 Operations | Pub: 2010; CIB: N1150 (Amd)
27875 | Amd1 | 1 | Space systems — Re-entry risk management for unmanned spacecraft and launch vehicle orbital stages — Amendment 1 | FDIS - 12/31/2015 Pub - 6/30/2016 | Kato, Akira | Japan | FDIS Ballot Concluded | 2016-01-30 | Publication | 2016-03-31 | Central Secretariat | 3 Operations
N0374 |  |  | Space systems — Launch collision avoidance | CANCELLED | Hasegawa, Mitsunori | Japan | Project deleted | 2006-10-20 |  |  |  | 3 Operations
N0440 |  |  | Space systems — General requirments for electrical and electronics | CANCELLED | Takahashi, Ichiro | Japan | New project rejected | 2007-02-07 |  |  |  | 1 Design Engineering
N0499 |  |  | Spacecraft reactant gauging | CANCELLED | Finkleman, Dave | USA | New project rejected |  |  |  |  | 3 Operations
N0718 |  |  | Mission assurance program planning | CANCELLED | Slane, Frederick | USA | New project rejected | 2010-12-01 |  |  |  | 5 Program Management
N0720 |  |  | Space systems — Glossary of terms for materials and processes | CANCELLED | Sorice, Andreia | Brazil | Project deleted | 2013-02-05 |  |  |  | 6 Materials and Processes
N0726 |  |  | Space systems — Relative motion analysis elements after LV/SC separation | CANCELLED | Qiang, Song | China | New project rejected | 2010-12-22 |  |  |  | 3 Operations | See N778 & ISO 16679
N0764 |  |  | Space environment (natural and artificial) — Cosmic ray and solar energetic particle penetration inside the magnetosphere: Method of the effective vertical cut-off determination | PWI | Nymmik, Rikho | Russia | New project approved | 2013-09-24 | See SC 14 N953 and ISO 17520 |  |  | 4 Space Environments | Project ISO/NP 17520; see N953
N0820 |  |  | Space environment (natural and artificial) — Procedure for obtaining worst case and confidence level of fluence using the quasi-dynamic radiation belts model | CANCELLED | Matsumoto, Haruhisa | Japan | New project rejected | 2012-06-19 |  |  |  | 4 Space Environments | Technical Specification
N0902 |  |  | Space systems — Calculation of orbit elements at spacecraft — Launch vehicle separation | CANCELLED | Yu, Chunmei | China | New project rejected | 2013-05-20 |  |  |  | 3 Operations
N0949 |  |  | Space systems — Design qualification and acceptance tests of small-scale satellite and units seeking low-cost and fast-delivery | PWI | Cho, Mengu | Japan | NWIP re-issued | 2014-01-14 | See SC 14 N1004 and ISO 19683 |  |  | 1 Design Engineering | Project ISO/NP 19275; registered as PWI; re-issued as SC 14 N1004
N0956 |  |  | Space systems — Programme management — Classification and management of product characteristics | CANCELLED | Nan, Qiu | China | Withdrawn | 2013-07-23 |  |  |  | 5 Program Management | Withdrawn by China (message sent on 7/23/13)
N0957 |  |  | Space systems — Small satellite best practices for operations and development | PWI | Finkleman, Dave | USA | Results of NWIP sent to PL | 2014-01-07 | Re-issue NWIP | 2014-04-07 | Project Leader | 3 Operations | Tech Spec; Project ISO/NP 19422; registered as PWI
N0977 |  |  | Space systems — Deliverable documentation for propulsion systems | CANCELLED | Zhang, Peng | China | New project rejected | 2014-01-08 |  |  |  | 2 Interfaces
N1005 |  |  | Space systems — Launch vehicle user's manual | CANCELLED | Huo, Yuqian | China | New project rejected | 2014-04-23 |  |  |  | 2 Interfaces
N1008 |  |  | Space systems — Launch and integration sites — Order of development of technical condition estimation techniques at operation phase | CANCELLED | Glazachev, Alexey | Russia | New project rejected | 2014-07-14 |  |  |  | 3 Operations
N1039 |  |  | Space environment (natural and artificial) — Spacecraft charging — Earth orbit | NWIP | Ferguson, Dale | USA | New project rejected | 2014-10-28 |  |  |  | 4 Space Environments | Project ISO/NP 20231
N1168 |  |  | Space systems — Magnetic testing | NWIP | Qi, Yanwen | China | NWIP initiated: 3 months | 2015-12-04 | National Votes Due | 2016-03-04 | SC 14 Members | 2 Interfaces
N1191 |  |  | Space systems — General requirements for control engineering | NWIP | Liu, Jiarun | China | NWIP initiated: 3 months | 2016-01-19 | National Votes Due | 2016-04-20 | SC 14 Members | 1 Design Engineering