## Sheet1
CCSDS Secretariat IT Development Project Priorities - Updated 08/01/2015
Task | Overview | Due Date | Timeline Issues | % Completed
RID System | - Develop New RID System in SharePoint 2010 for integration with rest of Framework | - 1/15/2015 - First Beta with Real 3 month Review - 5/15/2016 - Go Live | These dates could move by several weeks, if funding is available for new SPAM Filter, Firewall, or SSL Certificate. | 15%
Virtualize Mailman Mailing Lists) on Upgrades Hardware | - Currently resides on old CCSDS hardware. - Virtualizing hardware will allow for easier backups and better SPAM control. | - 2/28/2016 | Currently allocating 20% of billable hours to this effort. | 10%
New CCSDS SPAM Filter | - Current SPAM Filter is 10 years old and no longer supported. - Need modern SPAM filter in order to capture more SPAM, and have support. | Unknown - Will provide update to CMC when funding information becomes available. | Depends on funding with CCSDS Secretariat. Implementing this will cause a 2-4 week delay with the RID System. | 0%
New CCSDS Firewall | - Current Firewall will lose support on 12/31/2015, and CCSDS is at risk after that date. - New Firewall appliance is required for security and stability. | Unknown - Will provide update to CMC when funding information becomes available. | Depends on funding with CCSDS Secretariat. Implementing this will cause a 2-4 week delay with the RID System. | 0%
SSL Certificates on Mailman and CWE Websites | - https: added to both the CWE and Mailman. - Currently passwords are being passed unencrypted. | Unknown - Will provide update to CMC when funding information becomes available. | Depends on funding with CCSDS Secretariat. Implementing this will cause a 2-4 week delay with the RID System. There are many "hardcoded" http URLs in the CWE that would need corrected after implementation on the SSL Certificate. | 0%
CMC/CESG Polling System | Formal system for CMC/CESG (replaces existing) - Develop New Polling System in SharePoint 2010 - Requirements Known - Find solution for archiving all old polls - Add capability to have multiple “options” (like voting for multiple candidates) - Add ability to see quickly which items you’ve already voted on. | - 8/15/2016 |  | 0%
Standards Downloadable Software Library / “Gold Standard" Test Suite | - Requirments are unknown | TBD - To be directed by CMC | It is not know at this time what the requirements for this task is yet. | 0%
Redesign CCSDS.org Website | - Ensure it works well on mobile devices - Redevelop in SharePoint 2010 | TBD - To be directed by CMC | It is not know at this time what the requirements for this task is yet. | 0%
Develop a CCSDS.com Website | - Ensure it works well on mobile devices - Develop in SharePoint 2010 | TBD - To be directed by CMC | It is not know at this time what the requirements for this task is yet. | 0%