## Table 1
Approved CCSDS Projects that have changed their ECD-DA Since 11/15/2015
ECD-DA = Estimated Completion Date for Document Approved
Project Title | Charter | Document Type | Start Date | ECD-DA Was | ECD-DA Is Now | Total Estimated Time to Complete (in months) | ECD-DA Change in Months | Area Comments | Responding Agency | Agency Comment
Network Layer Security Adaptation Profile | 1.02 Security Working Group | Blue | 2012-04-12 | 2015-02-18 | 2017-06-30 | 54 | 28 | Delay due to resource issues, local facility security policy problems (Agency firewall rules), availability of equipment, etc. BB will be completed shortly now that the interagency testing has (finally) been completed. Once BB and YB are finished by WG and CTE the corresponding AD resolution and CESG / CMC polls will be issued.
Symmetric Key Management Rationale | 1.02 Security Working Group | Green | 2013-08-07 | 2017-06-02 | 2010-02-17 | 50 | 8 | The key management book was initially determined to be more of a "cook book" than a specification. However, it needed to be a specification for SDLS. Hence we determined that it made more sense to change the SecWG book to magenta and to write a more specific and testable blue book for SDLS. The magenta book is now tracking the development of the blue book. The Key Management Magenta Book is still on track to be completed in concert with the KM BB in the SDLS WG. The Green Book comes after the MB and hence we still think it will be produced during 2017.
XML Namespace Policy (Yellow Book) | 1.04 Space Assigned Numbers Authority Working Group | Yellow | 2007-01-03 | 2016-06-30 | 2016-01-03 | 106 | -4 | Delay due to unavailability of resources. YB will be completed shortlly.
Delta-DOR Quasar Catalogue development | 1.06 Delta-DOR Working Group | Magenta | 2013-03-12 | 2016-07-31 | 2017-08-31 | 44 | 13 | Project has been held up by delays in submitting the docs to the Secretariat, a confusion between AD and the WG chair, and by the delays due to the Secretariat contract change over. Both of these documents are listed as being in “Secretariat Document Processing”. I expect them to emerge for CESG voting shortly.(poll on going for RB Agency Review)
Delta-DOR operations - Issue 2 | 1.06 Delta-DOR Working Group | Magenta | 2013-03-12 | 2015-12-31 | 2016-08-31 | 32 | 7 | Project has been held up by delays in submitting the docs to the Secretariat, a confusion between AD and the WG chair, and by the delays due to the Secretariat contract change over. Both of these documents are listed as being in “Secretariat Document Processing”. I expect them to emerge for CESG voting shortly.(poll on going for RB Agency Review)
Producer Archive Interface Specification Tutorial | 2.01 Data Archive Ingestion WG | Green | 2008-10-28 | 2014-06-30 | 2016-05-31 | 90 | 23 | Book will be completed. Delivered to Secretariat in Nov15 for publication. Waiting for CESG poll.
INFORMATION PREPARATION TO ENABLE LONG TERM USE | 2.01 Data Archive Ingestion WG | Magenta | 2014-03-04 | 2016-05-30 | 2017-08-15 | 40 | 15 | Book will be completed. Now making very good progress. We have 2 months to the stage “Final WB submitted to AD for further processing”
Spacecraft Maneuver Message (SMM) | 2.02 Navigation WG | Blue | 2011-12-13 | 2016-10-15 | 2018-12-31 | 83 | 26 | Book will be completed. NAV WG is looking for the way forward. No resource is wasted. Please give the WG time.
Attitude Data Message (ADM) 5 Year Review Revision | 2.02 Navigation WG | Blue | 2015-04-16 | 2017-03-04 | 2018-07-31 | 42 | 16 | Book will be completed. Situation was unblocked at the Spring 16 CMC mtg, where ESA committed to develop prototype 2.
Tracking Data Message (TDM) 5 Year Review Revision | 2.02 Navigation WG | Blue | 2013-09-10 | 2016-10-15 | 2017-11-15 | 48 | 13 | Book will be completed. This 5-year revision is the result of the need raised by the WG to "revise". If we close it, it calls into question the validity of the CCSDS standards process.
Mission Operations - Mission Data Product Distribution Services | 2.04 Spacecraft Monitoring and Control WG | Blue | 2015-01-01 | 2014-01-01 | 2017-12-15 | 23 | 47 | Book will be completed. The book has been produced and is under internal review. The WG is looking for Prototype 2 sponsor.
XML Telemetric and Command Exchange (XTCE) 1.2 | 2.04 Spacecraft Monitoring and Control WG | Blue | 2008-01-01 | 2016-10-01 | 2016-11-16 | 105 | 10 | Book will be completed. Being this an OMG standard, we are waiting for the OMG approval.
Mission Operations - Message Abstraction Layer Binding to HTTP Transport and XML Encoding | 2.04 Spacecraft Monitoring and Control WG | Blue | 2015-03-30 | 2016-04-30 | 2017-01-30 | 22 | 9 | Book will be completed. The book has been produced and is under internal review. The WG is looking for Prototype 2 sponsor.
Mission Operations - Common Services | 2.04 Spacecraft Monitoring and Control WG | Blue | 2006-01-01 | 2016-12-30 | 2017-12-07 | 136 | 7 | Book will be completed. The book is the next priority of the WG once the other books currently in the production are publisheds under internal review. Both prototypes' sponsors have been identified.
Mission Operations - Monitor & Control Services | 2.04 Spacecraft Monitoring and Control WG | Blue | 2006-01-01 | 2016-06-30 | 2016-10-17 | 127 | 4 | Book will be completed. The Prototype 2 situation has been unblocked and the interoperability test are foreseen in the summer 2016.
Mission Operations - Message Abstraction Layer Binding to ZeroMQ Transport and CNES Binary Encoding | 2.04 Spacecraft Monitoring and Control WG | Blue | 2015-01-06 | 2016-12-31 | 2017-04-28 | 23 | 4 | Book will be completed. The book will be produced as for the indicated dates. Both prototypes' sponsors have been identified.
Mission Operations C++ API | 2.04 Spacecraft Monitoring and Control WG | Magenta | 2015-05-04 | 2011-01-16 | 2016-12-25 | 12 | 2 | Book will be completed. The book has been released by NASA only recently because of ITAR. No prototype requiredbeen identified.
Telerobotic Standard (Blue Book) | 2.06 Telerobotics WG | Blue | 2014-06-05 | 2016-02-04 | 2018-02-04 | 46 | 24 | The future of this books depends on the future of the entire WG.
Telerobotic Operations | 2.06 Telerobotics WG | Green | 2013-03-29 | 2015-11-13 | 2016-05-30 | 37 | 7 | Book will be completed. Delivered to Secretariat in Apr16 for publication. Waiting for CESG poll.
Cross Support Service Management: Planning Data Formats | 3.03 Cross Support Service Management Working Group | Blue | 2013-11-15 | 2016-03-30 | 2017-03-30 | 40 | 12 | Resource issues have emerged; best estimate at this time for ECD-DA is 30 June 2017
Cross Support Service Management: File Transfer, Ground Segment, Recommended Profile | 3.03 Cross Support Service Management Working Group | Blue | 2015-10-26 | 2017-01-30 | 2017-11-01 | 24 | 9 | 01 November 2017 is still best estimate at this time.
Evolutions of CCSDS recommendations for RF & Modulation systems, part 1 | 5.01 RF and Modulation Working Group | Blue | 2008-10-15 | 2014-12-28 | 2017-12-30 | 109 | 36 | This project calls mainly for updating document CCSDS 401 BB that is a collection of currently 109 individual self-standing recommendations. From 2008 until now, new items have been added to the project almost every year resulting in an overall shift of the project completion date. For instance, the impact of NGU requirements on existing telecommand recommendations, the inclusion of ACM/VCM jointly developed with the C&S WG as additional recommendation, or the alignment of the 8 GHz Earth exploration recommendation with the new 26 GHz recommendation were not included in the first version of the project. While some delay with some of the items is present and has been properly flagged at each meeting via the SLS area report (for instance with emergency communication, MSPA, 22 GHz modulations), the main cause of the date changes is the addition of new items to the project. Later this year, the WG will ask for including a revision of the DDOR recommendation and a new ranging technique (telemetry ranging) to the project. These requests, if accepted by CMC, will further delay the overall completion date as resources are normally not increased.. Additionally, this project is indicated as the one with the second longest delay (36 months.) However, the delay has to be scaled to the estimated duration: for instance 36/109 is about 33% whereas other projects that are ranked better have ratios like 24/46 or 52% or even 29/16 that corresponds to 55%. CMC shall be aware that this special project shall be regarded differently from the others. Splitting the project in 109+ individual projects just for showing that most of them are on time is not considered a good way forward.
TM Channel Coding for SCCC, Green Book | 5.02 Space Link Coding and Synchronization Working Group | Green | 2012-12-22 | 2015-06-19 | 2017-05-26 | 52 | 23 | Delay due to lower priority work.
TM Channel Coding for DVB-S2, Green Book | 5.02 Space Link Coding and Synchronization Working Group | Green | 2013-06-05 | 2015-04-30 | 2016-07-29 | 38 | 15 | Delay due to lower priority work. Book is now waiting Secretariat processing for issuing the CESG / CMC polls for publication.
Update TM channel coding Blue Book with LDPC slicing | 5.02 Space Link Coding and Synchronization Working Group | Blue | 2014-03-18 | 2016-01-02 | 2017-01-27 | 34 | 12 | Delay due to work slower than expected. CESG poll is on going for RB Agency review
Variable Code and Modulation (VCM) Systems for CCSDS | 5.02 Space Link Coding and Synchronization Working Group | Magenta | 2014-03-18 | 2017-01-03 | 2017-06-01 | 33 | -2 | Delay due to work slower than expected. A resolution for RB Agency review is going to be raised
Image Data Compression, Issue 2 | 5.03 Multispectral and Hyperspectral Data Compression Working Group | Blue | 2012-01-06 | 2015-01-06 | 2017-05-26 | 59 | 24 | SLS Area resolution issued to request promotion to Red Book. CESG Poll just approved and ready to start CMC Poll.Delay originated due to resource shortage during 2010-2014
Spectral Pre-Processing Transform for Multispectral & Hyperspectral Image Compression | 5.03 Multispectral and Hyperspectral Data Compression Working Group | Blue | 2013-11-29 | 2016-01-01 | 2017-05-26 | 41 | 16 | SLS Area resolution issued to request promotion to Red Book. Delay originated due to resource shortage during 2010-2014
Unified Space Data Link Protocol Blue Book | 5.04 Space Link Protocols Working Group | Blue | 2014-10-25 | 2012-12-16 | 2018-12-09 | 46 | 21 | Delays due to priority work on other books and elapsed time to reach consensus. RB has been delivered to Secretariat for issue of CESG / CMC polls authorising start of Agency Review
Unified Space Data Link Protocol Green Book | 5.04 Space Link Protocols Working Group | Green | 2013-10-24 | 2016-03-22 | 2017-09-20 | 35 | 18 | See explanation above.
Space Data Link Security Concept of Operation, Issue 1 | 5.09 Space Data Link Security WG | Green | 2008-11-28 | 2015-05-15 | 2016-12-15 | 95 | 19 | Final editing and review by the WG is planned for June 2016. Transfer to the CCSDS editor for publication resolution before September 2016. Delay due to scarce availability of resources for a lower priority Green Book.
Space Data Link Security (SDLS) protocol : extended procedures | 5.09 Space Data Link Security WG | Blue | 2011-11-17 | 2017-02-15 | 2017-07-15 | 67 | 5 | RB for Agency Review planned for Fall 2016. Delays due to complexity of specification and resources dedicated to other high priority books
Optical Communications Concepts and Terminologies | 5.10 Optical Communications Working Group | Green | 2013-12-28 | 2016-03-03 | 2019-01-01 | 59 | 33 | Lower priority item. The WG gave priority to the GB on Atmospherics and the 2 BBs.
Optical Communications Physical Layer | 5.10 Optical Communications Working Group | Blue | 2013-12-28 | 2017-01-03 | 2019-01-01 | 59 | 22 | Delay is due to lack of consensus on the near Earth Scenario for High data rate
Optical Communications Coding & Synchronization | 5.10 Optical Communications Working Group | Blue | 2013-12-28 | 2017-01-03 | 2019-01-01 | 59 | 22 | Delay is due to lack of consensus on the near Earth Scenario for High data rate
Atmospheric Characterization for Optical Communications Systems | 5.10 Optical Communications Working Group | Green | 2013-12-28 | 2016-03-03 | 2017-01-01 | 36 | 10 | Initial schedule was too optimistic. AD raised a resolution for GB Publication. CESG / CMC polls to be issued by Secretariat.
Schedule-Aware Bundle Routing ]was Contact Graph Routing] for CCSDS | 6.09 Delay Tolerant Networking Working Group | Blue | 2015-04-15 | 2017-01-03 | 2012-01-17 | 31 | 9 | Delayed start of Project due to resource shortage. JAXA can now produce a prototype. Completion date is now end 2018
Voice and Audio Communications | 6.10 Voice Working Group | Blue | 2010-03-05 | 2016-09-30 | 2017-10-30 | 88 | 11 | The WG chair changed 3 times, and they were caught in the middle of a PICS definition cycle. The book is now in the final editing stage before going for CESG poll to release for agency review. Current target date: October 2017 (assumes revisions post agency review; if the agency review goes smoothly it could be sooner)
Green Book Update | 6.10 Voice Working Group | Green | 2016-05-04 | 2016-11-30 | 2017-01-07 | 15 | 8 | Completion date is confirmed. Delays are negligible.
CCSDS File Delivery Protocol (CFDP) Update -- Introduction and Overview | 6.12 CFDP Revisions Working Group | Green | 2013-09-13 |  | 2016-01-03 | 29 | 16 | See explanation on CFDP BB and YB
CCSDS File Delivery Protocol (CFDP) Update -- Implementer's Guide | 6.12 CFDP Revisions Working Group | Green | 2013-01-10 |  | 2016-01-05 | 30 | 16 | See explanation on CFDP BB and YB
CCSDS File Delivery Protocol (CFDP) Revisions -- Interoperability Test Plan and Report | 6.12 CFDP Revisions Working Group | Yellow | 2013-01-10 | 2015-01-22 | 2016-01-02 | 28 | 12 | Status: Need to identify 2nd prototype partner. Will start pursuing GSFC implementation as test partner if KARI cannot commit by end of June. Rationale for delays: ESA was supposed to provide 2nd prototype but their proposed prototype needed modifications that couldn’t be made in time. The WG is looking for alternatives and have identified several. Current target date: November 2017 but this WG is not consuming significant resources in the interim.
CCSDS File Delivery Protocol (CFDP) Update -- Blue Book | 6.12 CFDP Revisions Working Group | Blue | 2013-09-13 | 2016-01-05 | 2016-08-08 | 34 | 4 | Status: Need to identify 2nd prototype partner. Will start pursuing GSFC implementation as test partner if KARI cannot commit by end of June. Rationale for delays: ESA was supposed to provide 2nd prototype but their proposed prototype needed modifications that couldn’t be made in time. The WG is looking for alternatives and have identified several. Current target date: November 2017 but this WG is not consuming significant resources in the interim.