## Slide 1: Action Items & Resolutions

## Slide 2: Action Items
Action Item on the CMC Members to identify what their agencies need for cross support for AOS uplink in the future.
Action Item on the Secretariat to add as a topic for the Fall CMC the consolidation of the SOIS and SIS program of work.
Action Item on the Secretariat to cross check the WG mailing lists users against the CWE users list. To complete by 30 August 2017
Action on the CCSDS Secretariat to check whether an individual with a CWE account can access the private areas of a working group.
  Completed – Response for minutes. CWE users are provided read only access to all private areas of the CWE. For the WGs for which they are registered within the CWE though, they are provided read/write access.
Action on CESG Chair to remind the WG chairs to clean the mailing lists.

## Slide 3: Action Items Continued
Action on the CCSDS Secretariat to remove the Liaison for the following organizations which do not have a CCSDS point of contact:
  CEOS
  COSPAR
  ISPRS
  ISO/IEC JTC 1 SC 2
  NISO
  NTSI
  OMG
  WMO
  Add ISO/IEC JTC 1/ SC 29 Liaison with CCSDS POC Rodney Grubbs as the Liaison with ISO Liaison Shinji Watanabe
  Add OMG Liaison Mario Merri with Steven MacLaird (OMG)
  Due Date – End of June
Action on the Secretariat to provide the updated Yellow Book text to the CESG. Due Date – End of June.
Action on the CMC Members – Each member should contact their agency to determine what the best opportunity is for discussing commercial participation with industry. To see how the CCSDS may engage more industry partners to develop space data system standards. CMC members will report during the mid-term teleconference. Due Date – Mid-Term Teleconference (September).
Action on the CCSDS Secretariat to determine a method for adding the strategic plan developed by J. Miro to the CCSDS public website on the strategic plan webpage. Due Date – TBD – Add to Secretariat IT Queue for review.
Action on the CCSDS Secretariat to draft letters of thanks to both ROSCOSMOS and San Antonio SwRI. Due Date – End of June

## Slide 4: Action Items Continued
Action on the CCSDS Secretariat to provide YB text regarding a notation on the expected priorities of the CCSDS Technical Editor. Due Date - end of July.
Action on the Secretariat to provide the list of IT Development projects and their expected complexity to complete (Hard, Medium, Easy). By end of June.
Action on the CESG to review the list of IT Development projects and to provide feedback to the Secretariat and CMC General Secretary regarding prioritization of requests. By End of July.
Action Item on the CESG Chair to organize a meeting between the IT Support team and the Agency Review teams to discuss what needs to be done for the RIDs system to be useful for the users. TBD based upon availability of Agency Review team.
Action item on the Secretariat to provide a response to the CMC on the plan to complete the current 10 blue book publications in the document editors queue. Due Date – By end of June.
Action on the CESG chair to work with the IOAG liaison, Michael Schmidt, regarding the participation he wants from CCSDS regarding the IOP. Due date – TBD by CESG Chair.

## Slide 5: Resolution
The CMC resolves that it does not believe the use of a Memorandum of Understanding (MOU) between the Object Management Group and CCSDS is a necessity to complete the coordination of activities between the two organizations. It requests that if the CCSDS liaison feels that it is necessary or beneficial to the CCSDS to obtain an MOU for collaboration with OMG that he provide justification detailing its necessity.
The CMC resolves that, after having reviewed the MP&S proposal for developing one blue book that it agrees with the approach to develop one blue book as stated in the charter and the current blue book project instead of dividing the book into separate projects.
The CMC resolves to approve the 12 reconfirmations provided by the CESG (on final notes will add all titles on slide 115)
The CMC resolves to approve the retirement of 910.11-B-1, 910.14-G-1 and A31.0-G-1. (Final notes will show full names)
The CMC resolves that:
“(1) The CMC recognizes the notional architecture as proposed by the DAI WG as a good basis for planning DAI’s future work in the digital archive arena.
(2) The CMC recognizes that for the work of the Digital Archive Ingest Working Group, it is important to interact with a community larger than the nominal CCSDS space agencies and for the ISO participation to be encouraged during the CCSDS Agency Review phase, in order to avoid extensive delays and rework in later ISO review phases. The CMC therefore resolves to express support for the inclusion of the ISO community in such review.”
CMC Resolution thanking the hosts – ROSCOSMOS and San Antonio Southwest Research Institute.