## ICPA Updates
Project Title | Document Number | Charter | IOAG Services | Document Type | Approval | Project Status | Start Date | Sched Pub | IOAG Priority | IOAG Need Date | IOAG Comments | CCSDS Response | CCSDS Comments | IOAG Priority | IOAG Need Date | IOAG Comments | Update Comments
Cross Support Service Management: Service Package Data Formats | 902.4 | 3.03 Cross Support Service Management Working Group | Service Management Function | Blue | Approved | Behind Schedule | 12/15/2017 | 12/31/2023 | Priority 1 | 12/31/2021 | Need date as per IOAG-24a decision | Agreed | Work in progress |  | 12/31/2023 |  | should be ready this year
Cross Support Service Management: Service Agreement and Service Configuration Profile Data Formats | 902.5 | 3.03 Cross Support Service Management Working Group | Service Management Function | Blue | Draft | N/A - No Tasks Completed |  |  | Priority 1 | 12/31/2022 | Need date as per IOAG-24a decision | Agreed | Draft project for this has been created. Work is expected to commence in 2019. Revised schedule will be issued once required resources have been formalised and project officially started. |  | 12/31/2024 |  | just shifted by two year
Cross Support Service Management: Event Sequence Data Format | 902.6 | 3.03 Cross Support Service Management Working Group | Service Management Function | Blue | Draft | N/A - No Tasks Completed |  |  | Priority 1 | 12/31/2022 | Need date as per IOAG-24a decision | Agreed | Draft project for this has been created. Work is expected to commence in 2019. Revised schedule will be issued once required resources have been formalised and project officially started. |  | 12/31/2024 |  | just shifted by two year
Cross Support Service Management: Service Catalog | 902.7 | 3.03 Cross Support Service Management Working Group | Service Management Function | Magenta | Draft | N/A - No Tasks Completed |  |  | Priority 2 | 12/31/2024 | Need date as per IOAG-24a decision | Agreed | Draft project for this has been created. Likely start date TBD, pending agreement on required resources.. | Priority 3 | TBD |  | not in current catalogue anymore
Cross Support Service Management: Service Accounting | 902.8 | 3.03 Cross Support Service Management Working Group | Service Management Function | Blue | Draft | N/A - No Tasks Completed |  |  | Priority 3 | 2028-01-01 | DLR only | Agreed | Draft project for this has been created. Likely start date TBD, pending agreement on required resources. Currently Low priority |  |  |  | not in current catalogue anymore
Cross Support Service Management: Management Services (Automation) | 902.1 | 3.03 Cross Support Service Management Working Group | Service Management Function | Blue | Draft | N/A - No Tasks Completed |  |  | Priority 3 | 12/31/2028 | DLR only | Agreed | Draft project for this has been created. Likely start date TBD, This depends on various other Service Management Books being published (or at least in a stable state) before work can begin. |  | TBD
Cross Support Service Management: Service Management Utilization Request Formats | 902.9 | 3.03 Cross Support Service Management Working Group | Service Management Function | Blue | Approved | Behind Schedule | 2016-01-02 | 07/30/2023 | Priority 1 | 12/31/2021 | Need date as per IOAG-24a decision | Agreed | Work in progress |  | 12/31/2023 |  | should be ready this year
Cross Support Transfer Services : Service Control CSTS |  | 3.06 Cross Support Transfer Services Working Group | Service Management Function | Blue | Draft | N/A - No Tasks Completed |  |  | Priority 3 | 12/31/2028 | Need date as per IOAG-24a decision. | Under Review | A draft project for this has been created. The project scoping is still being determined/worked inside the CSS area. A resolution for requesting formal project initiation is expected in fall 2019, with work tentatively set to get underway in early 2020. | Priority 2 | 12/31/2025 |  | needed for replacement of SLE Throw Events in case CSTS FF is used
Evolutions of CCSDS recommendations for RF & Modulation systems, part 1 | 401 | 5.01 RF and Modulation Working Group | All Service Catalog #1 and #2 Services | Blue | Approved | On Schedule | 10/15/2008 | 12/30/2023 | TBD | 12/31/2025 | Need date as per IOAG-24a decision. This BB is of global interest for IOAG but no specific update is required in the short term | Agreed | Work in progress.
Optical Communications Physical Layer (Issue 2) | 141 | 5.10 Optical Communications Working Group | Return All Frames Optical Service Return Channel Frames Optical Service | Blue | Approved | On Schedule | 2019-03-06 | 2022-01-04 | Priority 1 | 12/31/2020 | Need date as per IOAG-24a decision | Agreed | Project approved, work stared. |  | TBD |  | check with optical comms WG
Optical Communications Coding & Synchronization (Issue 2) | 142 | 5.10 Optical Communications Working Group | Return All Frames Optical Service Return Channel Frames Optical Service | Blue | Approved | Behind Schedule | 2019-01-06 | 2022-01-10 | Priority 1 | 12/31/2020 | Need date as per IOAG-24a decision | Agreed | Project approved, work stared. |  | TBD |  | check with optical comms WG
CSTS Offline Radio Metric Service |  | IOAG-requested | Validated Data Radio Metric Service | Blue | Draft | N/A - No Tasks Completed |  |  | Priority 3 | 12/31/2028 | Need date as per IOAG-24a decision. | Under Review | Future Work | TO BE REMOVED
Cross Support Transfer Services Working Group is the candidate WG, however this is not part of the charter and therefore no resources and schedule have been identified yet.
CSTS D-DOR Data Service |  | IOAG-requested | Delta DOR Service | Blue | Draft | N/A - No Tasks Completed |  |  | Priority 3 | 12/31/2028 | Need date as per IOAG-24a decision. | Under Review | Future Work | TO BE REMOVED
Cross Support Transfer Services Working Group is the candidate WG, however this is not part of the charter and therefore no resources and schedule have been identified yet.
CCSDS Delivery Agent |  | IOAG-requested | Forward Last Hop Delivery Service, Return First Hop Delivery Service | Blue | Draft | N/A - No Tasks Completed |  |  | Priority 3 | 12/31/2028 | Need date as per IOAG-24a decision. | Under Review | Too premature for discussion and agreement at CESG level due lack of resources to achieve committed Programme of work |  |  |  | SC#2
NO candidate WG and therefore no resources and schedule have been identified yet.
Time Transfer |  | IOAG-requested | Time Synchronization Service | Blue | Draft | N/A - No Tasks Completed |  |  | Priority 3 | 12/31/2028 | Need date as per IOAG-24a decision. | Under Review | Too premature for discussion and agreement at CESG level due lack of resources to achieve committed Programme of work |  |  |  | SC#2
NO candidate WG and therefore no resources and schedule have been identified yet.
Clock Correlation |  | IOAG-requested | Time Synchronization Service | Magenta | Draft | N/A - No Tasks Completed |  |  | Priority 3 | 12/31/2028 | Available at NASA? | Under Review | Too premature for discussion and agreement at CESG level due lack of resources to achieve committed Programme of work |  |  |  | SC#2
NO candidate WG and therefore no resources and schedule have been identified yet.
Time Synchronization |  | IOAG-requested | Time Synchronization Service | Blue | Draft | N/A - No Tasks Completed |  |  | Priority 3 | 12/31/2028 | Need date as per IOAG-24a decision. | Under Review | Too premature for discussion and agreement at CESG level due lack of resources to achieve committed Programme of work |  |  |  | SC#2
NO candidate WG and therefore no resources and schedule have been identified yet.
Forward CFDP-File Service |  | IOAG-requested | Forward CFDP File Service | Blue | Draft | N/A - No Tasks Completed |  |  | Priority 3 | 2028-01-01 | Need date as per IOAG-24a decision | Under Review | No CCSDS Agency has shown interest in this service yet. | TO BE REMOVED
Not yet assigned to a WG.
Forward Packets-File Service |  | IOAG-requested | Forward Packet File Service | Blue | Draft | N/A - No Tasks Completed |  |  | Priority 3 | 2028-01-01 | Need date as per IOAG-24a decision. | Under Review | No CCSDS Agency has shown interest in this service yet. | TO BE REMOVED
Not yet assigned to a WG.
Return CFDP-File Service |  | IOAG-requested | Return CFDP-File Service | Blue | Draft | N/A - No Tasks Completed |  |  | Priority 3 | 2028-01-01 | Need date as per IOAG-24a decision | Under Review | No CCSDS Agency has shown interest in this service yet. | TO BE REMOVED
Not yet assigned to a WG.
Return Packets-File Service |  | IOAG-requested | Return Packets File Service | Blue | Draft | N/A - No Tasks Completed |  |  | Priority 3 | 2028-01-01 | Need date as per IOAG-24a decision. | Under Review | No CCSDS Agency has shown interest in this service yet. | TO BE REMOVED
Not yet assigned to a WG.