## Action Items
AI # | Meeting | Concerning | Action | Assignee | Due Date | Status | DateClosed | Notes
221110-01 | Telecon | PDU encoding | Design a trade study for "solving" ASN.1 encoding vs other telemetry file formatting approaches | HD, MG, MS | 2023-01-17 | Open |  | Some other encoding schemes might include JSON. It may be that the some of the SLE concept is retained (e.g., TLM Frame + annotation).
22110-02 | Telecon | Use cases | Provide more information/further considerations from client side re how to get, e.g., tracking data, telemetry data | JL | 2023-01-17 | Open |  | What kind of APIs are involved? Based on work that J. Liao has already done with AWS
2