## Action Items
AI # | Meeting | Concerning | Action | Assignee | Due Date | Status | DateClosed | Notes
221110-01 | Telecon | PDU encoding | Design a trade study for "solving" ASN.1 encoding vs other telemetry file formatting approaches | HD, MG, MS | 2023-01-17 | Closed | 2023-01-19 | Some other encoding schemes might include JSON. It may be that the some of the SLE concept is retained (e.g., TLM Frame + annotation). 230119 Closure notes: BOF meeting conclusion is that likely for telemetry some sort of binary encoding will be offered that has fixed offsets for geting quickly to the telemetry frame vs metadata.
22110-02 | Telecon | Use cases | Provide more information/further considerations from client side re how to get, e.g., tracking data, telemetry data | JL | 2023-02-16 | Closed | 2023-02-16 | What kind of APIs are involved? Based on work that J. Liao has already done with AWS; 230119 -- Deferred until February 16 telecon.
230119-01 | Telecon | PDU encoding | Develop a table that shows the various data types and current encoding scheme and conceptually what will be done for encoding for cloud data delivery standard(s) | EB | 2023-02-16 | Closed | 2023-02-16 | WG conclusion on closure date is to allow "native" encoding (that already stated in the reommdentations) and then to have at least one alternate encoding on a per data type basis
230119-02 | Telecon | TDM XML Schema | Check to see if the TDM spec already includes an XML Schema definition | EB | 2023-01-23 | Closed | 2023-02-03 | TDM standard includes an XML Schema definition allong with "flat" Ascii encoding (KVN - Keyword Value Notation)
230119-03 | Telecon | Books | Based on standards shaping chart so far, identify the likely recommendation or reommendations to be produced by the eventual working group | EB + BOF | 2023-02-16 | Closed | 2023-02-16 | WG should double check books identified.
230216-01 | Telecon | Books | Reivew and provide comments (if any) re books identified as the deliverables for eventual WG | BOF | 2023-04-13 | Open |  | 230316 -- postponed to April 13
1