## Sheet1
Development schedule for FF-CSTS book
Mar. 13, 2018
External Dependencies:
(1) Extent of received RIDs and change requests
(2) Review/Approval from CESG/CMC
(3) Priority schedule of secretariat's documentation
(4) Resource availability from prototype partner.
(5) Security compliance requirement for prototype environment
1. RED BOOK |  | Notes
Whitebook completed | Apr. 2018
Internal WG review | May 2018 | Assume no significant issues raised by WG
Document submitted to AD | June 2018 | Subject to AD approval
Secretariat document preparation completed | Sep. 2018 | Subject to secretariat schedule
CESG Review | Sep. 2018 |  | Draft SFW Pink Book needed
Redbook Call for Review | Oct. 2018
Redbook review | Nov. 2018
Redbook RID resolution | Dec. 2018 | Subject to received RID inputs and extent of changes
2. PROTOTYPE
Prototype started (based on draft Redbook) | Apr. 2018
Test Plan document | June 2018
Prototype completed | Dec. 2018 | Subject to GSFC resource & prototype environment compliance with security requirements
Test Report document | Dec. 2018
3. BLUE BOOK
Bluebook "package" drafted | Feb. 2019
Secretariat preparation completed | Mar. 2019 | Subject to secretariat schedule
Bluebook Call for Review | Apr. 2019 | Subject to AD/CESG approval
Bluebook review | May 2019
Bluebook RID disposition | Jun 2019 | Subject to received RID inputs and extent of changes
Bluebook published | July 2019 | Subject to CESG approval