## Sheet1
# FR | Creator | Editor | Reviewer | Status
Antenna | "CSS Area" | Wolfgang | Tim | Review until 15th of May 2019
Forward 401 Space Link Carrier Transmission | "CSS Area" | Wolfgang | Tim | 80% editing done, Review
Forward Link Ranging | "CSS Area" | Wolfgang | Harald | Review
Forward TC Sync and Channel Encoding | "CSS Area" | Wolfgang |  | Some editing left - 9 pages errata
Fwd AOS Sync and Channel Encoding | "CSS Area" | John / Tim | SLS feedback pending | Awaiting implementation of Kent Andrews suggestion
Forward TC MC Mux | "CSS Area" | John |  | 11 pages of errata
Forward TC VC Mux | "CSS Area" | John |  | 95% complete
Forward TC Encap VC Pkt Processing & VC Gen | "CSS Area" | Wolfgang |  | 90% editing complete no review yet
Forward Encap & MAP Pkt Processing | "CSTS WG" | Wolfgang |  | 90% editing complete no review yet
Forward (TC?) MAP Mux | "CSTS WG" | Wolfgang |  | 90% editing complete no review yet
Forward TC MC Mux | "CSS Area" | John |  | Some material in the FR Reference Model, but none in the XML file
Forward TC VC Mux | "CSS Area" | John |  | Some material in the FR Reference Model, but none in the XML file
Forward TC Encap VC Pkt Processing & VC Gen | "CSS Area" | Wolfgang |  | Not started
Forward Encap & MAP Pkt Processing | "CSTS WG" | Wolfgang |  | Not started
Forward (TC?) MAP Mux | "CSTS WG" | Wolfgang |  | Not started
Forward AOS MC Mux | "CSS Area" | John |  | Not started
Forward AOS VC Multiplexing | "CSTS WG" | John |  | Not started
Forward AOS Encapsulation, Packet Processing and VC Generation | "CSTS WG" |  |  | Not started
Forward-CLTU-Transfer-Service-Provider | "CSS Area" | Wolfgang |  | 90% editing complete no review yet
Forward Frame CSTS Provider | "CSTS WG" | John |  | Not started
FSP TS Provider | "CSTS WG" | Wolfgang |  | 90% editing complete no review yet
CFDP Entity | "CSTS WG" | Holger | Felix Flentge | Type definitons missing, rethink one FR for sending and receiving
Forward File Server | "CSTS WG" |  |  | Not started
Forward File Data Store | "CSTS WG" |  |  | Not started
TGFT Host (was Cross Support File Transfer Service Provider) | "CSTS WG" | Discuss in CSS Area: what is the approach? |  | Not started
Return 401 Space Link Carrier Reception | "CSS Area" | Wolfgang | Harald | 80% editing done, Review
Return Range and Doppler Extraction | "CSS Area" | Wolfgang | Harald | Review
Return Telemetry Synchronization and Decoding | "CSS Area" | Wolfgang |  | Some editing left - 2 pages errata
Return TM MC Demux & Reception | "CSTS WG" | Wolfgang/ John? |  | 95% complete. Needs to be tuned to TM
Return TM VC Demux & Reception | "CSTS WG" | Wolfgang/ John? |  | 95% complete. Needs to be tuned to TM
Retunr TM Packet Extraction & De-encapsulation | "CSTS WG" | Wolfgang/ John? |  | Most parameters are defined, no events, no directives. Needs to be tuned to TM
Return AOS MC Demux & Reception | "CSTS WG" | Wolfgang/ John? |  | 95% complete. Needs to be tuned to AOS
Return AOS VC Demux & Reception | "CSTS WG" | Wolfgang/ John? |  | 95% complete. Needs to be tuned to AOS
Return AOS Packet Extraction & De-encapsulation | "CSTS WG" | Wolfgang/ John? |  | Most parameters are defined, no events, no directives. Needs to be tuned to AOS
Return USLP MC Demux & Reception | "CSTS WG" | Wolfgang/ John? |  | Not started
Return USLP VC Demux & Reception | "CSTS WG" | Wolfgang/ John? |  | Not started
Return USLP Packet Extraction & De-encapsulation | "CSTS WG" | Wolfgang/ John? |  | Not started
Frame Data Sink | "CSTS WG" | John |  | Not started
Offline Frame Buffer | "CSTS WG" | John |  | Not started
Return All Frames Transfer Service Provider | "CSS Area" | Wolfgang |  | 95% complete
RCF TS Provider | "CSTS WG" | Wolfgang |  | 95% complete
ROCF TS Provider | "CSTS WG" | Wolfgang |  | 95% complete
CFDP Receiving Entity | "CSTS WG" | Wolfgang / Felix Flentge |  | Type definitons missing, rethink one FR for sending and receiving
Return File Server | "CSTS WG" |  |  | Not started
Return File Data Store | "CSTS WG" |  |  | Not started
TDM Segment Generation | "CSTS WG" | John |  | Not started
TDM Sink | "CSTS WG" | John |  | Not started
TDM Recording Buffer | "CSTS WG" | John |  | Not started
Real-Time Tracking Data CSTS Provider | "CSTS WG" | John |  | Not started
Open-Loop Receiver/Formatter | "CSTS WG" | Wolfgang | Tim | Parameters according to ESA equipment defined
Open Loop Data Store | "CSTS WG" |  |  | Not started
D-DOR Raw Data Collection | "CSTS WG" |  |  | Not started
D-DOR Raw Data Store | "CSTS WG" |  |  | Not started
Raw Radiometric Data Collection | "CSTS WG" |  |  | Not started
Raw Radio Metric Data Store | "CSTS WG" |  |  | Not started
Validated Radiometric Data Store | "CSTS WG" |  |  | Not started
Monitored Data CSTS Provider | "CSS Area" | John |  | Not started
Monitored Data Collection | "CSTS WG" | Take it out? |  | Not started
Service Control CSTS Provider | "CSTS WG" |  |  | Not started
Service Control Production | "CSTS WG" |  |  | Not started
415 Forward and Return Carrier and Ranging - may be split into several FRs | "CSTS WG" | Tim |  | Not started