## Open Action Items
Date | Action ID | WG | Action | Assignee | Due Date | Status | Comment
2014-03-31 | AI#03 | RAC | Continue review of the training modules. Forward comments to Steve Hughes for inclusion in master version. | ALL | TBD | Closed | 20140605 - JGG reports that RAC is creating training modules. DG has completed drafts of several modules and they are being reviewed. Once Training Course is complete and used, it will be source material for the RAC GB 20140617 - About 8 of about 15 modules completed. RAC is planning class last of September and first of October in London 20140718 - JGG reported that drafts of all but 1 of the training modules are completed. Registration for the London class is open 20140814 - JGG reported that sufficient sign-ups have been received to ensure that class will be held Sept 29-Oct 03. Teachers are David, Simon, Mariella and JGG. Modules are going through a final review and associated exercises and quizes are being created. 20140904 - JGG reported that instructors are continuing work on module presentations as well as associated exercises and exam questions. There are currently 12+ people registered for the class and limited spaces are still available. 20140922 - JGG reported that initial class is next week. At the next meeting he will report on how it went. 20141030 - JGG reported that the initial class was presented to about 15 students and went well. Training modules are being updated based on feedback and experience with the class. Another class is planned for California in mid to late January.
2014-03-31 | AI#06 | DAI | Continue to monitor progress of towards approval as an ISO Standard 20104 and report back as status changes | DB JGG | As needed | Open | 20140605 - JGG reports that TG told us that PAIS Standard has been sent to ISO TC20/SC13 as a project. PAIS does not yet show up on website as a project. 20140613 - JGG requested status information from Nick T 20140718 - JGG reported that PAIS has not been assigned a number yet, but Nick will check on status 20140814 - JGG reported that PAIS has been assigned ISO # 20104 20140922 - Awaiting word on publication of DIS and start of balloting. Should be taking place any day. 20141030 - PAIS is under review. Due date for comments is 15 December 2014
2014-03-31 | AI#09 | DAI | Investigate location to host test cases (example data and tool inputs and outputs) | DB | TBD | Open | 20140605 - On hold until GB Test Cases are nearing completion 20140904 - DB has received authorization to publish information on a CNES system. Work is still needed to get it setup.
2014-03-31 | AI#10 | DAI | Ask for access to SIP builder to CNES web site | DB | TBD | Open | 20140605 - On hold until GB Test Cases are nearing completion 20140904 - DB has received authorization to publish information on a CNES system. Work is still needed to get it setup.
2014-03-31 | AI#13 | DAI | Check with NASA re. making data from GB test case available | MM | TBD | Open | 20140605 - On hold until GB Test Cases are nearing completion
2014-03-31 | AI#20 | DAI | Generate a draft 0 strawman of the ICP MB for comment by DAI WG | JGG | 2014-11-03 | Open | 20140506 - Early version has been distributed for comment. 20140605 - Awaiting comments on Introduction and Terminology items already distributed. Another version will be sent possibly for next telecon. 20140718 - Comments only from DB. Also received slightly updated LTDP materials. Still awaiting comments from others. Plan to generate an updated draft incorporating any comments received. 20140810 - Updated Proposed ICP Purpose and Scope and Terminology distributed. 20140921 - Proposed Terminology discussed with LTDP group. Will incorporate new agreements into draft. | 2014-06-05 | 2014-07-03 | 2014-08-10 | 2014-09-16
2014-03-31 | AI#24 | DAI | Work with MB of SANA as required to ensure CCSD ADIDs in PAIS (and other DAI standards) are registered. | JGG | As needed | Open | 20140605 - Registry has not yet been setup in SANA. DB will contact SANA regarding its status.
2014-03-31 | AI#25 | DAI | Contact Brian Oliver, CCSDS IT support, to have links to the XSD schemas added to the PAIS and XFDU entries on the publication page | TG | TBD | Closed | 20140605 - Registry has not yet been setup in SANA. DB will contact SANA regarding its status 20140807 - DAI Registry moved to approved area of SANA 20140904 - DB has contacted Brian Oliver . We will open a new AI (20140914 AI#1) for him.
2014-03-31 | AI#26 | DAI | Contact Brian Oliver, CCSDS IT support, to implement a solution re. forwarding links to previous issues of documents. (JGG is available for details) | TG | TBD | Closed | 20140605 - Expect this to be done at same time as links to registry are added 20141112 - TG contacted BO. A new AI (20141110 AI#33) has been opened for JGG to follow up with BO and TG to get the forwarding documents installed in the CCSDS website.
2014-04-16 | 4 | DAI | Provide example of XFDU with referenced data objects (remote URL or URI) | SM | 2014-06-xx | Open | Don't have examples, needs to create new examples 20141030 - No progress
2014-04-16 | 9 | DAI | Explain more (in GB) the CCSD0015: how it is registered and reference where more information could be found on that subject (also explain how to define and use a locally defined format) | SM | 2014-06-05 | Open | CCSDS-630.0-B-1 defines Control Authority Procedures. CCSD ADIDs are defined in CCSDS documents. CCSD0015 is defined in PAIS BB 20141030 - No progress
2014-04-16 | 15 | DAI | Send comments on LTDP Process. | All | 2014-06-19 | Open | 20140605 - Message with attachments are not making it through MOIMS-DAI mailing list. The group did not receive the materials before today's telecon. Comments should be provided by next telecon 20141030 - DB has updated version that she will send out w/ her comments | 2014-06-05
2014-04-16 | 17 | DAI | Follow the work of LTDP group on preservation process, and send all available information to the DAI group on this subject. | DB | Ongoing | Open | Daniele: I have asked M. Albani to be member and in the DAI list. We await his answer. 20140717 - DB forwarded updated materials from LTDP group 20141030 - DB has been forwarding materials forom LTDP group as the are provided.
2014-04-16 | 18 | DAI | EUMETSAT has shown interest in the use of PAIS and asked for SIP builder. Wait for green book and test cases. |  | Future | Open | 20140904 - EUMETSAT has asked again if the GB is ready
2014-06-05 | 1 | DAI | Contact J.Faundeen on subjects of interest and invite him to participate in DAI | DS | 2014-06-19 | Open | 20141030 - No progress
2014-06-19 | 4 | DAI | Provide ideas for collaboration/coordination with other standardization efforts | All | ongoing | Open | 20141030 - Mike has provided some links
2014-07-18 | 7 | DAI | Plan the DEDSL project (currently behind schedule). Move the plan of the XML control authority | All | 2014-08-13 | Open | 20140904 - Plan is to do this next year 20141030 - CNES will have to wait for budget to address this
2014-07-18 | 8 | DAI | Ask Brian Oliver for a solution to improve the access to PAIS blue book when searching with internet (RB comes up first) | DB | 2014-08-13 | Open | 20140904 - DB has asked the question, but BO does not have a solution 20141030 - No answer yet. We will speak about this at the CCSDS meeting
2014-08-14 | 5 | DAI | Check if there is a section about hierarchy of collections in the tutorial. If not, add it with example and explanation. | SM | 2014-11-06 | Open | 20141030 - This will be in the new version | 2014-09-03
2014-08-14 | 6 | DAI | Check if there is a section about type of group structure in the tutorial. (see 20140814 minutes) | SM | 2014-11-06 | Open | 20141030 - This will be in the new version | 2014-09-03
2014-08-14 | 7 | DAI | Check if there is a section about the dataObjectTypeOccurrence in the tutorial. If not, add it case showing the different possibilities and explanation for use of one or the other. (see 20140814 minutes) | SM | 2014-11-06 | Open | 20141030 - This will be in the new version | 2014-09-03
2014-08-14 | 8 | DAI | Correct the generation of the ISEE SIP Manifest from the SIP Builder | SM | 2014-08-28 | Open | 20141030 - Manifests have been updated manually. We need to identify what in SIP Builder needs to be updated to address this issue.
2014-09-04 | 1 | DAI | Add links to the XSD schemas in SANA DAI registry to the PAIS and XFDU entries on the publication page | BO | 2014-09-22 | Open
2014-09-04 | 4 | DAI | Provide analysis of Reference Architecture for Space Information Management (RASIM) (including overlaps with DAI projects) | MM | 2014-09-21 | Open | 20141007 - MM sent email discussing RASIM and RASDS
2014-09-04 | 6 | DAI | Send comments on ISEE test case (email from DS 20140903) | All | 2014-10-11 | Open | 20140921 - DS distributed a new version | 2014-07-03
2014-09-22 | 1 | DAI | Update the definitions in the terminology document according to the discussions of the day and provide to LTDP Group | CCSDS DAI WG | 2014-09-29 | Open
2014-09-22 | 2 | DAI | Provide answers to the analysis in the discussion part of the proposed terminology document | LTDP Group | 2014-09-29 | Open
2014-09-23 | 1 | DAI | Finalize updates of ISEE manifests and send to DS | DB | 2014-09-29 | Open
2014-09-23 | 4 | DAI | Ask David for RAC sessions for CCSDS fall meeting 1 day (feedback on training sessions, certiication status,etc.) | JGG | 2014-10-03 | Open
2014-10-09 | 2 | DAI | Update PAIS Wrap-up | MM | 2014-10-29 | Open | 20141030 - MM just received JGG's comments.
2014-10-09 | 3 | DAI | Initiate table taking into account the timeline and showing ICP, LTDP (EO) and other communities, –see also the last slide of presentation sent by MM (data once in the Archive: use archival terminology, outside the Archive: more related to domains/communities). | DB | 2014-10-29 | Open
2014-10-09 | 4 | DAI | Look at RASIM documentation and identify links to ICP | All | 2014-10-29 | Open
2014-10-09 | 6 | DAI | Check the last version of the ESA test case | MM | 2014-10-29 | Open
2014-10-30 | 1 | DAI | Send an updated version of the CoRoT test case | SM | 2014-11-07 | Open
2014-10-30 | 2 | DAI | Updated the sentence in the SAFE test case concerning the size of the data | DB | 2014-11-07 | Open
2014-10-30 | 3 | DAI | During meeting ask SANA if there is a possibility to store software and test cases | DB JG | 2014-11-14 | Open
2014-11-10 | 1 | RAC | Determine during meeting if RAC GB project should be continued. | ALL RAC WG | 2014-11-14 | Closed | 20141114 It was determined during the meeting that the RAC GB project should be terminated. Training activities will be conducted outside of CCSDS by PTAB.
2014-11-10 | 2 | RAC | Determine during meeting if DAI and RAC WGs should be merged. | ALL DAI ALL RAC | 2014-11-14 | Closed | 20141114 It was determined that RAC WG should be closed and its activities and responsibility for its documents should be merged into the DAI WG.
2014-11-10 | 3 | DAI | Generate table with 2 diagrams explaining the 2 ISEE SIP interpretations | DB SM | 2014-11-12 | Closed | 20141112 A couple versions of the figure were created. The final version is included in London minutes.
2014-11-10 | 4 | DAI | Following generation of table, update ISEE test case description describing table and provide generalized description of issue for GB core (3.3, 4.1,or 4.3) | DS
2014-11-10 | 5 | DAI | Update CoRoT test case with expanded view of steps for SIP ingestion | SM
2014-11-10 | 6 | DAI | Review terminology used to identify data objects [Level 0, N0, Product, Product-Set] in all test cases to ensure consistency and understanding by those outside of the Space community | SM
2014-11-10 | 7 | DAI | Provide feedback on efficacy of step by step example of archive | MM
2014-11-10 | 8 | DAI | Implement agreed changes in GB core and distribute to group for further review | SM
2014-11-10 | 9 | DAI | Generate METS PAIS model by next telecom PM tomorrow | DB | 2014-11-12 | Closed | 20141112 Model sent to meeting participants
2014-11-10 | 10 | DAI | Send group SIP Manifest and objects | SR | 2014-11-12 | Closed | 20141112 Materials sent to meeting participants
2014-11-10 | 11 | DAI | Send all METS info out to group for review before telecom tomorrow PM | DB | 2014-11-12 | Closed | 20141112 Materials sent to meeting participants
2014-11-10 | 12 | DAI | Send corrected METS Model, and SIP Constraints to Group | DB
2014-11-10 | 13 | DAI | Send the Excel table mapping between the PAIS Model and METS (SIP elements with Model IDs) and the METS manifest including the PAIS elements | BnF
2014-11-10 | 14 | DAI | Provide a solution the model the BnF metadata part directly included in the METS Manifest (i.e. there is no separate file) | All
2014-11-10 | 15 | DAI | Send updated naming convention example (Sec. 4.1.1) and descriptorModelID section for comment | All
2014-11-10 | 16 | DAI | Confirm updates in naming convention example (Sec. 4.1.1) | All
2014-11-10 | 17 | DAI | Decide if descriptorModelID needs to be changed for restrictions of schema. If so we should not recommend to systematically restrict. | All
2014-11-10 | 18 | DAI | Provide namePreservationRule example/discussion (not mandatory) | DS
2014-11-10 | 19 | DAI | Rename sections 4.1.3 Collections 4.1.4 Transfer Objects 4.1.5 Transfer Object Groups 4.1.6 Transfer Object-Data Objects | SM
2014-11-10 | 20 | DAI | Generate text on the uses of the ‘undefined’ structure name for insertion somewhere in section 4. Maybe also for other groupTypeStructureName values? | DS
2014-11-10 | 21 | DAI | Update core GB | SM
2014-11-10 | 22 | DAI | For tomorrow’s teleconference: look at the material discussed with a view identifying information to help make a decision re. the main boxes + arrangement) | All | 2014-11-12 | Closed | 20141112 Continued discussions re. LTDP workflow
2014-11-10 | 23 | DAI | If possible, Settle on 4 or 5 steps for ICP this week | All DAI WG
2014-11-10 | 24 | DAI | Provide on comments the LTDP preservation workflow (main steps, content, and terminology). | All | 2014-11-14 | Closed | 20141114 Comments were provided during meeting. This AI was closed and AI#26 was opened.
2014-11-10 | 25 | DAI | Provide recommendations for which blbliography items to focus on | DB MM
2014-11-10 | 26 | DAI | By next week comments on LTDP workflow | All | 2014-11-21 | Closed | 20141118 Comments were provided to DB 20141121 DB consolidated comments and forwarded them to LTDP WG.
2014-11-10 | 27 | DAI | Provide high-level concepts from CEDA | EC
2014-11-10 | 28 | DAI | Send presentation | EC
2014-11-10 | 29 | DAI | Circulate info on MOLES 3 Standard, Include new terminology not in OAIS and TRAC | EC
2014-11-10 | 30 | DAI | Respond to DG figure (RDA and CCSDS) tonight | EC | 2014-11-14 | Closed | 20141114 Comments were sent and incorporated into figure which was presented to NP.
2014-11-10 | 31 | DAI | All comments by the 18th November (comments expected by the LTDP the 21st at the latest). DB will try to organize them between the 18th and 20th. | All | 2014-11-21 | Closed | 20141118 Comments were provided to DB 20141121 DB consolidated comments and forwarded them to LTDP WG.
2014-11-10 | 32 | DAI | Follow up to ensure that DAI glossary entries are entered in CCSDS glossary. | JGG
2014-11-10 | 33 | DAI | Follow up with BO to see if forwarding pages for DAI and RAC documents can be provided. | JGG
2014-12-04 | 1 | DAI | Send a synthetic model, from the slides presented during the London meeting (for beginning week 50) | EC
2014-12-04 | 2 | DAI | Send comments on the email sent by David the 23rd November (for next telecon 9th january at the latest). | ALL WG
2014-12-04 | 3 | DAI | Send the “specialization kit” to the group, to be included in the annex of the GB. | SM
2014-12-04 | 4 | DAI | Provide a planning for the end of the GB: 1. completion of all topics to be dealt with, and 2. identification of sections that can be fully written by SM and/or the group. | SM
2014-12-04 | 5 | DAI | Send the updated test case implementation to DB for test with the CNES proto, update the repository. | SM
2014-12-04 | 6 | DAI | Comment the Corot practical example. | ALL WG
2014-12-04 | 7 | DAI | Complete the EXCEL file to be closer to the Abstract SIP Model view, including containers (Monday), to be sent by DB before Thursday to BnF. | DS | 2014-12-09

## Closed
Date | Action ID | WG | Action | Assignee | Closed Date | Status | Comment
2014-03-31 | AI#01 | RAC | Remind Nick Tongson, CCSDS Liaison to ISO, that we are relying on him to continue to monitor progress of ISO FDIS 16919 to ensure that ISO review, if needed, is started as soon as possible. | DG | 2014-04-02 | Closed | During CCSDS Meeting See section 2 of Minutes
2014-03-31 | AI#04 | DAI | Contact TG, CCSDS Editor, to request that the PAIS BB be forwarded to ISO | DB | 2014-04-02 | Closed | During meeting with TG
2014-03-31 | AI#07 | DAI | Provide some additional material for tomorrow’s discussion on the E2E example that is proposed | MM | 2014-04-02 | Closed | See email attachment
2014-03-31 | AI#08 | DAI | Propose a simpler method to document test case information | SM MM | 2014-04-02 | Closed | See SM email attachment
2014-03-31 | AI#17 | DAI | Obtain a document number for the new CCSDS MB project: Information Curation Process | DB | 2014-04-02 | Closed | Number is 653.0 MB will become CCSDS 653.0-M-1
2014-03-31 | AI#15 | DAI | Comment and if necessary add information (SAFE version 2.0 …) to the SAFE test case description by next week | DB | 2014-04-12 | Closed
2014-03-31 | AI#18 | DAI | Check with CCSDS Editor to determine if there are any CCSDS graphical guidelines for presentation of a Process in CCSDS documents | DB | 2014-04-12 | Closed | No required format. Use what works best.
2014-04-16 | 7 | DAI | Propose a SIP implementation without XFDU | SM | 2014-04-16 | Closed | Decision made to use METS example from BnF
2014-04-16 | 11 | DAI | Send proposal on namespace to SANA, Nestor and Peter, and ask if they have any objection to our proposal. | SM | 2014-04-16 | Closed | PAIS BB has been published including the schemas that make use of the proposed namespace
2014-04-16 | 13 | DAI | Give comments and proposals as input for the LTDP terminology and steps of workflow | All | 2014-04-16 | Closed
2014-04-16 | 20 | DAI | Search for procedure to use the CCSDS webexp -> no CCSDS webexp available | JGG | 2014-04-16 | Closed | WEBEX from ISO is available to us. Nestor set up an an account for use by MOIMS WGs. On 2013-10-27 JGG forwarded a 2012-09-02 email from Nestor with details for using it.
2014-03-31 | AI#19 | DAI | Provide pointer to where Data Warehousing terminology can be found | MM | 2014-04-17 | Closed | see MM's 20140417 email with presentation or see http://research.microsoft.com/pubs/76058/sigrecord.pdf
2014-04-16 | 1 | DAI | Sign the CCSDS meeting minutes | JGG | 2014-04-18 | Closed
2014-03-31 | AI#14 | DAI | Send info on SAFE changes | PS | 2014-05-02 | Closed
2014-03-31 | AI#16 | DAI | Send the updated packages of data (dummy file for the product, and RepInfo Packages) | PS | 2014-05-02 | Closed
2014-04-16 | 10 | DAI | Table in section 4.6.4 should be reviewed for (during) next telecon | All | 2014-05-06 | Closed | Comments were made. New versions will need comment, but new AI will be opened when comments are needed.
2014-04-16 | 19 | DAI | Ask Peter Shames on possible NASA involvment in CCSDS/MOIMS/DAI | MM | 2014-05-06 | Closed | Peter expressed enthusiasm for the effort but is unable to provide any support. Any support will need to come from projects. NSSDC and PDS are unlikely to provide any additional support.
2014-04-16 | 5 | DAI | Deliver the CNES proto software to John | DB | 2014-06-05 | Closed | 20140605 - JGG has downloaded the SW, but is having trouble starting up | 2014-05-15
2014-04-16 | 6 | DAI | Send samples of PDS4 data | MM | 2014-06-05 | Closed | See 30 October email 20140605 - Since MM will not continue support for PAIS, we will suppress the PDS test case from GB | 2014-05-13
2014-04-16 | 12 | DAI | Ask David for preservation/curation definition | DB | 2014-06-05 | Closed | Danièle: done, but have to ask again, so keep open 20140605 - DG responded with a general answer but no specific definitions. We will take his comment into consideration as we develop ICP terminology
2014-05-06 | 1 | DAI | Fill in the PDS test case according to the pattern with agreed TOC for Green Book with the text and figures. | MM | 2014-06-05 | Closed | See 30 October email 20140605 - Since MM will not continue support for PAIS, we will suppress the PDS test case from GB
2014-05-06 | 2 | DAI | Send an updated version of ESA-SAFE test case section of PAIS GB | DB | 2014-06-05 | Closed | 20140604 - DB distributed ESA SAFE test case to group. All should provide comments by next week (20140612). | 2014-05-09
2014-05-06 | 3 | DAI | Write a paragraph describing the Information Curation Process project | JGG (with DB) | 2014-06-05 | Closed | 20140604 - JGG distributed ICP Purpose/Scope to group. All should provide comments by next week (20140612).
2014-04-16 | 8 | DAI | Send comments on Mike's information on PDS4 sample (email 30th October) | All |  | Closed
2014-04-16 | 14 | DAI | Write and send more precise elements on this LTDP process to the group. | DB |  | Closed | Elements have been presented during the CCSDS meeting. Do you think more details are necessay?
2014-04-16 | 2 | DAI | Review the ESA SAFE test case, then send it to the group. | DB SM | 2014-06-19 | Closed | 20140604 - DB distributed ESA SAFE test case to group. All should provide comments by next week (20140612). We will keep this open till TC is validated. 20140612 - DS provided comments 20140614 - JGG provided comments 20140618 - DB provided updated document | 2014-05-12
2014-04-16 | 3 | DAI | Complete the ISEE usecase about SIPs (according to the test case TOC). | DS | 2014-06-19 | Closed | 20140604 - DS distributed partially completed ISEE test case to group. All should provide comments by next week (20140612). 20140612 - DB provided comments 20140619 - DS provided updated document
2014-06-05 | 2 | DAI | Send example of clearer presentation of XML in Section 1.1.4 of ESA-SAFE test case | DS | 2014-06-05 | Closed | 20140605 - Email from DS | 2014-06-12
2014-06-05 | 3 | DAI | Review and send comments on the ESA-SAFE test case section of PAIS GB | DS JGG | 2014-06-18 | Closed | 20140612 - DS provided comments 20140614 - JGG provided comments 20140618 - DB provided updated document | 2014-06-12
2014-06-05 | 4 | DAI | Review and send comments on the ISEE test case section of PAIS GB | DB | 2014-06-19 | Closed | 20140612 - DB provided comments 20140619 - DS provided updated document | 2014-06-12
2014-03-31 | AI#23 | DAI | Include the XFDU schema in the DAI registry | GL | 2014-06-30 | Closed | 20140605 - Registry has not yet been setup in SANA. DB will contact SANA regarding its status. | 2014-04-02
2014-06-19 | 2 | DAI | Send updated ESA-SAFE test case | DB | 2014-07-01 | Closed
2014-06-05 | 7 | DAI | Ask Mirko Albani about potential updates in LTDP workflow | DB | 2014-07-17 | Closed | 20140717 - DB forwarded updated materials from LTDP group | 2014-06-18
2014-07-18 | 1 | DAI | validate the SIP Model and XFDU descriptions for SANA | All | 2014-07-19 | Closed
2014-07-18 | 2 | DAI | send the descriptions to SANA; ask to replace “xfdu0” by “xfdu” in the registry table; give OK to open the DAI registry to all | DB | 2014-07-21 | Closed
2014-03-31 | AI#05 | DAI | Inform us of the ISO reference for PAIS when it is assigned | TG | 2014-07-30 | Closed | 20140814 - JGG reported that PAIS has been assigned ISO # 20104
2014-07-18 | 3 | DAI | Update ESA-SAFE test case text (see minutes notes) | DB | 2014-08-13 | Closed | See 20140813 email
2014-03-31 | AI#21 | DAI | Create the DAI registry (“Data Archive Ingest XML registry”), and include the PAIS schemas inside | GL | 2014-08-07 | Closed | 20140605 - Registry has not yet been setup in SANA. DB will contact SANA regarding its status 20140630 - Beta version was made available 20140701 with requrest to provide descriptions 20140702 - Beta version has been updated with additional column indicating group (i.e. short name of source standard) 20140718 - Draft descriptions have been generated and once validated will be sent to SANA 20140807 - DAI Registry moved to approved area of SANA. | 2014-04-02
2014-03-31 | AI#22 | DAI | Verify that XFDU sent to SANA matches the XFDU schema in the XFDU Standard | JGG | 2014-08-13 | Closed | 20140506 - Seems to be correct. Will check again once registry is setup. 20140807 - DAI Registry moved to approved area of SANA
2014-06-19 | 3 | DAI | Send comments on ISEE test case (email from DS 20140619) | All | 2014-07-03 | Closed | 20140904 - DS sent a new version yesterday
2014-07-18 | 4 | DAI | Review and send final comments on ESA-SAFE test case text | All | 2014-09-03 | Closed | 20140813 - Updated version distributed 20140904 - DB will be distributing new version before next meeting | 2014-08-13
2014-07-18 | 5 | DAI | finish the SIP part of the ISEE test case | DS | 2014-09-03 | Closed | 20140814 - Updated version distributed 20140904 - DS sent a new version yesterday | 2014-08-13
2014-08-14 | 1 | DAI | Ask ESA for the reference to the SAFE 2.0 standard | DB | 2014-09-03 | Closed | 20140904 - Reference was received and forwarded to list today.
2014-08-14 | 4 | DAI | Update ESA-SAFE test case text (see 20140814 minutes) | DB | 2014-09-03 | Closed | 20140904 - Update sent. DB will be distributing new version before next meeting
2014-07-18 | 6 | DAI | Ask NSSDC about Control Authority standard | JGG | 2014-09-04 | Closed | 20140904 - NSSDC is still using ADIDs and assigning new ones. Unsure how long it will continue to do so. If an XML version was available, they might use it. They do not expect to have resources to contribute to development of the XML version of the standard or the prototypes. | 2014-08-13
2014-09-04 | 3 | DAI | Generate ICP terminology document (w/ just definitions) for discussion with LTDP group | JGG DB | 2014-09-22 | Closed | 20140919 - JGG updated document to just include the proposed definitions 20140921 - DB added additional descussion to document for LTDP telecon 20140922 - Telecon w/ LTDP, DB, and JGG resulted in agreements on terms that will be used as a baseline. We can revisit terms as we work the ICP document. | 2014-09-16
2014-06-05 | 5 | DAI | Review and Comment on the Introduction section of ICP MB | All | 2014-09-23 | Closed | 20140923 - Discussed at telecon. Will now be incorporated into ICP draft document | 2014-06-18 | 2014-08-28
2014-06-05 | 6 | DAI | Review and Comment on the proposed Terminology for ICP MB | All | 2014-09-23 | Closed | 20140904 - Discussed at today meeting (see minutes) 20140919 - JGG updated document to just include proposed definitions 20140921 - DB added additional descussion to document 20140922 - Telecon w/ LTDP, DB, and JGG resulted in agreements on terms that will be used as a baseline. We can revisit terms as we work the ICP document. 20140923 - Discussed at telecon. Will now be incorporated into ICP draft document | 2014-06-18 | 2014-08-28
2014-09-23 | 2 | DAI | Update the figure describing the ISEE data by the Producer (1977 to 1978 to match data, etc.) | DB | 2014-10-08 | Closed | 20140926 - SM and DB provided figures in .svg 20141008- DB provided .jpg version of figure
2014-10-09 | 5 | DAI | Provide new version of ISEE Test Case with latest comments | DS | 2014-10-09 | Closed | 20141009 - DS sent new verions 20141028 - DS sent reminder message re.new version | 2014-10-29
2014-10-09 | 7 | DAI | Review draft agenda for CCSDS Fall meeting | All | 2014-10-13 | Closed | 20141016 - DB provided update based on comments 20141017 - DB provided 2 more updates based on comments | 2014-10-13
2014-09-23 | 3 | DAI | Provide initial agenda for CCSDS fall meeting | DB | 2014-10-17 | Closed | 20141007 - DB provided very draft agenda 20141016 - DB provided update based on comments 20141017 - DB provided 2 more updates based on comments | 2014-10-08
2014-10-09 | 1 | DAI | Resend comments on MM's PAIS Wrap-up | JGG | 2014-10-28 | Closed | 20141028 - JGG resent 20140923 message with marked up document to DAI-WG, and directly to MM and other editing team | 2014-10-16
2014-03-31 | AI#02 | RAC | Continue to monitor progress towards approval as an ISO Standard 16919 and report back as status changes | DG JGG | 2014-10-30 | Closed | JGG informed DAI WG about new ISO timeline which includes an extra 2 months for translation before a review starts. 20140605 - Still awaiting start of review (entered stage 20140320) 20140612 - Received word from ISO contact that it is stuck in an editing queue but they will try to move it along 20140718 - JGG reported that the 2 month ISO review is underway 20140904 - JGG reported that the 2 month ISO review ends tomorrow. 20140922 - JGG reported that no comments were received from the ISO review. The document has entered the ISO publication process. We hope it will be available from ISO soon. 20141030 - JGG reported that ISO 16929:2014 is now published and available on the ISO website | As needed
2014-03-31 | AI#11 | DAI | Check with CNES re. making data from GB test case available | DB | 2014-09-04 | Closed | 20140605 - On hold until GB Test Cases are nearing completion 20140904 - DB has received authorization to include the CNES test case | TBD
2014-03-31 | AI#12 | DAI | Check with ESA re. making data from GB test case available | SM | 2014-10-30 | Closed | 20140605 - On hold until GB Test Cases are nearing completion 20141030 - DB reported that we have authorization to include the ESA test case | TBD
2014-04-16 | 16 | DAI | Exchange on high level process (3 main steps preparation/preservation/maintenance) and links with PAIMAS phases for return to the LTDP group. | All | 2014-10-30 | Closed | 20140605 - DB will ask contact LTDP group to find out what new has been done 20141030 -This is linked to other items and will be folded into those items. | TBD
2014-06-19 | 1 | DAI | Ask Tom G. for suggestion of where to make available to public input data and outputs associated with PAIS tutorial. | DB | 2014-10-30 | Closed | ? DB discussed issue with TG. He indicated there is no appropriate area on CCSDS websites 20141030 - Since therer is no appropriate place to store these on the CCSDS website, we plan to make test cases available at a CNES site | 2014-07-19
2014-08-14 | 2 | DAI | Overall reading (consistency, coherence, grammatical issues, …) of ESA-SAFE test case text | All | 2014-10-30 | Closed | 20140904 - DB will be distributing new version before next meeting 20141030- Received comments have been addressed. A general reading of all test cases will be needed as a new AI. | 2014-09-03
2014-08-14 | 3 | DAI | Give explanation for using "directory" group structure in detailed case and "set" in the simple case (see 20140814 minutes) | DB | 2014-10-30 | Closed | 20141030- This has been addressed. A general reading of the entire document including all test cases will be needed as a new AI. | 2014-09-03
2014-08-14 | 9 | DAI | Understand the validation of the group structure level from the CNES prototype | DB | 2014-09-03 | Closed | 20140904 - DB has been working the issue. It seems that the CNES prototype validates identifiers, but does not validate structures 20141030 - This was done and result is as stated above.
2014-09-04 | 2 | DAI | Update ESA-SAFE test case text (including the reference to SAFE documentation) | DB | 2014-10-08 | Closed | 20141030 - DB provided update on 2014-10-08 | 2014-09-22
2014-09-04 | 5 | DAI | Generate draft agenda for CCSDS fall meeting | DB | 2014-10-17 | Closed | 20141007 - DB provided very draft agenda 20141016 - DB provided update based on comments 20141017 - DB provided 2 more updates based on comments | 2014-09-21

## Assignee Codes
Code | Given Name | Family Name
BO | Brian | Oliver
DB | Daniele | Boucon
SM | Stephane | Mbaya
JGG | John | Garrett
DS | Don | Sawyer
MM | Mike | Martin
TG | Tom | Gannett
PS
SR | Stephane | Reecht
EC | Esther | Conway

## Sheet1
1 | 20140422 | It is decided to have 2 separate sections for the minutes documents: 1st section for the minutes of the day including the actions taken during the telecon, 2nd section for "historical" part that has to be kept.
2 | 20140422 | The actions will be sent in a separate file managed by John. This file will be updated and sent after the production of the minutes.
3 | 20140422 | (DS) The rightmost column of the table in §4.6.4 of the PAIS GB shall be renamed « Restriction » instead of
4 | 20140422 | (JG) these XSD shall be placed side to the originals.