## bugs-2018-10-28 (1)
Suggested Change ID | Product | Component | Status | Resolution | Summary | Changed | Reporter Real Name | Depends on | Number of Comments | Figure | Last comment | Diagram changes done?
227 | OAIS June 2012 | Section 4.2: Information Model | RESOLVED | CHANGE AGREED | Change label for Figure 4-15 to clarify what is and is not part of the AIP | 2018-02-13 16:19 | Mark Conrad |  | 4 | Fig 4-15 | From: Figure 4 15: Archival Information Package (AIP) To: Figure 4 15: Archival Information Package (AIP) and its associated Package Description and Packaging Information | n/a
228 | OAIS June 2012 | Section 4.2: Information Model | RESOLVED | CHANGE AGREED | Change label for Figure 4-17 to clarify what is and is not part of the Package Description | 2018-02-13 16:20 | Mark Conrad |  | 4 | Fig 4-17 | From: Figure 4 17: Package Description To: Figure 4 17: Package Description and its associated Archival Information Package | n/a
229 | OAIS June 2012 | Section 4.2: Information Model | RESOLVED | CHANGE AGREED | Change label for Figure 4-18 to clarify what is and is not included in the AIP | 2018-02-13 16:20 | Mark Conrad |  | 4 | Fig 4-18 | From: Figure 4 18: Archival Information Package (Detailed View ) To: Figure 4 18: Archival Information Package (Detailed View ) and its associated Package Description and Packaging Information | n/a
230 | OAIS June 2012 | Section 4.2: Information Model | RESOLVED | CHANGE AGREED | Change label for Figure 4-21 to clarify what is and is not included in the AIU | 2018-02-13 16:21 | Mark Conrad |  | 4 | Fig 4-21 | From: Figure 4-21: Archival Information Unit (AIU) To: Figure 4-21: Archival Information Unit (AIU) and its associated Unit Description and Packaging Information | n/a
231 | OAIS June 2012 | Section 4.2: Information Model | RESOLVED | CHANGE AGREED | Change label for Figure 4-22 to clarify what is and is not a part of the Unit Description | 2018-02-13 16:21 | Mark Conrad |  | 4 | Fig 4-22 | From: Figure 4-22: Unit Description To: Figure 4-22: Unit Description and its associated Archival Information Unit | n/a
232 | OAIS June 2012 | Section 4.2: Information Model | RESOLVED | CHANGE AGREED | Change label for Figure 4-23 to clarify what is and is not part of the AIC | 2018-02-13 16:22 | Mark Conrad |  | 4 | Fig 4-23 | From: Figure 4-23: Archive Information Collections Logical View To: Figure 4-23: Archival Information Collection and its associated Collection Description and Packaging Information Logical View | n/a
177 | OAIS June 2012 | Section 4.2: Information Model | RESOLVED AWAITING DIAGRAM | CHANGE AGREED | Section 4.2.2.8 text re: Access Collection v Figure 4-24 | 2018-06-19 17:57 | Mark Conrad |  | 4 | Fig 4-24 | On 20180619 the DAI WG agreed to the following updates In Section 1 Terminology Section From: Collection Description: A type of Package Description that is specialized to provide information about an Archival Information Collection for use by Access Aids. To: Collection Description: A type of Package Description that is specialized to provide information about an Archival Information Collection (or an Access Collection) for use by Access Aids. In Section 4.2.2.8 From: To create an Access Collection, an Archive would create a Collection Description that did not have an associated AIC. The Collection Description could have a customized Associated Member Description that documented the newly mined description data for each member AIP. A specialized Finding Aid could use this new Associated Member Description in conjunction with existing Associated Descriptions in the Package Description information of each member AIP to locate AIPs of interest to the user. To: To create an Access Collection, an Archive would create a Collection Description that did not yet have an associated AIC. The Collection Description could have a customized Member Description that documented the newly mined description data for each member AIP. A specialized Finding Aid could use this new Member Description in conjunction with existing Member Descriptions in the Package Description information of each member AIP to locate AIPs of interest to the user. Update Figure 4-24: Collection Description Change annotation on line connecting AIC and Collection Description From: Derived From To: May Be Derived From Change cardinality (AIC to Collection Description) From: 1 to 1 (implied) To: 0..1 to 1 | y
233 | OAIS June 2012 | Section 4.2: Information Model | RESOLVED | CHANGE AGREED | Change label for Figure 4-24 to clarify what is and is not part of the Collection Description SC#233 MC DG Type: Update needed for clarification Status: Resolved – Change Agreed (Figure Title) By DAI WG on 20180213 SC#177 MC DG Type: Update to add missing concept Status: Resolved – Awaiting Diagram By DAI WG on 20180619 TBD UPDATE FIGURE 4-6 Change annotation on line connecting AIC and Collection Description From: Derived From To: May Be Derived From Change cardinality (AIC to Collection Description) From: 1 to 1 (implied) To: 0..1 to 1 | 2018-02-13 16:22 | Mark Conrad |  | 4 | Fig 4-24 | From: Figure 4-24: Collection Description To: Figure 4-24: Collection Description and its associated Archival Information Collection | n/a
144 |  |  |  |  | SC#144 (Section 4.3) Eld Zierau for Nancy McGovern (DPC) DG Type: Update needed for clarification Status: Resolved – Change Agreed By DAI WG on 20171106 TBD: Update Figure 4-26 Rounded boxes for internal fuctions – Done TBD Producer and Consumer as stick figures (Still desired?) SC#147 (Section 4.3) Eld Zierau for Nancy McGovern (DPC) DG Type: Update needed for clarification Status: Resolved – Change Agreed By DAI WG on 20171106 TBD: Update Figure 4-26 Put (OAIS) box around the 4 internal functions SC#217 DG (for MH) DG Type: Editorial Status: Resolved – Change Agreed Status: Resolved – Awaiting Diagram Update by DAI WG on 20180710 Note: No update needed for Figure 4-26 |  |  |  |  | Fig 4-26 | DAI WG Agreed on 20171106 We agree that consistency and ability to distinguish different items are important. Therefore we have reexamined the current diagrams. See SC#143 | Y
205 |  |  |  |  | SC#205 JGG DG UPDATED FIGURE 4-3 NEEDS TO BE GENERATED |  |  |  |  | Fig 4-3 | Agreed at DAI virtual meeting 24 Jan 2017 to change to "It simplifies the work of this function if all hardware and software within the Archive provide notification of detected errors and that these errors are routed to standard error logs that are checked by the Archival Storage staff." Also update diagram 4-3 to be consistent | Y
1 |  |  |  |  | SC#001 DG DG BC Issue Type: --- (Technical Question) Status: Resolved – Change agreed By DAI WG on 20180410 TBD UPDATE FIGURE 4-4 Remove Descriptive Information from the arrow between Generate Report and Access |  |  |  |  | Fig 4-4 | In the data management functional entity On 20180410 the DAI WG agreed to the following changes: Remove last sentence of text in Generate Report that talks about descriptive information. We believed that other functions could also deal with descriptive information and calling it out only for Generate Report just muddied the water. The group felt it was better to simply remove the sentence rather than adding in the same comment in other locations also. The figure will be updated to remove Descriptive Information from the arrow between Generate Report and Access | Y
105 | OAIS June 2012 | Section 4.1: Functional Model | RESOLVED | CHANGE AGREED | Figure 4-5 missing system evolution plans | 2017-08-29 16:10 | Mark Conrad |  | 4 | Fig 4-5 | Fig 4-5 Does this need any change to the diagram? Is it not just a description of the functionality of Manage System Configuration? On second thoughts this perhaps it would be better to add a label "plans for system evolution" to the arrow from Manage System Configuration to Preservation Planning. Preservation planning then (see 4.1.1.6) send recommendations to Administration. | Y
106 | OAIS June 2012 | Section 4.1: Functional Model | RESOLVED | CHANGE AGREED | Figure 4-5 missing Manage System Configuration inputs | 2017-08-29 16:14 | Mark Conrad |  | 4 | Fig 4-5 | Fig 4-5 Yes arrow between the Manage System Config and Establish Standards and Policies should also show "Performance info and inventory reports" (which also goes to Preservation Planning) | Y
110 |  |  |  |  | SC#110 MC DG Type: Update needed for clarification Status: Resolved – Change Agreed Status: Resolved – Awaiting Diagram Update UPDATED FIGURE 4-5 NEEDS TO BE GENERATED Change Ausit Submission box to Check Submissions Change Audir report to Submission Report on line to Ingest by DAI WG on 20180717 |  |  |  |  | Fig 4-5 | Section 4.1.1.5 Under the Audit Submission function: Revised To v2: The Check Submission function receives AIPs or SIPs from Ingest and reviews from Preservation Planning. The Check Submission function will verify that SIPs meet the specifications of the Submission Agreement. In the case of submitted AIPs it verifies the understandability of the Content Information by the Designated Community. It also verifies that the AIPs meet the specifications in the AIP template. This function receives AIP/SIP reviews from Preservation Planning and may also involve an outside committee (e.g., science and technical review); these reviews report on whether the AIP/SIP templates have been properly applied in Ingest. The check submission process must verify that the quality of the data meets the requirements of the Archive. It should also ensure that it meets the requirements of the outside committee if one is used. The Check Submission function must verify that there is adequate Representation Information and PDI to ensure that the Content Information is understandable and independently usable by the Designated Community. The formality of the review will vary depending on internal Archive policies. The check submission process may determine that some portions of the SIP are not appropriate for inclusion in the Archive and must be resubmitted or excluded. A check submission report is provided to Ingest. After the check submission process is completed, any liens are reported to the Producer, who will then resubmit the SIP to Ingest or appeal the decision to Administration. In the case of producing a new version of an AIP this function checks that the migration goals have been met. This could include checking usability and checking evidence for Authenticity such as ensuring maintenance of Transformational Information Properties (see 5.2???). After the check submission process is completed, a final ingest report is prepared and provided to the Producer and to Negotiate Submission Agreement function. SC#110 MC DG Type: Update needed for clarification Status: Resolved – Change Agreed Status: Resolved – Awaiting Diagram Update UPDATED FIGURE 4-5 NEEDS TO BE GENERATED Change Ausit Submission box to Check Submissions Change Audir report to Submission Report on line to Ingest by DAI WG on 20180717 | y
111 | OAIS June 2012 | Section 4.1: Functional Model | RESOLVED | CHANGE AGREED | Figure 4-5 missing Activate Requests inputs | 2017-08-29 14:49 | Mark Conrad |  | 5 | Fig 4-5 | Section 4.1.1.5 Under the Activate Requests function: Should there be an arrow from Consumer to Activate Requests function in Figure 4-5 to reflect, "This function can also generate orders on a periodic basis where the length of the period is defined by the Consumers or on the occurrence of an event (e.g., a database update)." Comment 1 David Giaretta 2017-07-18 14:24:19 CEST Yes we should add the extra arrow. Comment 2 John Garrett 2017-07-18 17:32:39 CEST The DAI WG agreed to change the sentence to the following text on 20170718. No update to the diagram is needed since the diagram is notional and not every action is necessarily shown. For example, this This function can also generate orders on a periodic basis. w.here theThe length of the period is was originally defined by the Consumers in a request. or Another example of a triger is on the occurrence of an event (e.g., a database update). Comment 3 John Garrett 2017-07-18 17:48:27 CEST Sorry, the pasted update text included markup which garbled the display here. The updated text should read as below. For example, this function can generate orders on a periodic basis. The length of the period was originally defined by the Consumer in a request. Another example of a trigger is on the occurrence of an event (e.g., a database update). | y
206 | OAIS June 2012 | Section 4.1: Functional Model | RESOLVED | CHANGE AGREED | Hard to see difference of Functional Areas & Functions in Figure | 2017-05-30 16:13 | John Garrett |  | 4 | Fig 4-5 | Agreed at DAI virtual meeting 24 Jan 2017 Update Fig 4-5 to make it clear that different blocks can be distinguished. Hard to see difference of Functional Areas & Functions & Other Entities in Figure 4-5 (and possibly other figures). Also DIP is inside one of the boxes. Also color and shadow of Management | y
120 | [9 empty] | Fig 4-6 | The diagram Figure 4-6 should be changed to show the lines to "Develop Preservation Strategies and Standards" from "Monitor DC" and "Monitor Technology" should both instead feed into "Preservation Watch" which then goes to "Develop Preservation Strategies and Standards". The other lines from "Monitor DC" are unchanged. The descriptions of the lines in this section should be updated to be consistent. Comment 6 John Garrett 2018-02-27 16:20:15 CET On 20180227 DAI WG agreed to make changes to text as detailed in comment 3 and the diagram as detailed in comment 5. | y
129 | OAIS June 2012 | Section 4.1: Functional Model | RESOLVED AWAITING DIAGRAM | CHANGE AGREED | Section 4.1.1.6 text v Figure 4-6 | 2018-04-11 16:20 | Mark Conrad |  | 5 | Fig 4-6 | Section 4.1.1.6 Under Develop Packaging Designs and Migration Plans function: The text does not match what is shown in Figure 4-6. 1. The text says this function develops prototypes, but the figure shows the Develop Packaging Designs and Migration Plans function sending prototype requests to Monitor Technology and receiving prototype results back from Monitor Technology. BTW, it is not clear what these prototypes are. 2. Figure 4-6 indicates that Develop Packaging Designs and Migration Plans function receives preservation requirements from Administration. This is not reflected in the text. Comment 1 David Giaretta 2018-04-03 15:15:25 CEST I agree that Fig 4-6 must be re-drawn - also for SC 120 Comment 2 David Giaretta 2018-04-11 16:17:46 CEST . Remove all references to prototypes from the Figure - also make changes from 120 Comment 3 David Giaretta 2018-04-11 16:18:47 CEST (In reply to David Giaretta from comment #2) > . Remove all references to prototypes from the Figure > - also make changes from 120 Also change text to eliminate mention of prototypes Comment 4 David Giaretta 2018-04-11 16:20:16 CEST (In reply to David Giaretta from comment #3) > (In reply to David Giaretta from comment #2) > > . Remove all references to prototypes from the Figure > > - also make changes from 120 > > Also change text to eliminate mention of prototypes Should have said - make text consistent with diagram | y
131 | OAIS June 2012 | Section 4.1: Functional Model | RESOLVED AWAITING DIAGRAM | CHANGE AGREED | Section 4.1.1.7 v Figure 4-7 SC#131 MC DG Type: Update needed for clarification Status: Resolved – Awaiting Diagram Change agreed By DAI WG on 20180411 TBD UPDATE FIGURE 4-7 Figure (and text) updates TBD JGG: MC had several questions/Comments. Not all shown here. | 2018-04-11 16:31 | Mark Conrad |  | 3 | Fig 4-7 | Section 4.1.1.7 Under the Coordinate Access Activities function: It is difficult to match up the text for this function with Figure 4-7. 1. The text says, "Three categories of Consumer requests are distinguished: query requests, which are executed in Data Management and return immediate query responses for presentation to the user". Figure 4-7 shows the query request coming from the Consumer to Coordinate Access Activities. Coordinate Access Activities sends the request to Data Management and receives the request response from Data Management. Coordinate Access Activities sends the query (request) response to Deliver Response. Deliver Response sends the query (request) response to the Consumer. BTW, should the word, "user", be replaced with "Consumer"? 2. The text says, "Three categories of Consumer requests are distinguished: ... report requests, which may require a number of queries and produce formatted reports for delivery to the Consumer;" Figure 4-7 shows a report request coming from the Consumer to the Coordinate Access Activities and it shows a report being sent to Deliver Response and Deliver Response sending the report to the Consumer. The figure does not show the intermediate queries or the formatting of the report. That would probably be ok except that the figure shows a report request being issued by Generate DIP to Data Management. I would suggest changing the name of this latter "report request" to "request descriptive info" to avoid confusion. 3. The text says, "Three categories of Consumer requests are distinguished: ...and orders, which may access either or both Data Management and Archival Storage to prepare a formal Dissemination Information Package (DIP) for on- or off-line delivery." The figure shows an order coming from the Consumer to Coordinate Access Activities. It then shows Coordinate Access Activities sending a DIP request to Generate DIP. Generate DIP sends requests to Data Management for Descriptive info and/or Archival Storage for a (copy of?) an AIP? Using the results of these requests Generate DIP creates a DIP and sends it back to Coordinate Access Activities. Coordinate Access Activities sends the DIP to Deliver Response. Deliver response forwards the DIP to the Consumer and sends a Notice of shipped order to Coordinate Access Activities. 4. The text says, "or an Event Based Order that will be maintained by the Activate Requests function in Administration,". It would be helful to add "See Figure 4-5." after "Administration." 5. The text says, "The Archival Information Update function in Administration also submits dissemination requests to obtain DIPs needed to perform its update functions. It would be helful to add "(See Figure 4-5)" after "Administration." 6. The text says, "This function also provides assistance to OAIS Consumers including providing status of orders and other Consumer support activities in response to an assistance request." The figure indicates that the assistance is provided to the Consumer by Deliver Response. Comment 1 David Giaretta 2018-04-03 15:17:32 CEST I agree that the Figure must be consistent with the text Comment 2 David Giaretta 2018-04-11 16:29:12 CEST Awaiting diagram and other changes - see http://review.oais.info/show_bug.cgi?id=217 | y
157 | OAIS June 2012 | Section 4.1: Functional Model | RESOLVED AWAITING DIAGRAM | CHANGE AGREED | Section 4.1.1.7 Generate DIP function v Figure 4-7 SC#157 MC DG Type: Updates needed for clarification Status: Resolved – Awaiting Diagram Change agreed By DAI WG on 20180411 TBD UPDATE FIGURE 4-7 Figure (and text) updates TBD JGG: MC had several questions/Comments. Not all shown here. MC: Hard to match text to figure | 2018-04-11 16:43 | Mark Conrad |  | 3 | Fig 4-7 | Section 4.1.1.7 Under the Generate DIP function: It is difficult to match up the text for this function with Figure 4-7. 1. The text says, "The Generate DIP function accepts a dissemination request," Figure 4-7 indicates that the Co-ordinate Access Activities function receives the dissemination request and sends a DIP request to the Generate DIP function. 2. The text says, "retrieves the AIP from Archival Storage." Does the Generate DIP function retrieve the AIP or a copy of the AIP? 3. The text says, "and moves a copy of the data to a temporary storage area for further processing." This temporary storage is not shown in Figure 4-7. 4. The text says, "This function also transmits a report request to Data Management to obtain Descriptive Information needed for the DIP." Suggest changing the name of the Report request to some other name so that it is not confused with the Report request from the Consumer. 5. The text says, "If special processing is required, the Generate DIP function accesses Data Objects in temporary storage and applies the requested processes." This temporary storage and these processes are not shown in Figure 4-7. 6. The text says, "The types of operations which may be carried out include statistical functions, sub-sampling in temporal or spatial dimensions, conversions between different data types or output formats, and other specialized processing (e.g., image processing). Inserting DRM information and filtering the personal data to ensure consistency with the user rights also come under this type of operation." It should be made clear that this is not an exhaustive list. 7. The text says, "This function places the completed DIP response in the temporary storage area and notifies the Coordinate Access Activities function that the DIP is ready for delivery." This temporary storage is not shown in Figure 4-7. Figure 4-7 shows the Generate DIP function delivering the DIP to the Coordinate Access Activities function. It does not show the Generate DIP function notifiying, " the Coordinate Access Activities function that the DIP is ready for delivery." 8. The text says, "It is worth noting that in some implementations the AIP content or the DIPs could be kept in temporary storage for ready availability." This text only applies to some implementations, adds to the confusing text, and does not add to the explanation of the function. 9. Figure 4-7 shows the Archival Storage function sending a Notice of transfer to the Generate DIP function. This Notice of transfer is not mentioned in the text for the Generate DIP function. Comment 1 David Giaretta 2018-04-03 15:36:02 CEST I agree that the text and the Figure should be consistent Comment 2 David Giaretta 2018-04-11 16:42:56 CEST Awaiting diagram and text - see http://review.oais.info/show_bug.cgi?id=217 | y
158 | OAIS June 2012 | Section 4.1: Functional Model | RESOLVED AWAITING DIAGRAM | CHANGE AGREED | Section 4.1.1.7 Deliver Response function v Figure 4-7 | 2018-04-11 16:44 | Mark Conrad |  | 2 | Fig 4-7 | Section 4.1.1.7 Under the Deliver Response function: It is difficult to match up the text for this function with Figure 4-7. 1. The text says, "The Deliver Response function handles both on-line and off-line deliveries of responses (DIPs, query responses, reports and assistance) to Consumers." Figure 4-7 does not show a split in processes for on-line and off-line distribution. 2. The text says, "For on-line delivery, it accepts a response from Coordinate Access Activities and prepares it for on-line distribution in real time via communication links. It identifies the intended recipient, determines the transmission procedure requested, places the response in the temporary storage area to be transmitted, and supports the on-line transmission of the response." This temporary storage is not shown in Figure 4-7. The text does not explain how DIPs are related to orders from the Consumer - only that a Notice of shipped order is sent to the Co-ordinate Access Activities function. Which function is responsible for ensuring that the order is complete? 3. The text says, "For off-line delivery it retrieves the response from the Coordinate Access Activities function, prepares packing lists and other shipping records, and then ships the response. When the response has been shipped, a notice of shipped order is returned to the Coordinate Access Activities function and billing information is submitted to Administration." "[P]repares packing lists and other shipping records," sounds very implementation specific. For example, couldn't the Consumer came to the repository to pick up their order? Wouldn't the Deliver Response function need to identify " the intended recipient," and "determines the transmission procedure requested" for off-line orders as well as on-line orders? Comment 1 David Giaretta 2018-04-11 16:43:32 CEST Awaiting diagram and text - see http://review.oais.info/show_bug.cgi?id=217 | Note: did not add "Temporary storage"
217 | OAIS June 2012 | Section 4 : Detailed Models | RESOLVED AWAITING DIAGRAM | CHANGE AGREED | Changes to Figures 4-7,8,9,26 for consistency SC#217 DG (for MH) DG Type: Editorial Status: Resolved – Change Agreed Status: Resolved – Awaiting Diagram Update by DAI WG on 20180710 TBD – Update Figure 4-8 What updates needed? | 2018-07-10 17:04 | David Giaretta | 131, 158 | 6 | Fig 4-7 Fig 4-8 Fig 4-9 Fig 4-26 | Inserted by David Giaretta on behalf of HemmjeEngel The following was a comment to suggested change #20 http://review.oais.info/show_bug.cgi?id=20 but has been elevated to a new Suggested Change Yes, this request is fully correct: “request agreement” needs to be changed to “order agreement”. Further, some terms are not consistent applied in various texts and figures (e.g. Figure 4-7,8,9,26). We propose to change and consistently use: • Change “order request” to “order”. The return is a “DIP”. • The return of a “assistance request” is an “assistance”. • The return of a “report request” is a “report”. • Change “query response” to “response”, that is the return of a “query” Comment 1 John Garrett 2017-05-12 05:04:27 CEST Discussed at DAI WG meeting on 20170511. Generally agree with the suggestion, but in Figure, Query Response works its way through many functions. Changing it to just response throughout figure would be make the figure confusing. Needs more analysis. Comment 2 David Giaretta 2018-04-11 16:31:27 CEST SCs 131, 157, 158 have comments on this also Comment 3 David Giaretta 2018-07-10 16:30:42 CEST DAI 20180710 agree with first 3 changes but want to keep "query response" Comment 4 David Giaretta 2018-07-10 16:44:33 CEST DAI 20180710: Arrow from Generate DIP to DM should say "Request Descriptive Info" and returns "Descriptive Info" Comment 5 David Giaretta 2018-07-10 17:04:10 CEST DAI 20180710: John has also updated text in the working copy to be consistent.. | y
159 | OAIS June 2012 | Section 4.1: Functional Model | RESOLVED AWAITING DIAGRAM | CHANGE AGREED | Section 4.1.2 Improvements to Figures 4-8 and 4-9 | 2018-04-11 16:46 | Mark Conrad |  | 2 | Fig 4-8 Fig 4-9 | ection 4.1.2 It would be very helpful of Figures 4-8 and 4-9 could be enlarged or re-drawn in such a way that it is clearer what is being received by each function by placing the texts near the ends of the arrows as is the case with the earlier figures. Comment 1 David Giaretta 2018-04-11 16:46:05 CEST Awaiting diagram which should improve readability | y
160 | OAIS June 2012 | Section 4.1: Functional Model | RESOLVED AWAITING DIAGRAM | CHANGE AGREED | Figure 4-9 Arrows pointing wrong direction | 2018-04-11 16:25 | Mark Conrad |  | 3 | Fig 4-9 | Figure 4-9 It appears that the arrows between Preservation Planning and Administration are pointing the opposite directions that they should be. Comment 1 David Giaretta 2018-04-03 12:18:52 CEST I think this is correct - the two arrows should be reversed. Comment 2 David Giaretta 2018-04-11 16:24:38 CEST Diagram to be produced and reviewed | y
145 |  |  |  |  | SC#145 (Section 6.1) Eld Zierau for Nancy McGovern (DPC) DG Type: Update needed for clarification Status: Resolved – Change Agreed By DAI WG on 20171106 NOTE: TBD Figure still needs to be updated |  |  |  |  | Fig 6-4 | DAI WG Agreed on 20171106 We agree that consistency and ability to distinguish different items are important. Therefore we have reexamined the current diagrams. See SC#143 | y
135 | [9 empty] | Fig 6-5 Fig 6-6 | Add figures for primary OAIS/supporting OAIS | y
140 | OAIS June 2012 | Section:Annexes | RESOLVED | CHANGE AGREED | Figure A-1 should reflect the placement of functional entities as in Figure 4-1 | 2018-05-14 12:42 | Eld Zierau |  | 5 | Fig A-1 | See http://review.oais.info/show_bug.cgi?id=140 Nestorgram Reposition Fes etc | Awaiting confirmation of other changes
141 | OAIS June 2012 | Section:Annexes | RESOLVED AWAITING DIAGRAM | CHANGE AGREED | Revised/corrected Figure A-1 "Composite of Functional Entities" | 2018-05-14 13:40 | Eld Zierau |  | 8 | Fig A-1 | David Giaretta 2018-04-03 12:15:39 CEST We agreed in http://review.oais.info/show_bug.cgi?id=136 NOT to make the change to Preservation Storage. However Figure A1 should be reviewed and made consistent with with small changes agreed elsewhere. The colours were removed through a CCSDS level decision - so that the diagram would make sense even if printed in greyscale. Comment 3 David Giaretta 2018-04-11 16:23:10 CEST Diagram to be produced for final review Comment 4 Eld Zierau 2018-05-14 12:47:50 CEST See issue 140 Comment 5 Eld Zierau 2018-05-14 12:49:28 CEST See issue 140 Comment 6 Eld Zierau 2018-05-14 13:36:12 CEST Created attachment 34 [details] New with change role symbol I am not sure whether it is agreed about symbol for roles, so I have attached one with the suggested changed roles symbol Comment 7 Eld Zierau 2018-05-14 13:39:36 CEST Created attachment 35 [details] Legend | Awaiting confirmation of other changes
143 |  |  |  |  | SC#143(Section 4.1) (Change Functional Entity Box Shape) Eld Zierau (DPC) DG Type: Update to add useful terminology Status: Resolved – Change Agreed By DAI WG on 20171106 NOTE: TBD Figure still needs to be updated. DONE? |  |  |  |  | Figs 4-2, 4-3, 4-4, 4-5, 4-6, 4-7, A-1 | DAI WG Agreed on 20171106 We agree that consistency and ability to distinguish different items are important. Therefore we have reexamined the current diagrams. Following basic flowchart symbology, we will represent Functional Entities as rectangles, the functions internal to the Functional Entities will be represented as rounded rectangles. The actors (Producer, Consumer and Management) will be shown as stick figures. | y
226 | OAIS June 2012 | Section 4.2: Information Model | RESOLVED | CHANGE AGREED | Change label for Figure 4-13 to clarify what is and is not part of the Information Package Contents | 2018-02-13 16:18 | Mark Conrad |  | 5 | Fiug 4-13 | rom: Figure 4 13: Information Package Contents To: Figure 4 13: Information Package Contents and its associated Package Description and Packaging Information | n/a
220 | OAIS June 2012 | Section 4.1: Functional Model | RESOLVED AWAITING DIAGRAM | CHANGE AGREED | Issues arising from review of item 104 | 2018-07-24 16:38 | TerryLongstreth | 115 | 10 | Multiple figs | On 20180724, the DAI WG agreed to * replace all mentions of "migration plans" and "migration packages" and "migration strategy" by "preservation plans". * replace "migration goals" and " migration policies" by "Preservation Objectives" Note that some diagrams used the replaced terms and will need to be updated. | y
112 | OAIS June 2012 | Section 4.1: Functional Model | RESOLVED | CHANGE AGREED | Figure 4-5 shows Customer Service output that is not discussed in 4.1.1.5 | 2017-08-29 14:48 | Mark Conrad |  | 4 | NONE | No Fig change DAI WG agreed to add following text on 20170718 A Consumer may generate a Special Request which Customer Service sends to Access. Special Request types are not detailed. | n/a
By DAI WG on 20171106