## Slide 1
Data Archive Interoperability
DAI WG Report to MOIMS
Ames Research Center
Mountain View, CA, USA
Spring 2019
David Giaretta (WG Chair)
John Garrett (WG Deputy Chair)
Notes: 1
1
1

## Slide 2
  DAI WG Executive Summary
Achievements for this meeting cycle:
  Extensive progress on OAIS-IF Architecture Description document
    Primarily Modelling activity
    Upcoming emphasis on Interfaces
  OAIS v3 ready for formal review – reviewing Deputy Area Director comments now
  CCSDS 652,0 (ISO 16363) Audit Metrics – reviewing several recent new comments
  IPELTU – Developed draft annex for Space Mission programs
  Reviewed and provided comments on DLR archive project
  US Government Publishing Office system for all government publications certified as a Trustworthy Digital Repository based on our standards
Working Group Status:
  GOOD
  Good Momentum – majority of projects near schedule, Massive OAIS effort ending, Audit books being updated, Architecture work accelerating
  Both Agency and outside participation in DAI is improving, but support is hard to maintain
    Several Agencies (and outside participants) are expressing keen interest in WG activities
    Limited in person attendance at this meeting, with additional virtual attendance via Skype
  Support from remaining Agencies is needed
Interaction with other WGs
  Met with SEA AD
    Discussed taking over RASIM GB and making use of it in their Data Architecture efforts
      SEA will reconfirm RASIM. DAI uses parts in Architecture and will consider additional parts when/if we start work on archive underlying functionality
    Mention made of efforts to consolidate SANA Terminology. We expressed our understanding of effort to improve consistency, but also thought down select to single definition is counter-productive
Notes: JAXA is interested, resources being identified. Possible issues getting resources allocated / schedule.

## Slide 3
  DAI WG Executive Summary
Problems and Issues:
  Resources to update Control Authority BBs
  SANA Terminology Registry
Request made to DAI to update these BBs to use SANA registry
630.0-B-1 Standard Formatted Data Units — Control Authority Procedures
631.0-G-2 Standard Formatted Data Units — Control Authority Procedures Tutorial
632.0-B-1 Standard Formatted Data Units — Control Authority Data Structures
  BBs so update to refer to SANA registries would require 2 new prototypes
  Need to identify resources (development of prototypes) to proceed with update
  Need ask to CMC to identify if anyone will provide prototype resources (Resolution?)
    Current missions see no reason to expend resources to make this change and may continue using the current version even if BB is updated
  If no prototype resources are identified, we suggest they be reconfirmed
Notes: JAXA is interested, resources being identified. Possible issues getting resources allocated / schedule.

## Slide 4
Resolutions agreed upon this meeting
  DAI-1: We wish to thank NASA and ARC for hosting this meeting
  DAI-2: Publish 650.0-M-3 Reference Model for an OAIS for concurrent CCSDS and ISO reviews
  DAI-3: Reconfirm 651.2-G-1 Producer-Archive Interface Specification (PAIS)— A Tutorial
    Reconfirm for now, will revisit once Architecture Description completed to determine if maintained as a separate book or to be combined with planned Producer-Archive Interface Protocol
  DAI-4: Reconfirm the following (pending from previous meeting but Control Authority books removed)
  Limited current use of SFDU (and components for supplying data and metadata in specific formats)
  Extensive amounts of SFDU exist in legacy archives)
620.0-B-2 Standard Formatted Data Units — Structure and Construction Rules
621.0-G-1 Standard Formatted Data Units — A Tutorial
622.0-B-1 Standard Formatted Data Units — Referencing Environment
641.0-B-2 Parameter Value Language Specification (CCSD0006 and CCSD0008)
641.0-G-2 Parameter Value Language — A Tutorial
643.0-B-1 ASCII Encoded English (CCSD0002)
647.1-B-1 Data Entity Dictionary Specification Language (DEDSL) — Abstract Syntax (CCSD0011)
647.2-B-1 Data Entity Dictionary Specification Language (DEDSL) — PVL Syntax (CCSD0012)
647.3-B-1 Data Entity Dictionary Specification Language (DEDSL) — XML/DTD Syntax (CCSD0013)
  Following GB is dated but gives underlying rationale, etc., but is worth keeping around for now.
  It will likely be updated at next review to bring in information from Architecture work, but resources should be directed to completing Architecture description first.
610.0-G-5 Space Data Systems Operations with Standard Formatted Data Units: System and Implementation Aspects
  DAI WG Executive Summary
Notes: JAXA is interested, resources being identified. Possible issues getting resources allocated / schedule.

## Slide 5
Further Resolutions anticipated in the next 6 months
  DAI-5: Publish 652.0-M-2 Audit and Certification of Trustworthy Digital Repositories for concurrent CCSDS and ISO reviews
  DAI WG Executive Summary
Notes: JAXA is interested, resources being identified. Possible issues getting resources allocated / schedule.

## Slide 6
Planning:
The 5-year reconfirmations noted above are needed
  DAI Executive Summary
Area and WG name | CCSDS Ref Nr | Document Title | Status / Comments | Start and / or Target Publication Date
MOIMS DAI | 653.0 | INFORMATION PREPARATION TO ENABLE LONG TERM USE | OK, Progress being made after lagging Added proforma to annex expect new inputs in proforma format shortly | Start date 03 April 2014 End date 30August 2020
MOIMS DAI | 650.0 | Reference Model for an Open Archival Information System (OAIS) - 5 year review | OK, Ready for formal review All suggested changes have been addressed Currently addressing DAD comments | Start date 22 August 2016 End date 15 June 2021
MOIMS DAI | 652.0 | Audit and Certification of Trustworthy Digital Repositories. (ISO 16363) - 5 year review | OK, On Schedule Resolved several suggested changes this cycle more SCs will be required to keep consistency with OAIS updates | Start date 22 August 2016 End date 15 August 2021
MOIMS DAI | 671.0 | Data Archive Architecture Description Document | OK, Good work this past year developing info model Moving on to interfaces | Start date 31 July 2017 End date 25 September 2022
Notes: JAXA is interested, resources being identified. Possible issues getting resources allocated / schedule.

## Slide 7
  DAI WG Upcoming New Work Items
Area and WG name | CCSDS Ref Nr | Document Title | Target Start / Publication Date | Resources Needed (total, Editor, Proto 1, Proto 2) [man month] TOTAL EDITOR PROTO1 PROTO2 |  |  |  |  | Comments/Rationale What if not started?
MOIMS DAI | 652.1 | Guidelines for Bodies Providing Audit and Certification of Candidate Trustworthy Digital Repositories | 15 July 2019 15 June 2021 | 2019 | 1 wm | 1 wm |  |  | 5 year update Document specializes from ISO 17021 for archives Reviews to follow on OAIS update review and coincide with updated Archive Auditing MB NASA (US Industry volunteer) to provide Document Editor
 |  |  |  | 2020 | 1 wm | 1 wm |  |  | 
 |  |  |  | 2021 | 1 wm | 1 wm |  |  | 
Notes: 7
7
7

## Slide 8
  SANA Terminology Registry
    Effort to improve consistency and reuse of definition when appropriate and specialization when appropriate – good ideas
    Requirement to reduce each term to single definition – bad idea
    Advocate fixing problem with providing context field in SANA rather than changing language in all CCSDS documents
  Incorporating SANA Registry in 5 year update of Control Authority docs
    BBs so update to refer to SANA registries would require 2 new prototypes
    We are willing to support update effort if agencies fund prototype efforts
    Limited and legacy use therefore not appropriate to retire
    Limited and legacy use therefore we view it as not worth effort for extensive work for update
    Therefore we recommend reconfirmation as is
  Outstanding Issues from previous meetings
    Access to ISO videoconferencing software (Zoom)
    Accessible CMC Resolutions and Status and CMC Minutes
  DAI WG Issues for CESG / CMC
Notes: JAXA is interested, resources being identified. Possible issues getting resources allocated / schedule.