## Slide 1
DAI WG Report to MOIMS
Virtual Meeting
Spring 2022
Chair David Giaretta (DAI WG Chair)
Deputy Chair John Garrett (DAI WG Deputy Chair)
Notes: 1
1
1

## Slide 2
  DAI WG Executive Summary
Achievements for this meeting cycle:
  Completed update of CCSDS 652.0-P-1.1: Audit and Certification of Trustworthy Digital Repositories (ISO 16363),– awaiting ISO review
  Completed update of CCSDS 652.1-P-2: Requirements for Bodies Providing Audit and Certification of Candidate Trustworthy Digital Repositories (ISO 16919), awaiting ISO review
  Completed new CCSDS 653.0-R-1: Information Preparation to Enable Long Term Use (IPELTU) update, – awaiting ISO review
  Made significant progress of set of documents for OAIS-Interoperability Framework:
    Draft Green Book, collecting further ideas for interfaces and protocols and additional Use Cases from ESA
    Draft Architecture Description
    ESA co-operation for interoperability testing with NASA implementation promised
Working Group Status: GOOD
  We continue to hold 60-120+ minute Skype video meetings every week with Bugzilla based web-site to help in reviews.
  Average attendance: UK: 1, Germany: 1, ESA: 1+, USA: 5
  Good Momentum – projects schedules updated, OAIS-IF work accelerating
Problems and Issues:
  Uncertainty about ISO reviews are delaying completion of documents
Notes: JAXA is interested, resources being identified. Possible issues getting resources allocated / schedule.

## Slide 3
Resolutions agreed upon this meeting:
  See table below for list of publications ready for CCSDS Agency review
Further Resolutions anticipated in the next 6 months:
  Expect to update set of OAIS-IF related projects including new Green Book
  After ISO issues settled, start projects 5 year review/update of PAIS docs
Planning (only approved Projects):
  DAI WG Executive Summary
Area and WG name | CCSDS Ref Nr | Document Title | Status / Comments | Start and / or Target Publication Date
MOIMS DAI | 653.0 | Information Preparation to Enable Long Term Use | Undergoing Agency review | Start date 03Apr2014 End date 22Dec2023
MOIMS DAI | 650.0 | Reference Model for an Open Archival Information System (OAIS) - 5 year review | Awaiting ISO review, which may delay publication to ensure ISO/CCSDS have consistent documents | Start date 22Aug2016 End date 06Jun2022
MOIMS DAI | 652.0 | Audit and Certification of Trustworthy Digital Repositories. (ISO 16363) - 5 year review | Awaiting ISO review | Start date 22Aug2016 End date 22Dec2023
MOIMS DAI | 671.0 | Open Archive Information Systems Interoperability Framework (OAIS-IF) Architecture Description | OK, Good work this past year developing info model and interfaces | Start date 31Jul2017 End date 08Dec2025
MOIMS-DAI | 652.1 | Guidelines for Bodies Providing Audit and Certification of Candidate Trustworthy Digital Repositories. (ISO 16919) - 5 year review | Awaiting ISO review | Start date 20Dec2019 End Date 22Dec2023
Notes: JAXA is interested, resources being identified. Possible issues getting resources allocated / schedule.

## Slide 4
  DAI WG Upcoming New Work Items
  To be updated when OAIS-IF related projects finalised
Notes: 4
4
4

## Slide 5
Reinstate the relationship with ISO
  Concern that DAI books were delayed by 18 months by ISO issues
  Request that DAI be allowed to fully participate in communications with ISO
  DAI WG desperately needs ISO to publish our standards, as has happened up to now, because our standards are important outside the Space Community.
Need CCSDS hosting for all digital assets related to the standards in order avoid dependencies on external services or individuals including
  location for software interfaces and protocols defined in the standards.
  Videos are currently hosted on CCSDS.org, but only using CCSDS member’s private accounts. CCSDS should establish its own YouTube account and take on responsibility for CCSDS video assets (or some similar solution.)
      Note: The new video layout by the Secretariat at CCSDS.org > outreach > videos is excellent. Visit it for videos of the recent Keynote presentations made by DAI WG members at the EWA conference in August.
      See https://public.ccsds.org/outreach/overview.aspx
  DAI WG Issues for CESG / CMC
Notes: JAXA is interested, resources being identified. Possible issues getting resources allocated / schedule.