| Action Number | Action Item | Assignee | Due Date |
| --- | --- | --- | --- |
| CMC-S04-A1 | Reinstitute online polling functions to the current CCSDS website. Implement a new online polling mechanism through the redesigned CCSDS website. | CCSDS Secretariat | 15 June 2004 |
| CMC-S04-A2 | Take action to reestablish NASA participation in the MOIMS Area Information Packaging and Registries (IPR) Working Group and Data Archive Ingestion (DAI) Working Group. | NASA | 15 July 2004 |
| CMC-S04-A3 | Update the CCSDS Glossary document (CCSDS A30.0-G-3). Approved CCSDS documents will be culled for new material, and the glossary will be reviewed for out-of-date terminology. The System Engineering Area will review the document and provide input. | CCSDS Secretariat | 30 June 2004 |
| CMC-S04-A4 | Establish an e-mail process that enables users to differentiate between “action required” messages and those that are only informational in nature. This process will be documented in the CCSDS Procedures Manual (CCSDS A00.0-Y-9). | CCSDS Secretariat | 15 July 2004 |
| CMC-S04-A5 | Evaluate the relationship between CCSDS and European Cooperation for Space Standardization (ECSS) standards and attempt to improve allocation of resources by focusing technical standards work towards CCSDS. | Agencies (ESA, CNES, DLR, ASI, and BNSC) | 1 November 2004 |
| CMC-S04-A6 | Update and publish the Achievements and Products document (CCSDS A10.0-Y-5). | CCSDS Secretariat | 15 September 2004 |
| CMC-S04-A7 | Update the CCSDS Procedures Manual (CCSDS A00.0-Y-9) to reflect the current CCSDS “RESTRUCTURED CCSDS ORGANIZATION AND PROCESSES” document and the current CCSDS Strategic and Operating Plans. Particularly review the Procedures Manual to make sure that the on-line voting procedures and decision criteria are clearly explained. Provide the CESG with a draft for review and comment. | CCSDS Secretariat | 15 August 2004 |
| CMC-S04-A8 | Area Directors and CESG management will update the Unique Identification of CCSDS Objects and Services document (CCSDS A31.0-Y-1). Area Directors will provide updates where appropriate. | CESG | September 2004 |
| Action Number | Action Item | Assignee | Due Date |
| CMC-S04-A9 | Distribute the most current version of the TC 999 Business Plan to CMC membership. | CCSDS Secretariat | 15 June 2004 |
| CMC-S04-A10 | Solicit CMC feedback concerning possible new CCSDS logos by making them available for review at the CCSDS website. | CCSDS Secretariat | 15 July 2004 |
| CMC-S04-A11 | Create and post a CCSDS Document Status Report to the CCSDS website. This report will be updated and reposted twice each month. | CCSDS Secretariat | 30 June 2004 |
| CMC-S04-A12 | Obtain updated WG charters from the CSS Area Director containing technical and resource plans for the new “Super Service” development proposal, with 2 initial prototype applications (Return all Data and Return Radiometric Data) plus the extension of the Service Management work at an adequate level to support this ongoing evolution. | CESG | 15 June 2004 |
| CMC-S04-A13 | Assess and implement in the CCSDS website redesign, if accepted, a CESG request that each Area and Working Group have their own web page at www.ccsds.org with both public and private areas, and corresponding links in DocuShare. | CCSDS Secretariat | 31 October 2004 |
| CMC-S04-A14 | Establish an area on the CCSDS website where non-English versions of approved documents can be accessed. | CCSDS Secretariat | 30 June 2004 |
| CMC-S04-A15 | Poll agencies to see if they are willing to provide the resources necessary for the Security WG to support the addition of a new Security section to all future Blue Books. | Agencies (All) | 30 June 2004 |
| CMC-S04-A16 | Issue a formal invitation to the Interagency Operations Advisory Group (IOAG) to a joint meeting at the Fall 2004 meeting in Toulouse, France. In addition, issue request inviting formal liaison status to the IOAG, with Ms. Genevieve Campan as the point of contact. | CCSDS Secretariat | 5 June 2004 |
| CMC-S04-A17 | Formally contact the Object Management Group (OMG) to discuss and clarify recent misunderstandings. Mr. Jean-Francois Kaufeler/ESA will work with Andrew Dowen/NASA. | CCSDS Secretariat | 15 June 2004 |
| Action Number | Action Item | Assignee | Due Date |
| CMC-S04-A18 | Issue formal letters inviting liaison status to the System Modeling Language Partners (SysML) and the U.S. National Archives and Records Admin. (NARA). Provide the CCSDS points of contact and invite SysML and NARA to do likewise. | CCSDS Secretariat | 15 June 2004 |
| CMC-S04-A19 | Send request to CESG to poll Area Directors to discover what liaisons they currently maintain (both formal and informal) and to ascertain their current status. | CCSDS Secretariat | 15 June 2004 |
| CMC-S04-A20 | Formally review and comment on the CCSDS STRATEGIC PLAN, CCSDS A01.1-Y-2, dated April 2004 | Agencies (All) | 1 July 2004 |
| CMC-S04-A21 | Update the “Draft Resource Allocation Matrix” (13 May 2004 version) to reflect the commitments of the Agencies for the upcoming work period (May-November 2004), and send this information back to the CESG within 2 weeks. | Agencies (All) | 15 June 2004 |
| CMC-S04-A22 | Complete the “Resource Commitments for CESG Leadership” Matrix and send this information back to the CESG within 2 weeks. | Agencies (All) | 15 June 2004 |
| CMC-S04-A23 | Update the CCSDS OPERATING PLAN, CCSDS Y-2, based on the actual resource commitments received from the Agencies in response to CMC-S04-A21. | CESG | 31 July 2004 |
| CMC-S04-A24 | Approve the updated CCSDS OPERATING PLAN, CCSDS A01.2-Y-3. | CMC | 15 August 2004 |