TITLE OF GROUP: 	Space Assigned Numbers Authority (SANA) WG

CHAIR: 			Bob Bradford

AREA DIRECTOR:		 Peter Shames

MAILING LIST:		sea-sana@mailman.ccsds.org

A.	RATIONALE:

CCSDS A02.1-Y-2.  Restructured Organization and Processes for the Consultative Committee for Space Data Systems. Yellow Book.  Issue 2. April 2004:

1.4.6 Space Assigned Numbers Authority (SANA) The core registrar for the CMC’s activities is the SANA. Many space mission protocols require that someone keep track of key protocol numbering assignments that were added after the protocol came out. Typical examples of the kinds of registries needed are for Spacecraft IDs, protocol version numbers, reserved APIDs and SFDU Control Authorities. The SANA provides this key configuration management service for CCSDS. The CCSDS Management Council (CMC) approves the organization that will act as the SANA. Its public interface is focused through web-based services provided by the Secretariat.

The purpose of the Space Assigned Numbers Authority (SANA) Working Group is to establish a high level authoritative registry and proposed SANA Operations Entity for CCSDS under the responsibility of the CESG.

A SANA registry will register information about protocols and standards, as they relate to spaceflight, that need updating or extension more frequently than is practical in a CCSDS standard or report.  In general, the SANA team will provide:

  - A single focus (a CCSDS Registry Portal) for entry into the CCSDS realm with participation ranging from an organization’s URL to actual database integration

  - Expertise concerning registry creation and management

  - Resolution to concerns/problems between other standards organizations and CCSDS, and

  - Security of registries

There are four prioritized categories of work which need to be either investigated for registry requirements or assessed for possible adjustment.

Category one (1) is current CCSDS registries, namely SCIDs and SFDU CA.

Category two (2) is the set of protocol identifiers, assigned numbers, port numbers and reserved APIDs that are currently documented within a variety of CCSDS documents and SCPS protocol numbers including other current deployments.  This would include existing elements e.g. glossary, ground data systems and acronym lists.

Category three (3) is the list of current CCSDS working groups and birds of a feather that may require registries and also includes current CCSDS developments including SLE service providers and XML schema.

Category four (4) is the catch all for all other activities which may possess a registries requirement, e.g. information models, name spaces, reference software, but currently do not fall under CCSDS and/or do not currently operate under a registry.

B.	GOALS, OBJECTIVES AND DELIVERABLES:

Goal: Enable interoperability through CCSDS registries; provide easy, common access to CCSDS registered information through a single CCSDS portal.

Objective 1: Establish a CCSDS system of registries for space assigned numbers for current and future international space operations and information management.

Objective 2: Coordinate and integrate current CCSDS registry processes and other operational information into a single unified standardized framework working with cooperating organizations.

Objective 3: Provide a focal point from which any authorized organization or individual can acquire CCSDS registry content and be pointed to Agency, and other, related registry content as appropriate.

Objective 4: Propose a SANA Operations Entity and develop rules and processes to operate and support the SANA and identify the resources needed for the continuing operation, deployment, outreach, and evolution.

Objective 5: Facilitate transition to a working organization under CESG responsibility.

Green Book, addressing security, under the auspices of the CESG.

Deliverable 1: Provide an assessment of categories 1 through 4 information sources for registry requirements in a SANA White Paper or Green Book.

Deliverable 2: Develop a prototype of the single point of entry into the SANA, providing at least two different sets of relevant data objects from different organizations provided through a web based interface with appropriate security.

Deliverable 3: Provide an operations plan to include a SANA organizational structure, operational rules, processes and framework in a SANA White Paper or

Deliverable 4: Publish Red Book/Blue Book as appropriate based on assessments, progress and overall success.

- SCHEDULE:

| Date | Milestone |
| --- | --- |
| Oct 2005 | SANA WG Charter approved |
| Apr 2006 | Requirements assessment complete |
| Jun 2006 | Draft org/rules/processes complete |
| Aug 2006 | White Paper(s)/Green Books (org/rules/processes) review complete |
| Aug 2006 | Prototype development begins |
| Sep 2006 | SANA WG meeting, review documents, coordinate final Green Book, review Green Book draft (in Rome) |
| Oct 2006 | Prototype complete |
| Oct 2006 | Finalize Green Book for review |
| Nov 2006 | Draft Red/Blue Books |
| Jan – May 2007 | Review of books |
| Jun 2007 | Approval of books |
| Jun 2007 | Portal access with pointers and identified databases from central SANA site |
| Aug 2007 | Full operational status |

# D.	Risk Management Strategy:

D1	Technical risks:

Risks: No significant technical risk is involved.  Technical risks are low since this is essentially process based.  The prototype activity does not entail any cutting edge technologies.

Mitigation:  None required

D2	Management risks:

Risks:  Some management risk is involved including the usual politics and consensus building necessary for success.

  - Issues of privacy, ownership

  - Issues of security and access to aggregated information

  - International resources for the WG and operations team

Mitigation: Work as required

E.	RESOURCE  REQUIREMENTS:

| FY06: Total 1.15 FTEs |  |
| --- | --- |
| WG Lead, 0.4 FTE | NASA/MSFC |
| White Paper and Book Development/Review, 0. 2 FTE | NASA/JPL |
| White Paper and Book Development/Review, 0. 2 FTE | NASA/GSFC |
| White Paper and Book Review, 0. 05 FTE | ESA/ESOC |
| White Paper and Book Review, 0. 05 FTE | JAXA/ISAS |
| White Paper and Book Review, 0. 05 FTE | CNES |
| Prototype, 0.2 FTE for FY06 | NASA/JPL |
| FY07: Total .9 FTEs |  |
| WG Lead, 0.3 FTE | NASAMSFC |
| Portal/Database integration/pointing, 0. 2 FTE | NASA/JPL |
| Portal/Database integration/pointing, 0. 2 FTE | NASA/GSFC |
| Portal/Database integration/pointing, 0. 05 FTE | ESA/ESOC |
| Portal/Database integration/pointing, 0. 05 FTE | NASA/MSFC |
| Portal/Database integration/pointing, 0. 05 FTE | JAXA/ISAS |
| Portal/Database integration/pointing, 0. 05 FTE | CNES |