## Sheet1
Seq | Month | Year |  |  | Document | Deliverable | Priority
1 | 10 | 2014 | 10+2014i | ODM | Orbit Data Messages Version 2 | 5 year review complete | 1
| 0 | 2015 | 2015i
2 | 10 | 2015 | 10+2015i | TDM | Tracking Data Message Version 2 | Pink Book/Completed Agency Review | 1
3 | 10 | 2015 | 10+2015i | GREEN | Navigation Green Book Version 4, v.1 | Green Book complete | 2
| 0 | 2016 | 2016i
4 | 4 | 2016 | 4+2016i | TDM | Tracking Data Message Version 2 | Blue Book complete | 1
5 | 4 | 2016 | 4+2016i | PRM | Pointing Requests Message | Red Book/Commence Agency Review | 2
6 | 4 | 2016 | 4+2016i | SMM | Spacecraft Maneuver Message (V1/MPM) | Red Book/Commence Agency Review | 3
7 | 4 | 2016 | 4+2016i | NHM | Navigation Hardware Message | Red Book/Commence Agency Review | 4
8 | 10 | 2016 | 10+2016i | ODM | Orbit Data Messages Version 3 | Pink Book/Completed Agency Review | 1
9 | 10 | 2016 | 10+2016i | SREM | Satellite Re-Entry Message | Abstract/Concept Paper complete | 1
10 | 10 | 2016 | 10+2016i | XML | NDM/XML Version 2 | Pink Book (common schemas only) | 2
11 | 10 | 2016 | 10+2016i | ADM | Attitude Data Messages Version 2 | Red Book/Commence Agency Review | 3
| 0 | 2017 | 2017i
12 | 4 | 2017 | 4+2017i | NHM | Navigation Hardware Message | Blue Book complete | 1
13 | 4 | 2017 | 4+2017i | SMM | Spacecraft Maneuver Message (V1/MPM) | Blue Book complete | 2
14 | 4 | 2017 | 4+2017i | ADM | Attitude Data Messages Version 2 | Blue Book complete | 3
15 | 10 | 2017 | 10+2017i | PRM | Pointing Requests Message | Blue Book complete | 1
16 | 10 | 2017 | 10+2017i | ODM | Orbit Data Messages Version 3 | Blue Book complete | 2
17 | 10 | 2017 | 10+2017i | SREM | Satellite Re-Entry Message | Initial White Book complete | 2
| 0 | 2018 | 2018i
18 | 4 | 2018 | 4+2018i | GREEN | Navigation Green Book Version 4, v.2 | Green Book complete | 1
19 | 4 | 2018 | 4+2018i | XML | NDM/XML Version 2 | Pink Book/Completed Agency Review | 1
20 | 4 | 2018 | 4+2018i | SPM | Spacecraft Perturbation Message | Abstract/Concept Paper complete | 3
21 | 10 | 2018 | 10+2018i | CDM | Conjunction Data Message | 5 year review complete | 1
| 0 | 2019 | 2019i
22 | 4 | 2019 | 4+2019i | XML | NDM/XML Version 2 | Blue Book complete | 1
23 | 4 | 2019 | 4+2019i | EVM | Events Message | Initial White Book complete | 1
24 | 4 | 2019 | 4+2019i | SPM | Spacecraft Perturbation Message | Initial White Book complete | 2
25 | 10 | 2019 | 10+2019i | SREM | Satellite Re-Entry Message | Red Book/Commence Agency Review | 1
| 0 | 2020 | 2020i
26 | 4 | 2020 | 4+2020i | SMM | Spacecraft Maneuver Message (V2/MDM+MAM) | Red Book/Commence Agency Review | 3
27 | 10 | 2020 | 10+2020i | SPM | Spacecraft Perturbation Message | Red Book/Commence Agency Review | 1
| 0 | 2021 | 2021i
28 | 4 | 2021 | 4+2021i | EVM | Events Message | Red Book/Commence Agency Review | 1
29 | 4 | 2021 | 4+2021i | TDM | Tracking Data Message Version 2 | 5 year review complete | 1
30 | 10 | 2021 | 10+2021i | SREM | Satellite Re-Entry Message | Blue Book complete | 1
| 0 | 2022 | 2022i
31 | 4 | 2022 | 4+2022i | SMM | Spacecraft Maneuver Message (V2/MDM+MAM) | Blue Book complete | 1
32 | 4 | 2022 | 4+2022i | NHM | Navigation Hardware Message | 5 year review complete | 3
33 | 10 | 2022 | 10+2022i | SPM | Spacecraft Perturbation Message | Blue Book complete | 1
34 | 10 | 2022 | 10+2022i | PRM | Pointing Requests Message | 5 year review complete | 2
| Meetings | Event Ct | Month/Year
| 2014, Fall | 1 | 10+2014i | 10
| 2015, Spring | 0 | 4+2015i | 4
| 2015, Fall | 2 | 10+2015i | 10
| 2016, Spring | 4 | 4+2016i | 4
| 2016, Fall | 4 | 10+2016i | 10
| 2017, Spring | 3 | 4+2017i | 4
| 2017, Fall | 3 | 10+2017i | 10
| 2018, Spring | 3 | 4+2018i | 4
| 2018, Fall | 1 | 10+2018i | 10
| 2019, Spring | 3 | 4+2019i | 4
| 2019, Fall | 1 | 10+2019i | 10
| 2020, Spring | 1 | 4+2020i | 4
| 2020, Fall | 1 | 10+2020i | 10
| 2021, Spring | 2 | 4+2021i | 4
| 2021, Fall | 1 | 10+2021i | 10
| 2022, Spring | 2 | 4+2022i | 4
| 2022, Fall | 2 | 10+2022i | 10
| 17 | 34
Generalized Navigation Component Message