## WG3_Roster
Role | Country / Region | Gender | First Name | Last Name | Organisation | Email address | Phone | 2015-11-01 | May-16 | 2016-11-01 | 2017-06-01
WG3 member | Brazil | Mr. | Antonio Vinicius | Diniz Merladet | DCTA / Industrial Fostering and Coordination Institute (IFI) | dinizavdm@ifi.cta.br |  |  |  | excused
WG3 observer | Brazil | Mr. | Helio | Kuga | INPE | hkakinha@hotmail.com |  |  |  |  | ?
WG3 member | Brazil | Mr. | Mario | Niwa | DCTA / Industrial Fostering and Coordination Institute (IFI) | niwamn@ifi.cta.br |  | excused | excused | excused
WG3 observer | Brazil | Mr. | Paulo | Sakai | DCTA / Industrial Fostering and Coordination Institute (IFI) | sakaiprs@iae.cta.br |  |  |  |  | ?
WG3 observer | Brazil | Mr. | João | Matos | DCTA / Industrial Fostering and Coordination Institute (IFI) | joaomatosjbcm@ifi.cta.br |  |  |  |  | ?
WG3 member | China | Mr. | Han | Feng | China Academy of Launch Vehicle Technology | hanfeng2001fei@126.com |  | X | X | X
WG3 member | China | Mr. | Hu | Haifeng | China Academy of Launch Vehicle Technology | huhaifeng2002@hotmail.com |  | X | X
WG3 member | China | Mr. | Shao-wie | Feng | China Academy of Launch Vehicle Technology | fawwi@126.com | +86 137 1868 3598 |  | X
WG3 member | China | Mr. | Zhaozhao | Gao | China Academy of Space Technology | zhaoxiaofang@live.com |  |  | X | X
WG3 member | China | Ms. | Xiaofang | Zhao | China Academy of Space Technology | zhaoxiaofang@live.com | +8 010 6811 3190 |  | X | X
WG3 member | China | Mr. | Tong | Xin | China Astronautics Standards Institute (CASI) | tongxinsuede@163.com
WG3 observer | China (HoD) | Mr. | Wie | Yonggang | China Astronautics Standards Institute (CASI) | wygww567@sina.com |  |  |  |  | ?
WG3 observer | China | Ms. | Li | Qiong | China Astronautics Standards Institute (CASI) | std@ht708.com.cn |  |  |  |  | ?
WG3 observer | China | Mr. | Wei | Wei | China Astronautics Standards Institute (CASI) | wei90909@163.com |  |  |  |  | ?
WG3 observer | China | Mr. | Lei | Shisong | China Astronautics Standards Institute (CASI) | leishisong@hotmail.com |  |  |  |  | ?
WG3 member | China | Mr. | Yanfeng | Gu | Shanghai Academy of Spaceflight Technology (SAST) | couth_gyf@sohu.com
WG3 member | China | Ms. | Mingliang | Tang | Shanghai Academy of Spaceflight Technology (SAST) | tang2mingliang@sina.cn |  | X | X | X
WG3 member | China | Mr. | Jialin | Wu | Shanghai Academy of Spaceflight Technology (SAST) | wujialin_6666@sina.com | +86 21 2418 6703 | X | X | X
WG3 member | Europe | Mr. | Tim | Flohrer | ESA ESOC | tim.flohrer@esa.int
WG3 member | Europe | Mr. | Vitali | Braun | ESA ESOC (IMS Space Consultancy GmbH) | Vitali.Braun@esa.int | +49 6151 902036
WG3 observer | Europe | Mr. | Alfio | Mantineo | ESA ESOC (Q&S Human Spaceflight & Operations) | alfio.mantineo@esa.int | +49 6151 902462
WG3 observer | Europe | Mr. | Mario | Merri | ESA ESOC | mario.merri@esa.int
WG3 observer | France | Ms. | Nathalie | Fuentes | CNES | nathalie.fuentes@cnes.fr
WG3 observer | France | Mr. | Karim | Benmeziane | BNAE | benmeziane@bnae.fr | +33 1 4765 7009
WG3 convener | Germany | Mr. | Andre | LaCroix | Airbus Safran Launchers (ASL) | andre.a.lacroix@airbusafran-launchers.com | +49 421 539-5378 | X | X | X | X
WG3 member | Germany | Mr. | Osvaldo | Peinado | DLR - German Space Operations Center (GSOC) | osvaldo.peinado@dlr.de | +49 8153 28 3010
WG3 observer | Germany | Mr. | Benjamin | Gentz | DLR German Space Administration | Benjamin.Gentz@dlr.de | +49 228 447 616 |  |  |  | WG5
WG3 observer | Germany (HoD) | Mr. | Stephan | Bonk | DLR German Space Administration | stephan.bonk@dlr.de |  | WG5 | WG5 | WG5 | WG5
WG3 observer | Germany | Mr. | Kristofer | Proll | DIN (CEN/CENELEC TC-5 Secretariat) | kristofer.proll@din.de
WG3 observer | Germany | Mr. | Daniel | Schiller | DLR German Space Administration (ECSS TA member) | daniel.schiller@dlr.de | +49 228 447 249
WG3 observer | Italy | Mr. | Roberto | Destefanis | ECSS Liaison (Thales Alenia Space) | roberto.destefanis@thalesaleniaspace.com | +39 01 1718 0320 | WG7 | WG7 | WG7 | WG7
WG3 member | Japan | Mr. | Akira | Kato | Japan Aerospace Exploration Agency (JAXA) | kato.akira@jaxa.jp | +81 50 3362 7889
WG3 member | Japan | Ms. | Mari | Goto Yuzawa | Mitsubishi Electric Co. | Yuzawa.Mari@dn.MitsubishiElectric.co.jp |  | X |  | X
WG3 member | Japan | Mr. | Jun'ichi | Horikawa | Mitsubishi Heavy Industries (MHI) | junichi_horikawa@mhi.co.jp | +81 52 611 2656 | X | X | X
WG3 member | Japan | Mr. | Yoichiro | Uchida | The Society of Japanese Aerospace Companies (SJAC) | yoichiro.uchida@sjac.or.jp
WG3 member | Russian Federation | Mr. | Anton | Agoshkov | TSENKI | agowkov_a@mail.ru |  | excused
WG3 member | Russian Federation | Mr. | Artyom V | Bondarenko | TsNIIMash | bondarenkoav@tsniimash.ru; a.bondarenko@fondpgu.ru | +7 915 347 29 78 | WG7 |  | excused
WG3 member | Russian Federation | Mr. | Anton | Spivak | TsNIIMash | tsniimash@bk.ru; instans@tsniimash.ru |  |  | X
WG3 member | UK | Mr. | Brian | Swinburne | Airbus Defence and Space | brian.swinburne@airbus.com |  | excused | excused | X
WG3 member | UK | Mr. | John | Davey | UK Head of Delegation ISO TC20 SC14 | j.r.davey@btopenworld.com
WG3 observer | UK | Mr. | Peter Hedley | Stokes | ISO TC20/SC14/WG7 Convenor (PHS Space Ltd.) | hedley_stokes@msn.com |  | WG7 | WG7 | WG7 | WG7
WG3 observer | UK | Mr. | Richard | Hebden | SSTL | richard.hebden@sstl.co.uk
WG3 member | Ukraine | Mr. | Valeriy | Kapinus | Yuzhnoye State Design Office | TK117@yuzhnoye.com
WG3 member | Ukraine | Ms. | Galyna | Matus | Yuzhnoye State Design Office | TK117@yuzhnoye.com |  | excused
WG3 member | USA | Mr. | Dan | Oltrogge | Analytical Graphics Incorporated (AGI) | doltrogge@agi.com | +1 719 482 4552 | X | X | X
WG3 member | USA | Mr. | David | Berry | CCSDS NAV WG (NASA Jet Propulsion Laboratory) | david.s.berry@jpl.nasa.gov
WG3 member | USA | Mr. | Dave | Finkleman | Comcast / SkySentry | dfinkleman@gmail.com | +1 719 510 8282 | X | excused
WG3 observer | USA | Mr. | Bill | Ailor | Aerospace Corporation | william.h.ailor@aero.org
WG3 observer | USA | Mr. | Nick | Tongson | AIAA | nickt@aiaa.org | +1 703 264 7515 |  | SC14 |  | SC14
TBD | France | Mr. | Christophe | Ducamp | Airbus Defence and Space
TBD | Germany | Mr. | Roland | Gessner | Airbus Defence and Space
TBD |  |  |  |  | Thales Alenia Space
TBD |  | Ms. | Costello | Nathalie | ???
TBD |  | Mr. | Stijn | Lemmens | ESOC
TBD | UK | Mr. | Alex | da Silva Curiel | SSTL | a.da-silva-curiel@sstl.co.uk
TBD | UK | Mr. | Richard | Hebden | SSTL | richard.hebden@sstl.co.uk

## WG3_ActionItemsList
Action Items List - ISO TC20/SC14/WG3 |  |  |  | Issue: | 2017-01-03
Ref. | Action: | Actionee | Deadline | Status | Result
WG3 45-01 | Propose to SC14 Secretariat to execute Resolution 374 with a written gratitude letter signed at least by the SC14 Chairman | WG3 Convener | May-2016 | Closed | see ISO TC20 SC14 Resolution 394 (May-2016) TC20/SC14 resolves to execute Resolution 374 with a written gratitude letter signed at least by the SC14 Chairman, to recognize the outstanding leadership and dedication of Dr. Dave Finkleman, and to thank him for his extensive contributions to WG3 as well as for having significantly advanced the overall SC14 standardization activities
WG3 45-02 | Propose a resolution for next SC14 Plenary, that Mr Oltrogge’s liaison role be expanded to SC14 perimeter | WG3 Convener with SC14 Secretariat | May-2016 | Closed | see ISO TC20 SC14 Resolution 395 (May-2016) TC20/SC14 resolves that Dan Oltrogge act as the technical liaison from SC14 to the CCSDS.
WG3 45-03 | Contact the French delegation (Karim Benmeziane, BNAE) to clarify the nomination of the new representative(s) and contact point(s) from France for WG3 activities, following the announced retirement of Mr Bruno Lazare/CNES. | WG3 Convener | May-2016 | Open | Open action at French mirror committee BNAE CB-MES since Dec-2015. No progress during BNAE meeting Apr-17.
WG3 45-04 | Clarify with SC14 secretariat (Nick Tongson) the status of FDIS 16679 and related disposition of comments. | WG3 Convener | Dec-2015 | Closed | see ISO TC20/SC14 work program (completion date: Sep-2015)
WG3 45-05 | Clarify with SC14 secretariat (Nick Tongson) the status of FDIS 16699 and related disposition of comments. | WG3 Convener | Dec-2015 | Closed | see ISO TC20/SC14 work program (completion date: Nov-2015)
WG3 45-06 | Contact the Russian delegation (Anton Spivak) to nominate a contact point for the ISO 17400 5-years systematic review confirmation. | WG3 Convener | May-2016 | Closed | Mr.Tsukanov is PL still responsible for 17400 though he doesn’t participate in WG3 meetings any more (Email AS 19-Apr-2016). For the time being, Anton Spivak is the point of contact to WG3
WG3 45-07 | Contact the ISO 14620 project leaders (Stephan Bonk/DLR, Emmanuelle Vergnault/CNES) for ensuring the liaison with WG3 during revision work of this standard series | WG3 convener | Dec-2015 | Open | Action addressed by German delegation at ISO TC20/SC14/WG5 Fall-2016 meeting (revision of ISO 14620-2).
WG3 45-08 | Contact CCSDS (ISO TC20/SC13) to obtain information on how they defined and implemented their process for terminology harmonisation incl. centralized registry management | WG3 liaison CCSDS (Mr. Dan Oltrogge) | May-2016 | Closed | See ISO TC20/SC14/WG3 MoM Fall-2016
WG3 45-09 | With reference to SC14 Resolution 377 propose a resolution for next SC14 Plenary to decide SC14 unique definitions for the term “spacecraft” and related terms “space vehicle”, “launcher”, “launch vehicle”, “payload”, etc. | WG3 Convener with SC14 Secretariat | May-2016 | Closed | Open action at ISO TC20/SC14/WG5 Fall-2016 meeting (revision of ISO 10795) Definition of terms reviewed durint ISO TC20/SC14/WG3+WG7 Fall-2016 meeting. New action WG3 47-03 established Nov-16.
WG3 45-10 | Contact Project leader (Dr Akira Kato) to clarify the disposition of the raised comment on 27875 §6.3.2.2 | WG3 members | Dec-2015 | Closed | see ISO TC20/SC14 work program (completion date: Mar-2016)
WG3 45-11 | WG3 members to identify persons from operator organisations (launcher, spacecraft) and other stakeholders (e.g. commercial space services) to be contacted for their involvement in developing the SC14 and WG3 future work plan and objectives | WG3 members | May-2016 May-2017 | Open | During ISO TC20/SC14 Plenary May-2016 (WG3 status presentation). See ISO TC20/SC14 Resolution 396 TC20/SC14 resolves to assemble a task force to develop a survey to be sent to appropriate stakeholders to increase awareness, obtain feedback, and encourage participation See also email SC14 Secretariat 16-Nov-2016 (proposed SC14 survey).
WG3 45-12 | To raise awareness of the SC14 Chair on the needs to review and update the SC14 charter and scope of working groups | WG3 Convener | Dec-2015 | Closed | Addressed during ISO TC20/SC14 Plenary May-2016 (WG3 status presentation). Delegations did not see needs to revise WG structure for the moment. WG3 Framework has been reviewed/updated during Fal-2016 meeting, which will help to clarify interfaces with the other SC14 Working Groups.
WG3 45-13 | Update WG3 distribution list on KAVI server | WG3 Convener with SC14 Secretariat | Dec-2015 | Closed | see "SC14 WG Rosters" (email Nick Tongsen 30-Jun-2016) Email WG3 sent 01-01-2017 to SC14 Secretariat with new updates following WG3-Nov-16 meeting
WG3 47-01 | Re-issue ISO 26872 with editorial changes only, and provide related WG3 recommendations to SC14 Secretariat | WG3 Convener | Dec-2016 | Open | Request as discussed Nov-16 sent to SC14 Secretariat 01-Jan-2017. A revision of 26872 has been initiated (email Nick Tongson 05-Apr-2017). Bill Ailor recontacted by email on 17-Apr-2017. No answer recieived yet. WG3 shall propose May-17 a draft resolution on whether to do a minor revision or an amendment. In that resolution, need to confirm the Project Leader, confirm no change in scope, and confirm the timeframe for development. We can start at the DIS stage.
WG3 47-02 | Clarify with ISO TC207SC14 Secretariat the way forward in case of subject matter expertise from originating country being no longer available, and when changes to a published document seem to be necessary | WG3 Convener | May-2017 | Closed | Question sent to SC14 Secretariat 01-Jan-2017: Typically, ISO Central Secretariat will interpret the lack of subject matter experts as a lack of interest in the standard. Whatever the case might be, the procedure is to initiate a ballot for withdrawal of the standard to determine if there is still sufficient support for keeping it. However, before initiating a withdrawal ballot, it might be a good idea to ask the HoDs if there is still interest in their countries for the standard.
WG3 47-03 (replacing 45-09) | With reference to SC14 Resolution 377, provide WG3 relevant definitions to ISO 10795 PL (Mr. Roberto Sakai and Ms. Maria Alice Carneiro), as well as the WG3/WG7 agreed definitions for the terms “spacecraft” and "launch vehicle" and related terms such as "launcher" etc. NOTE-1: The list of SC14 published documents that are impacted by revised terms should be established in the frame of the ISO 10795 revision. NOTE-2: The possibility to provide the glossary of terms through internet should be investigated in the frame of the ISO 10795 revision | WG3 Convener | Dec-2016 May-2017 | Open | WG3 Convenor contacted SC14 Secretariat as well as WG5 Convenor and asked for a specific workshop on terminology during SC14 Plenary week May-2017. Answer from Nick Tongson on 06-Jun: Unfortunately, due to the high attendance for these meetings in Paris, all the WG rooms are at or near capacity, so a separate meeting on terminology in one of the rooms is not possible. A brief meeting with WG5 Convenor has been suggested by WG7 Convenor ) to discuss their plans for harmonizing terminologies.
WG3 47-04 | Propose detailed changes (test requirements at launch site) to complement ISO DIS 24917 (general test requirements for LV), in cooperation with WG2 project leader (Mr. Alexander Isaev) | Mr Han Feng | 2017-02-01 | Closed | Email sent 26-Feb-2017 with new proposal as the structure of ISO 24917.
WG3 47-05 | Provide input to the multiple collocation in GEO NWIP (to Ms. Zhao Xiaofang) with regard to operator communication for collocation scenarii | Mr. Brian Swinburne | Dec-2016 | Closed | Email sent 24-Nov-2016 with information addressing operator communications
WG3 47-06 | Initiate formal NWIP to SC14 Secretariat on "Procedure for multiple satellite collocation in GEO" | Ms. Zhao Xiaofang | May-2017 | Closed | Email sent 15-Mar-2017 by Xiaofang Zhao with revised draft, Form 4 (NWIP) and Annex 4 (market evaluation).
WG3 47-07 | Clarify the status of the "atmospheric density / spacecraft aerodynamic forces" NWIP | WG3 Convener | May-2017 | Open | Question sent to Dave Finkleman 01-Jan-2017. DF is willing to draft, if WG4 confirms interest to participate actively. The subject is still appropriate,
WG3 47-08 | Provide further information as discussed during Fall-2016 meeting on the potential work items proposed 15-Nov-2016 | Mr Artyom V. Bondarenko | May-2017 | Open

## WG3_WorkPlan
| Issue: | Jun-27 |  | ISO TC20/SC14/WG3 Operations & Ground support
|  |  | Operations |  |  |  |  | Ground support
Operations Scheduling | Operations Data Exchange |  | Launch Operations |  | On-Orbit Flight Safety | Flight Operations | Facilities | Support Equipment | Logistics
(CCSDS Liaison) | ISO 26900 |  | ISO 16679 |  | ISO 23339 ** | ISO 14711 | ISO/TR 17400 | ISO 14625 | ISO 16458
Pointing Request Msg (Sensor Scheduling) NWIPs TT&C Operation Scheduling Msg Task scheduling Msg Sched/Cmd Msg Obs System Data Msg | Orbit Data | Msg ODM | Relative Motion Anal. LV/SC Separation |  | Estimate Residual S/C Propellant / Disposal | Unmanned Mission Operations Concept | Launch & Integration Site Test Req. | Ground Support Equipment | Unmanned S/C Transportation
| (CCSDS Liaison) |  | ISO/TR 19473 |  | ISO 26872 ** | ISO 14619 | ISO 26870 | ISO 15389 Amd.1
| Launch Data Msg Attitude Data Msg Navigation Data Msg Events Msg Re-entry Data Msg Fragmentation Data Msg Tracking Data Msg Conjunction Data Msg [NWIPs] Health & Status Msg RFI Alert Msg Sensor Description Msg |  | Orbit Elements LV/SC Separation |  | S/C Disposal Operating at GEO | Space Experiments | Launch Site Operational Doc. | Flight-to-Ground Umbilical
|  |  | ISO 14620-2 (WG5) |  | ISO 16164 ** | ISO 14950 | ISO 16159 | ISO 15860
|  |  | Safety - Launch Site Operations |  | S/C Disposal Operating at LEO | Unmanned S/C Operability | Launch Site Analysis of Failures | Gas Contamination Field Tests Measur.
|  |  | ISO 14620-3 (WG5) |  | ISO 27852 | ISO 23041 |  | ISO 22108
|  |  | Safety - Flight Safety Systems |  | Orbit Lifetime Estimation | Unmanned Operat. Procedures Doc. |  | Non-Flight Items Ident. & Control
[5 empty] | ISO/TR 16158 | ISO/TR 11233
[5 empty] | Avoiding Collisions Orbiting Systems | Orbit Determination & Estimation
[5 empty] | ISO 16699 ** | ISO NWIP
[5 empty] | Disposal of Orbital Launch Stages | RF Interference Mitigation
ISO 27875 Amd.1 *
S/C & LV Re-entry Risk Management
ISO N0957 ***
Small S/C Dev/Ops Best Practices
ISO NWIP
Multiple-S/C at GEO Collocation Coord.
New Work Item Proposal
Std or TR: Published
Std: Up for member body review
Potential new work area
CCSDS (ISO TC20/SC13) work item
WG3 work item
Other SC14 WG
(*) To be consolidated with ISO 21095 (WG7)
(**) Being cosolidated to detailed debris mitigation requirements
(***) To be cancelled or consolidated with work of ISO 20991 (WG1)