CCSDS NAVIGATION WG ACTION ITEMS
(From Gaithersburg, April 2018, Chronological Order)

Last Update: 13-Apr-2018

# CURRENT ACTION ITEMS

The following action items were produced during the meetings.  They are also available on the CWE at http://cwe.ccsds.org/moims/docs/MOIMS-NAV/Meeting%20Materials/2018/Spring/navwg-action-items-201804.pdf . (Note that the table below reflects the state as the "Last Update Date", which is not necessarily the state as of the end of the meetings.)

# New Action/Outstanding Action Items

| ## | Action Item | Actionee | Due Date (Original) | Due Date (Current) |
| --- | --- | --- | --- | --- |
| 52 | XML Section for ADM | David Berry | 31-Dec-2016 | 24-Apr-2018 |
| 10 | Request deletion of "CDM Originator" SANA Registry | David Berry | 09-Apr-2018 | 24-Apr-2018 |
| 33 | Update "NEM Requirements" document and send it by 04/27/2018. | Alain Lamy | 27-Apr-2018 | 27-Apr-2018 |
| 38 | Request updates to SANA infrastructure on PRM Registry (Provisional => Assigned, Policy, Authority, etc.) | David Berry | 30-Apr-2018 | 30-Apr-2018 |
| 3 | Draft Test Plan Section for TDM Phase Counts | Fran Martinez | 09-Apr-2018 | 01-May-2018 |
| 19 | Review SANA Registry annex information (time, frames, etc.) | All | 14-Mar-2018 | 01-May-2018 |
| 15 | Finalize SANA Registries for Time Scales, Reference Frames, Element Sets, etc. | All | 21-Mar-2018 | 08-May-2018 |
| 26 | XML Section for ODM (update) | David Berry | 08-May-2018 | 08-May-2018 |
| 29 | Review the Time System material targeted for the SANA Registry and "make it perfect" | Frank, Fran, Cheryl | 08-May-2018 | 08-May-2018 |
| 42 | Re-type attitude material LATeX | Julie Halverson | 08-May-2018 | 08-May-2018 |
| 25 | Produce ODM P2.38 | Dan Oltrogge | 15-May-2018 | 15-May-2018 |
| 27 | Fix errors in draft RDM XML schema to conform to the RDM draft (keyword change, number of segments => 1) | David Berry | 15-May-2018 | 15-May-2018 |
| 32 | Define schema that can be used with an XML editor to define events and parameters that go with it to validate the event description | Fran Martinez | 15-May-2018 | 15-May-2018 |
| 36 | Prioritize SANA Annex material | All | 16-May-2018 | 16-May-2018 |
| 41 | Produce Navigation Data Messages Overview draft #1 | Patrick Zimmerman | 16-May-2018 | 16-May-2018 |
| 37 | Provide SANA Annex material to SANA Operator | David Berry | 17-May-2018 | 17-May-2018 |
| 98 | Produce Navigation Events Message initial draft | Alain Lamy | 31-Jan-2018 | 21-May-2018 |
| 30 | Provide content on international standards to UNCOPUOS/LTSSA WG | Dan, David | 31-May-2018 | 31-May-2018 |
| 31 | Look at implementation of epoch time system in abstract type, convey preference to Colin | Fran Martinez | 31-May-2018 | 31-May-2018 |
| 39 | Provide "Description" for each template on PRM Registry | Fran Martinez | 31-May-2018 | 31-May-2018 |
| 100 | Produce Navigation D&C Green Book 3.6 | Dale Force | 01-Mar-2018 | 13-Jun-2018 |
| 40 | Provide "XML Boot Camp" session (dedicated telecon?) | Fran Martinez | 20-Jun-2018 | 20-Jun-2018 |
| 28 | Review Navigation D&C Green Book 3.6 | All | 27-Jun-2018 | 27-Jun-2018 |
| 7 | Request CESG Poll for Navigation D&C Green Book 3.6 | David Berry | 13-Apr-2018 | 27-Jun-2018 |
| 35 | Produce ACM Draft 3 | Julie Halverson | 30-Jun-2018 | 30-Jun-2018 |
| 22 | Produce NDM/XML P1.1 | David Berry | 31-Jan-2016 | 15-Jul-2018 |
| 34 | TDM Version 3 initial thoughts... send to Cheryl | All | 01-Oct-2018 | 01-Oct-2018 |
| 83 | Navigation Data Messages KVN Structural Requirements | Alain, Cheryl, Dan, David, Julie | 30-Sep-2017 | 15-Oct-2018 |
| 43 | Next available number | N/A | 31-Dec-2035 | 31-Dec-2035 |

# COMPLETED Action Items

| ## | Action Item | Actionee | Status | Completion Date |
| --- | --- | --- | --- | --- |

# CANCELLED Action Items

| ## | Action Item | Actionee | Reason |
| --- | --- | --- | --- |