# mission operations and information management services area

## Information Packaging and Registry Working Group

| Title of Group | 2.3 Information Packaging and Registry Working Group |
| --- | --- |
| Chair | Louis Reich |
| Area Director | Nestor Peccia |
| Mailing List | moims-ipr@mailman.ccsds.org |

### Rationale

Agencies need to reduce the cost and increase automation among applications associated with the exchange of information applications and those facilities that produce, distribute, and store information. CCSDS has been a leader in developing data packaging techniques and their association with the registration of schemas/data definitions.  CCSDS has produced several standards in this area that are in active use within agencies, and include those known as Standard Formatted Data Units, Parameter Value Language, Control Authority Procedures; and Control Authority Data Structures; however, the speed of technology change including the emergence of XML as a standard data description language, the vast increase in the size and interrelationships of space data, and the emergence of the Internet as a data delivery mechanism requires that vastly different versions of these documents be written. Also, the vast increases in space-hardened computer power and communications bandwidth allow techniques that previously were considered ground system only to be utilized in end-to-end space data systems. The large size and binary nature of space prevents the direct usage of commercial or international earth-based standards.

### Goals

The goals of this Working Group include:

- Collect use cases from the space operations community and develop requirements for XML data packaging; Based on these requirements, develop a set of recommendations and best practices documents that specify an extensible framework for packaging data and metadata that can contain an object physically, or by reference (e.g., Universal Resource Locator (URL), Universal Resource Identifier (UR), or by Universal Resource Name (URN).  This includes the ability to express appropriate relationships using XML and related techniques, and the implementation of the packaging format in an appropriate set of network and file protocols

;

- Oversee the deployment of at least two independent implementations of the packaging framework; Conduct prototyping and interoperability tests in many areas of space data systems (refer to the Resource Requirements paragraph);

- Based on the experience gained from the interoperability testing of the XML packaging software and use cases and requirements from various space data and operations groups, develop a set of registry/repository specifications that are extensible, addressing interfaces, data structures and information modeling.  This registry/repository should leverage the more widely based registry work such as ebXML and UDDI while supporting any special space-based operations registry/repository requirements.

- Transfer any XML tools and best practices developed for the XML Packaging and Registry/Repository tasks to the MOIMS Area Director for use in other CCSDS Working Groups

- Act as the responsible Working Group for any CCSDS Recommendations in the area of Information Understanding(Structures and Languages (formerly CCSDS Panel 2). This includes performing any CCSDS or ISO 5 year reviews of existing standards and monitoring any new activities by CCDS member agencies in this area.

### Schedule and Deliverables

Goals 1 and 2:XML Packaging Recommendations and Software

| Date | Milestone |
| --- | --- |
| 19 May 2003 | WG chartered and active. |
| 30 June 2003 | XFDU draft ‘proposed’ document (WB) With use cases/requirements available |
| November 2004 Complete | Submit CCSDS XFDU ‘Proposed Standard’ (RB) and Reference Implementation for CESG Review. |
| June 2006 | Generate first draft of XML Packaging Best Practices Green Book |
| May 2006 Complete | Generate CCSDS Proposed Standard (Redbook V2), Best Practices Green Book and two interoperable reference implementations |
| October 2006 | Generate CCSDS Recommended Standard and Best Practices Green Book based on Agency review comments and user feedback |
| June 2006 | White Papers on proposed enhancements for the XFDU packaging recommendations based on the planned Version 2 enhancements |
| June 2007 | XFDU V2 White Book‘ (WB) and proof –of-concept prototypes |
| 2007-2008 | Develop XFDU Version 2 Redbook and Bluebook( (or Pink Pages), update XFDU Greenbook and implement two interoperable implementations |

Goal 3:Registry and Repository Recommendations and Software

| Date | Milestone |
| --- | --- |
| April 2005 Complete | Joint FTF meeting with Systems Engineering, Information Architecture team to develop registry work plan in this area |
| June 2006 | White Papers on the Scope, Use Cases and Requirements for Registries and Repositories in the Space Information and Operations domains |
| 2006 -2008 | Develop Registry/Repository data structures, interfaces and procedure recommendations for the appropriate space operations and data domains. Develop XML Schema Registry prototypes that provides adequate services {e.g., schema versioning, schema validation, association of other xml artifacts such as style sheets) in addition to the registry/repository services of registration, query, subscription and lifecycle services. |

### Risk Management Strategy

#### Technical Risks

The Packaging Recommendation functionality has been split between two planned releases of the XFDU Packaging Recommendation to allow early prototyping of required capabilities. This should allow lessons learned in the prototyping to influence the design of the more complex capabilities

Also a wide variety of use cases and testing environments have been identified for the Interoperability Testbed for XFDUs:

- NASA PDS;

- NASA/EOSDIS Libraries;

- NASA SLE implementations;

- CNES SLE implementations;

- CNES Archive Ingest SIP development;

- ESA Data Distribution System

- ESA CAOS.

This range of environments should identify any efficiency or operability problems that must be solved either in the best practices document or by further implementations.In the area of Registries and Repositories, overlapping membership, frequent discussions and a minimum of one FTF meeting with the Information Architecture BOF/WG and  the SANA WG in the Systems Engineering area to avoid significant duplication of effort or significant divergence of concepts. It is recommended that only one WG be tasked with the development of specifications in the area of Registries and repositories.

#### Management Risks

Unavailability of resources could delay achievement of milestones. Fallback option would be to reschedule the milestones.

There may be a conflict for resources between the Registry/Repository activities and the XFDU V2 activities. Fallback would be to do the activities in sequence with the member agencies deciding on priority.

### Resources

Under separate cover