## Slide 1
Space Internetworking Services
Area Report
Tomaso de Cola (Area Director)
Rodney Grubbs (Area Deputy Director)
Notes: 1
1
1

## Slide 2
Working Group Status:
The DTN Working Group reviewed upcoming Agency missions to identify DTN capability requirements and timelines to serve as the basis for reevaluating and rescheduling current and draft DTN WG Work Items
  SIS-DTN Executive Summary (1/4)
Work Item | Mission: Need/Want | Date
BPv7 | DSN – W ISS – W LCRNS – N Moonlight – N | Now Now Now Now
BPSec (Blue Book + CCSDS BPSec Default Security Contexts + BPSec Interoperability Testing) | Moonlight - W DSN - W ESTRACK - W ISS – W | 2024 2024 2024 2024
Compressed Bundle Reporting | Lunar-related RFPs - N Earth Observation - W Moonlight - N Mars Relay Network - W | Orange - Fall 2023 2025 Orange - Fall 2023 IOC 2030+
DTN Multipoint Delivery: IMC URI & BPv7 protocol extensions | ISS-MTB - W Lunar Relay – N | Orange 12/2023
NetMgt ADMs (BPv7 Core ADMs) BPv7 CLA ADMs | Lunar-related RFPs | Cover Sheet/IETF External Dependency
New: Hooke Transmission Protocol | R&D - W | Orange – 12/2023
IETF IPN Revised Naming (URI) Scheme | Unknown | 5-year BPv7 review
NetMgt Interoperable Protocols | ISS - W Gateway – W | 2030+
Notes: From Spring 2018 Meetings:
SBSP: Proposed solution: If you want to encrypt a block that is the target of one or more integrity blocks, the confidentiality block must CONSUME the integrity blocks, incorporating them into the confidentiality block or concatenating them with the target block to be encrypted or ...) - Ed Birrane to draft text, Jeremy (DTN) and Scott (ION) to implement.
Fall 2018:
SBSP: add the ‘instantiate a new SA with these instructions’ block type

## Slide 3
  SIS-DTN Executive Summary (2/4)
Priority 1: BPv7 Blue Book – in Agency review, no action this meeting
  RID Resolution to be performed between review closure (6/6) and Fall meeting
Priority 2: BPsec (joint meeting w/ SEA-SEC):
  Normative Spec: Reviewed draft BPSec (Blue track)and addressed remaining concerns.
    Document is ready to enter the Agency Review pipeline – proposed resolution follows
  CCSDS BPSec Default Security Contexts – required for missions to be able to adopt BPSec
    This will be a (short) profile of RFC9173 (Default Security Contexts for Bundle Protocol Security) BPSec plus COSE (CBOR Object Signing and Encryption) (Internet Standard 9052)
  Interoperable Prototypes – call for Agency commitment due 5/31/2023
Priority 3: Compressed Bundle Reporting
  In-Progress Orange Book presented to WG by ESA
  Broad consensus that this capability is needed to support multiple missions
  Orange Book being pursued first to support requirements/RFP actions
  Likely candidate for Blue Book when schedule and resources permit (not now)
Priority 4: DTN Multi-Destination Delivery
  Multi-destination Naming Scheme (URI) and BPv7 Protocol Extension Block required to support Lunar Relay (and ISS for operational evaluation)
  Orange Book being pursued initially to support RFP generation
Priority 5: DTN Network Management Application Data Models (ADMs)
  BPv7 and BP Convergence Layer Adapters are initial targets
  Being developed in IETF – CCSDS will contribute to IETF effort/adopt via “cover sheet”

## Slide 4
  SIS-DTN Executive Summary (3/4)
Priority 6: Licklider Transmission Protocol reaffirmation
  DTN WG has prepared and initially reviewed a Technical Corrigendum for LTP
  Working Group will reaffirm LTP with the corrigendum and maintain its status as an active protocol
  The DTN Working Group is sensitive to impact on programs that are considering LTP and do not plan to retire it until a mature, stable replacement becomes the preferred choice of missions for future use
Priority 7: New topic – Hooke Transmission Protocol
  ESA/DLR findings show that the LTP protocol design is not ideally suited for FPGA implementation in support of (what are now) very high rate missions
  HTP is NOT an “LTPv2”
    Not backward compatible with LTP
    Not a profile of an IETF RFC
  ESA presented a high-rate design and concept paper derived, but distinct, from LTP
    ESA/DLR Demonstration of a (ground) prototype capable of ~30Gbps
    Working group will review between meeting cycles
    NASA/MSFC considering providing 2nd prototype – still TBD
    Orange book to be proposed as a new work item
  Optical link and video streaming provide highest priority use cases
Others: Not on know critical path for missions or infrastructure, beyond current planning horizon

## Slide 5
  SIS-DTN Executive Summary (4/4)
Interaction with other WGs:
  Meeting w/ SEA SEC to discuss bundle security protocol
    Consensus that BPSec Release Candidate 2 is ready for Agency Review
    Next steps – generation of default CCSDS BPSec Security Contexts and Interoperable Prototype Implementations
  Meeting with SEA SA to discuss DTN Stages
    Mission-informed priorities and need dates shape our work
    Will document DTN Stages in context of refactored WG Plan
Problems and Issues:
  Non-critical work items must be deferred in order to address mission needs (ref revisions to approved and draft projects)
  Some existing or previously-planned work items do not appear to be in DTN WG Scope – should be assigned to other Areas or WGs
  Need to expand SIS-DTN resource pool
    WG met for three days this week, started early and ended late each day, but could have used more time
    Pool of subject matter experts is shared with other WGs, so inter-plenary meetings remain critical to meeting mission-driven need dates
Fall Priorities:
  Two days: Finalize RID resolution on BPv7 and BPSec documents; review interoperability test results
  One day: Finalize Compressed Bundle Reporting Orange Book

## Slide 6
Resolutions agreed upon this meeting
  Submit BPSec for Agency Review
  Charter DTN Multi-Destination Orange Book work item
Further Resolutions anticipated in the next 6 months:
  Approve Compressed Bundle Status and DTN Multi-Destination Orange Books
Planning (only approved Projects):
  SIS-DTN Resolutions and Planning
Area and WG Name | CCSDS Ref Nr | Document Title | Status / Comments | Start and / or Target Publication Date
SIS-DTN | 734.5 | Bundle Security Protocol for CCSDS | Ready for Agency Review | Start date: 8/1/2020 End date: 7/30/2024
SIS-DTN | 734.4 | CCSDS Bundle Protocol Network Management | Immediate need for Application Data Models (ADMs): Cover sheet adoption of IETF RFC Defer Protocol Definition | Start Date: 12/18/17 End Date: 6/1/2024
SIS-DTN | 734.1 | LTP Update – 5 Year review | Corrigendum in WG review | Start date: 1/25/2021 End date: 11/19/2023
SIS-DTN | 734.2 | BP Update – 5 Year review | BPv7 in agency review | Start date: 8/1/2020 End date: 9/1/2023
SIS-DTN | 730.3 | CCSDS Bundle Protocol Network Management | Not currently on critical path for any missions | Start Date: 12/18/17 End Date: 2030
SIS-DTN / SEA-SEC |  | CCSDS BPSec Green Book | Not currently on critical path for any missions | Start Date: 9/1/2020 End Date: 2030
SIS-DTN |  | Compressed Bundle Status Reporting and Custody Signaling | Immediately needed or desired on all BPv7 missions | Start date: 1/1/2023 – End date: 10/2023

## Slide 7
  SIS-DTN Proposed Future Work Items (1/2)
Area and WG Name | CCSDS Ref Nr. | Document Title | Target Start / Publication Date | Resources Needed (total, Editor, Proto1, Proto2) |  |  |  | Comments Rationale What if not started?
SIS-DTN |  | DTN Reliable Multicast | 12/1/2023 – 12/31/2024 | 2023: 1.5 2024: 9.5 | 2023: 1.5 2024: 1.5 | 2023: 2.0 | 2024: 6.0 | For Gateway
SIS-DTN |  | DTN Multi-Destination Delivery | 6/1/2023 – 12/31/2023 | TBD | TBD |  |  | For ISS, Lunar Relay
SIS-DTN |  | First-Hop / Last-Hop Service (Application) | 3/1/2026 – 3/1/2028 | 2026: 4 2027: 12 2028: 6 | 2026: 4 2027: 4 2028: 2 | 2027: 4 2028: 2 | 2027: 4 2028: 2 | Work in concert w/ (or just support) CSS and/or SLS
SIS-DTN |  | Erasure Coding for LTP | 1/1/2025 – 7/1/2026 | 2024: 7.5 2025: 7.5 | 2024: 1.5 2025: 1.5 | 2024: 2 2025: 2 | 2024: 4 2025: 4 | Performance impact in deep space operations
SIS-DTN | CCSDS 734.0-G-2 | Rationale, Scenarios, and Requirements for DTN in Space (refresh) | 1/1/2023 – 6/30/2025 | 1.0 | 1.0 |  |  | Updates needed to track current CONOPS and CCSDS architecture.
SIS-DTN |  | Multi-Agency DTN Network Security | ??? |  |  |  |  | BPSec Addresses
SIS-DTN |  | SSI Cross-Support and Administration | 1/01/2019-5/20/2020 |  |  |  |  | 
SIS-DTN | 735.0-G-2 | Update Asynchronous Message Service Green Book | 1/01/2020- 1/01/2021 |  |  |  |  | Recharter AMS WG
Notes: 7
7
7

## Slide 8
  SIS-DTN Proposed Future Work Items (2/2)
Area and WG Name | CCSDS Ref Nr. | Document Title | Target Start / Publication Date | Resources Needed (total, Editor, Proto1, Proto2) |  |  |  | Comments Rationale What if not started?
SIS-DTN | 735.1-B-2 | Update Asynchronous Message Service Specification | 1/01/2020- 1/01/2022 |  |  |  |  | Recharter AMS WG
SIS-DTN |  | CCSDS Bundle Protocol Streaming Support Blue Book | 3/01/2025- 2/01/2027 |  |  |  |  | Protocol / service specification for CCSDS Bundle Streaming protocol.
Notes: 8
8
8