## Slide 1
Space Data Link Security (SDLS) WG
  Working Group Status: Active - Progress report:
  SDLS core protocol
    Blue Book (355.0) published – September 2015 : already several missions have selected SDLS for TC/TM/AOS links security
    Joint session with SLP WG
      Discussion on OID frames and SDLS (potential missing specification to avoid encryption of OID frames)
      Discussion on interaction of SDLS with USLP
    Green Book (350.5) :
      Review of the complete document. Discussion on last inputs to the document. Document now quasi-complete.
      Target: final editing and review by the WG June 2016. Transfer to the CCSDS editor for publication before September 2016. Publication tentatively by next meeting.
  SLS AREA REPORT
Notes: 1

## Slide 2
Space Data Link Security (SDLS) WG
  Working Group Status: Active - Progress report:
  SDLS extended procedures
    Finalization of Monitoring & Control, SA management and Key management services/procedures/PDU
    Discussion and decision on the communication service to be used for EP PDU transmission over the spacelink (joint session with SLP WG)
    Final decision on definition and parameters for baseline mode
    Discussion on validation and interoperability testing :
      Agreement on tests objectives, coverage & configurations
      2 prototypes currently being developed : ESA, NASA (3rd to be developed by CNES)
        Cloud based implementation. Interconnection of prototypes tested successfully.
    White book 90% complete. Target : final WB agreed by the WG at mid-May telecon. Red-1 to be issued before next meeting.
  SLS AREA REPORT
Notes: 2

## Slide 3
  SLS AREA REPORT
Space Data Link Security (SDLS) protocol (cont’d)
Problems and Issues:
None
status: | OK | CAUTION | PROBLEM
comment: | Good progress |  | 
Planning:
SDLS core protocol:
  Green Book completion : June 2016
  Submission to CCSDS editor : July 2016
  Publication : October 2016
SDLS extended procedures:
  White book – final : May 2016
  Red book 1 (including baseline mode): September 2016
  Agency review : November 2016
  Green book to be started at next meeting
Notes: 3

## Slide 4
SDLS WG Space Data Link Security
  SDLS core protocol
    Green Book (350.5) : Review of the complete document. Target: finalization of GB June 2016 aiming at a publication before fall meeting 2016.
  SDLS extended procedures
    Finalization of Monitoring & Control, SA management and Key management services/procedures/PDU
    Finalization of definition and parameters for baseline mode
    Discussion/decisions on interoperability testing :
      Tests objectives, coverage & configurations
      2 prototypes under development : ESA, NASA
        Interconnection of prototypes done using VM over cloud service
    White book 90% complete. Target : final WB agreed by the WG May 2016. Red-1 September 2016. Agency Review November 2016.
SLS Area want to thank NASA/GRC for the excellent accommodation and facilities.
  SLS AREA REPORT – SUMMARY