## Slide 1
Space Data Link Security
Working Group Report
Gilles Moury (WG Chair)
Howard Weiss (WG Deputy Chair)
Notes: 1
1
1

## Slide 2
Goals for this meeting cycle:
  Finalize SDLS Green Book for publication
  Finalize SDLS Extended Procedures red-1 book for agency review
Working Group Status:
  Complete review of the SDLS Core Protocol Green Book. All technical matters dealt with successfully. Minor editorial work still needed (e.g. references). Agreement of WG for issuing a resolution to publish
  Complete review of SDLS extended procedures red-1 book achieved. Document 95% complete. Agreement on all technical issues. Final editing and WG resolution for agency review anticipated before the end of the year.
  Interoperability testing of SDLS extended procedures: test plan reviewed and agreed, testing setup and progress discussed, interoperability testing over the cloud of the full stack  SDLS Core Protocol + Extended Procedures + TM/TC + SLE. Yellow book on interoperability testing over the cloud finalized  will be forwarded to CESG.
  Discussion of Physical Layer Security draft project: concept paper for a GB will be prepared for next meeting.
Problems and Issues:
  None
  SDLS WG Executive Summary
Notes: JAXA is interested, resources being identified. Possible issues getting resources allocated / schedule.

## Slide 3
Planning:
Interaction with other WGs
  Space Link Protocol WG : integration of SDLS in TM/TC/AOS/USLP protocols
  RF & Modulation : physical layer security
  Security WG : key management MB, threats to space missions, cryptographic algorithms BB, security architecture
Resolutions
  Resolution to publish SDLS Core Protocol Green Book
  Resolution to submit SDLS Extended Procedures red-1 book to agency review #1.
  SDLS Executive Summary
Area and WG name | CCSDS Ref Nr | Activity (RB, Pink, Draft. Update) | Document Title | Status | Start and / or Target Publication Date | Comments
SLS SDLS | 355.1 | BB | Space Data Link Security Extended Procedures | Red-1 completely reviewed and agreed. 95% complete. Final editing needed. WG resolution for requesting agency review #1 | Start date 17/11/2011 End date 15/10/2017 | WG resolution to submit red-1 to agency review #1
SLS SDLS | 350.5 | GB | Space Data Link Security - Summary of Concept & Rationale | Content complete and fully reviewed during meeting. Final minor editing needed. WG resolution to publish to be issued. | Start date 28/11/2008 End date 15/12/2016 | WG resolution to publish
Notes: JAXA is interested, resources being identified. Possible issues getting resources allocated / schedule.

## Slide 4
  SDLS WG Resource Issues for Approved Projects
None

## Slide 5
  SDLS WG Upcoming New Work Items
Draft project:
  Space Data Link Security Concept of Operation, Issue 2
  Could be started in the next 6 months once the SDLS GB Issue 1 is finalized/published
Notes: 5
5
5