## Open Actions
AI # | Action | Assignee | Due Date | Status | Notes | Change made
SMWG Spring 2011 Meeting, 16-20 May 2011
2011-0519-03 | Develop approach for integrating externally defined schemas that evolve independently of SCCS-SM | AC/JVP | Spring 2015 meeting
2011-0520-06 | State policy for schema maintenance regarding SANA and provide writeup of policy. Provide initial input by 13 May. | EB | 2015-01-13 |  | Originally Fall meeting 2011 then 21 Jan 14. Need this for SoS Blue book. Run by XML SIG Noted that this will likely need to be discussed within the context of XSG as part of the overall CCSDS schema management set of considerations. Smaller initial steps agreed to as initial steps to closing the action. Waiting for written version.
Noordwijkerhout 31 Mar - 3 Apr 2014
2014-0401-01 | Provide the key reporting metrics or statistical characterizations, with definitions that are reported for each Agency’s networks’ service accounting for the customer (as it relates to the Service Package/Service agreement and recommendations for other metrics reported out weekly/monthly, etc). | EB | 2015-03-21 |  | MG, JPC, MU and CC (for CNES) presented/discussed their agency's service accountability data at the London meeting. Erik will provide the DSN at a later date.Action closed for the others on 13-Nov-14.
2014-0402-05 | Service Package Request management component writeup | EB | 2015-02-10 |  | A presentation was completed on 8 May. Need to complete writeup
SMWG Telecon - 3 June 2014
2014-0603-02 | Provide write up on metadata for delta dor use case re: service package and service request | EB | 2015-03-21 |  | With regard to DDOR service and a mission using multiple agency TTC networks. Will reschedule at London Meeting. Original due date was 4-Nov-14
SMWG Telecon - 24 June 2014
2014-0624-01 | Propose namespace architecture for CSSA schemas within CCSDS namespace | JVP, AC | 2014-12-15 |  | Will be ready for a discussion in London. Original date 10-Nov-14
SMWG Telecon - 26 August 2014
2014-0826-03 | Talk with appropriate agency representatives and provide inputs with respect to radio frequency interference (RFI), data volume/data rate estimation, and cost estimate data inputs for consideration in the draft Planning Information recommendation | ALL | 2014-12-09 |  | Summary of events and parameters/data exchanged. Provide to CH so he can put it in the draft. Will discuss in London.
London - 10-14 November 2014
2014-1110-02 | Create a diagram to be included in the Simple Schedule introduction to clarify the context of the document (possibly by using the life-cycle diagram) | MG | 2014-12-09
2014-1110-03 | Look at the test report and provide any comments on mapping to SN or NEN items for EUMETSAT RID HH004. (Perform analysis relative to test report and as to abliity to map to proposed standard.) | JPC | 2014-12-09
2014-1110-06 | Update the diagram according to CNES RID JMS11 | MG | 2014-12-09
2014-1111-01 | Include in test report that we will not prototype the nesting of AdditionalParameter | MG,KT | 2014-12-09
2014-1111-02 | RE: RID ESA-ESA 11 Think through and come up with an answer. Consider if an optional parameter should be added to the Activity class to indicate the level of commitment to the activity. | CH | 2014-11-21 | CLOSED 19-Nov-14
2014-1111-03 | Look up the frequency for UHF and VHF for the SoS | MG | 2014-12-09
2014-1111-04 | Clarify the note to indicate the information bookmarking function in the case of the antenna free time in para 3.4.2.2. See NASA RID Antenna Freetime | MG | 2014-12-09
2014-1112-01 | Produce text re SANA policy that can be re-used for each CSS area blue book | EB, MdG | 2014-12-01 |  | Urgent
2014-1112-02 | Provide examples of recurrent requests for your agency | MG, CC, MU | 2015-01-13
2014-1113-01 | Produce a graphical model based on the green book planning request | EB | 2014-12-09
2014-1113-03 | Perform an analysis of the accountability data from each of the agencies | JR | 2015-03-21
2014-1113-04 | Do a proof of concept for 1) config profile out of service profiles 2) pare down TC/TM SLE-Plus profile (Bake-off) | JVP, AC | 2015-02-10
2014-1113-05 | Develop a standard header | CH | 2014-12-09 | CLOSED 18-Nov-14
2014-1114-01 | Develop the SANA registry considerations/policy | EB | 2015-01-13 |  | Define the namespace for the Simple Schedule
2014-1114-02 | Sort out the abstract request common type for the planning data format | EB, CH, JPC, JVP | 2015-02-10
2014-1114-03 | Define the remaining event definitions for the planning data format | All | 2015-01-13
2014-1114-04 | Check communition geometry events for the planning data format | All | 2015-01-13
2014-1114-05 | Update planning data format white book | CH | 2015-03-21
2014-1114-06 | Complete the service request component write-up | EB, JPC | 2015-03-21
2014-1114-07 | Flexibility and Constraints extensibility schema for the service request | JVP | 2015-03-21
2014-1114-08 | Service request vs planning request alignment | JPC, CH, JVP | 2015-03-21
2014-1114-10 | First draft (white book) of the Trajectory Prediction book | JR | 2015-03-21
2014-1114-11 | List of questions for the Generic File Transfer preliminary draft | CH | 2015-01-27
2014-1114-12 | First draft (white book) of the Event Sequence | PP, EB | 2015-03-21
2014-1114-13 | Strawman on service package result structuring | JPC, JVP | 2015-03-21
SMWG Telecon - 9 December 2014
2014-1209-1 | Double check the SOS RID disposition report prior to release to RID submitters | EB | 2014-12-15
2014-1209-2 | Process all instances of “network” and see where change to “Provider CSSS” does or does not make sense | CH |  |  | To be consistent with CSA ADD
2014-1209-3 | Update the revised the antenna free-time diagram re “network” term as determined by C. Haddow | MG
2014-1209-4 | Wordsmith the text for the antenna free time updates from M. Gnat | CH
2014-1209-5 | Provide comments/analysis on each info entity vs. the proposed common request header | EB | 2015-01-13 |  | Basic idea is good

## All Actions
AI # | Action | Assignee | Due Date | Status | Notes
SMWG Actions Items, Colorado Springs Meetings, 15 -- 19 January 2007
COS-01 | Provide parameters necessary for configuring of ranging service (for ESA) | KC | 2007-01-19 | Closed administratively | To be subsumed under an broader action for developing a survey for inputs from each agency
COS-02 | Update forward subcarrier frequency parameter to state a set of discrete options in SA, etc. | JP/FB | 2007-12-15 | CLOSED | Transferred to NGSM work items spreadsheet
COS-03 | Identify general time for shadow tracking opportunity for MEX | KC/.AC | 2007-04-20 | Closed administratvely | Prototype plans to be discussed at October meetings
COS-04 | Identify likely supported operations for prototype interoperations | YN | 2007-02-02 | Closed
C0S-05 | Provide complete details on CSSXP prototype limitations | PP | 2007-02-15 | Closed
COS-06 | Revise trajectory analysis with approach for folding ANT and AAT as a single operation | AC or JP | TBD | Closed | Pending discussion at March 2008 meetings
COS-07 | Provide use case information from JSC operations perspective | MP | 2007-12-30 | CLOSED | Overcome by events
COS-08 | Send JAXA represnetatives PQ test plan for original JPL/ESA prototype interoperations | EB | 2007-01-25 | Closed
COS-09 | Compute RID close out times and schedule times for each assignee | EB | 2007-01-19 | Closed | Results captured in RID Tracking Spreadsheet
COS-10 | Update the WG Charter | EB | 2007-10-30 | Closed
COS-11 | Send JP information on tune-in leg parameters | KC | TBD | Closed | Pending discussion at October meetings
SMWG Actions Items, Greenbelt Meetings 07, 08 June 2007
GB-01 | Determine Availabiltiy of JPL prototype Red-1 beyond end of 2007 (info to ESA) | EB | TBD | CLOSED | Overcome by events
GB-02 | State semantics of antennaPreferennece parameter in handover situations. | JP |  | Closed
GB-03 | Provide bullet points on handover concept and other concepts from conceptual analyses done so far. | JP (EB for EVT Seq) | 2007-11-01 | CLOSED | Event Sequence part transferred to NGSM work items spreadsheet
GB-04 | Need to defined what event sequence in conformance with applicable carrier profile means. (CSPC-22) | EB | 2007-11-01 | Closed | Pending check of Red-2
GB-05 | Determine what kind of signal threshold parameter would be stated for combined/dynamic polarization switching? | JM (CNES) | 15-Jul-07 (?) | Closed | Do not add any threshold values; see if any RIDs are produced in review of Red-2
GB-06 | Provide a list of scenarios for the revised green book to HK (e.g., UM "controlled" handovers vs. CM "initiated" handovers…also reserving antenna time followed by resplace service packages with sequence information) | EB | 2007-12-01 | CLOSED | Transferred to NGSM work items spreadsheet
GB-07 | Updated figure C-1 (Red book) to indicate message set; ie it is not a CSP-I message. | EB | 2008-03-14 | CLOSED | Transferred to NGSM work items spreadsheet (for Green Book)
GB-08 | Provide defintion of service package start time | JP | 2007-06-30 | Closed
GB-09 | Confirm ESA's position as to whether simple "yes" or "no" response on PSP is sufficient | AC | 30-Jun-07 (?) | Closed | Answer is simple yes or no should suffice
GB-10 | Put approppriate words in PSP operation description to include provisional scheduling; also put appropriate parameter in service agreement | JP |  | Closed | Pending discussions at October meeting
GB-11 | Check to see if its possible to configure CSSXP to skip production of ACK returns to help support message exchange protocol testing. | TB | 2007-06-30 | CLOSED | Overcome by events
GB-12 | Provide details on security approach for JAXA representatives (ie., e-mail subject line, public key,etc) and estimated availability date. | EB/TB | 2007-06-20 | Closed
GB-13 | Send e-mail to JAXA representatives containing sample xml messages. | EB | 2007-06-20 | Closed
GB-14 | Review JAXA ICD Parameters and SA Parameter documents and provide inputs. | EB | 2007-11-01 | Closed
GB-15 | Examine simplified diagrams to see if they can be formally "UML-ified" | JP | 2007-08-01 | Closed
GB-16 | Add legal CENTER_NAME values for OEM formatted trajectory predictions in the Service Agreement section. | FB | 2007-12-30 | CLOSED | Transferred to NGSM work items spreadsheet
GB-17 | Revise service package definition to allow multiple trajectory references (invocation, return stereotypes) | JP | 2007-07-15 | Closed
SMWG Actions Items, Telecon, Augst 2007
AGT-01 | Confirmation of "may" type requirement on CM vs. "shall" when considering cancellation of SP still needing full elaboration at expiration of minimum service definition lead time. State table to be updated accordingly | AC | 2007-10-01 | Closed
AGT-02 | Need to revise CM requirement CSPC-10 to clearly state that transfer services are not scheduled but that a spacelink aspects of the service package are scheduled. | EB | 2007-10-01 | Closed
AGT-03 | Revision of CM requirements with respect for CM determining aperture sufficiency if required and preferred antenna references are being utilized in the service package invocation (CSP operation) | EB/SZ | 2007-10-30 | Closed
AGT-04 | Revision of CM requirement CSPC-25 such that CM may construct a resultant service package that allows for service request satisfaction via multiple sequential spacelink sessions (i.e. handover situations) solely on the basis of whether or not the handover is allowed as opposed to absolutely requiring CM to do so only if satisfaction of the service request cannot be accomplished via a single continuous spacelink session. The rationale is to avoid precluding adoption of the minimally compliant CSP operation due to internal CM policy considerations (e.g., need for internal load-balancing of network resource utilization, etc.) | EB | 2007-10-01 | Closed
SMWG Actions Items, October 2007
H-01 | Present proposed parameters, approach for tune-in parameters (sweep rate, range, etc) | Michel Dugast | 2007-10-05 | Closed
H-02 | Need to revise reference framework diagram consistent with new event sequence approach, mapping between SLPS and tranfser profiles | AC | 2007-11-30 | Closed
H-03 | Update compliance matrix to indicate new operations | EB | 2007-10-30 | Closed
H-04 | Provide tutorial version of state table diagram for concept book | AC | 2007-11-30 | Closed
H-05 | Provide updated concept material for multi-center trajectory references | EB | 2007-11-30 | CLOSED
H-06 | Supply proper set of modulation options for section 5 | FB | 2007-11-15 | Closed
H-07 | Coordinate JPL DSN adoption of ALOS,including assitance for JAXA radio frequncy license, etc. | EB | ASAP | Closed
SMWG Action Items, March 2008
CC-01 | Check need for RID on document exchange protocol re "Ambiguos Retrns" (See CWE list) | JP | 2008-05-30 | Closed
CC-02 | Re-issue Trajectory Predicition handling paper | JP | 2008-04-20 | Closed
CC-03 | Update refactoring proposal to include at least one example of a service such as telemetry | NC | 2008-10-07 | Closed | (Pending further work…with regard to initial exercises for producing core book in relation to draft framework).
CC-04 | Provide a common briefing that can be used in support agency reviews of Red-2 | EB | 2008-03-24 | Closed
CC-05 | Perform editorial clean-up of Concept Book and post for support of agency reviews of Red-2 | EB | 2008-03-24 | Closed
SMWG Action Items, October 2008
BE-01 | Update timing relationship diagram to show relative event times in proper relations ship (to orange line) | SG | 2008-11-10 | Closed
BE-02 | Provide some concept metrial on event sequences, from a S/C oriented perspective (to A. Crowson) | EB | 2009-05-15 | Closed
BE-03 | Send DDOR WG example of service agreement, configuration profile, service package | EB | 2009-04-22 | Closed
BE-04 | Take a look at Red-3 and determine the set of test points (ascpects of Book that have a bearing on test plan -- ie, [perform operation] validations will likely not be in test plan) | AC | 2008-11-28 | Closed (by EB)
BE-05 | Determine if new WG is to be established for re-facotored SM approach | EB | 2009-01-02 | Closed
BE-06 | Examine XML Schema production from UML tools capabilities and report to SMWG | AC | 2014-10-01 | CLOSED 3-Apr-14 | Orignally 15-Nov-09. Initial focus will be on Info Entity schemas
BE-07 | Produces one or two UML diagrams from Red-3 in MagicDraw and release to WG | AC, PP | 2009-07-15 | Closed | Sept 2009 draft refactored core book
BE-08 | Arrange Telecon for RID Dispostion ~18 Nov 08 | EB | 2009-11-01 | Closed
SMWG Action Items, April 2009
CS-01 | Arrange montly telecons | EB | 2009-04-26 | Closed
SMWG Telecon, June 2009
040609-01 | Produce a diagram outlining the different enterprise models and implications thereof for service management -- for next telecon. | EB | 2009-06-30 | Closed
SMWG Telecon, July 2009
010709-01 | Clean-up Annex D of the Concept Book with proper figure references to the formal recommendation and removal of state machine information, | AC | 2009-07-10 | Closed
010709-02 | Check for hand-over material for concept book | JP | 2009-07-20 | Closed | Contratry to recollections, write-up/material is not immediately available
010709-03 | Provide responses to questions embedded as comments in latest concept book no later than 20 July 2009 (earlier if possible) | JP, EB | 2009-07-20 | Closed
010709-04 | Provide complete draft of test report for WG review. | EB | 2009-07-08 | Closed
SMWG Telecon, August 2009
AI # | Action | Assignee | Due Date
050809-01 | Double check draft test report findings (for omissions, errors, etc.) | AC | 2009-08-12 | Closed
050809-02 | Post copy of CESG approval version of service management recommendation for SMWG | EB | 2009-08-06 | Closed
050809-03 | Provide response re comment AC5 in draft concept book | JP | 2009-08-12 | Closed | Double check AC 5
050809-04 | Revise sections 7.3.1.1 + 7.3.1.3 in draft concept book | AC | 2009-08-12 | Closed
050809-05 | Provide response re comment AC33 in draft concept book |  |  | Closed
SMWG Telecon, October 2009
051009-01 | Review JVP's technical note monitor data naming | ALL | 2009-10-26 | Closed
SMWG Technical Meetings, 26 -- 30 October 2009
301009-01 | Perform analysis of CSTS Framework strucuturing, book approach etc. | JP | 2010-02-02 | Closed | New due date of 9 April 2010
030109-02 | Develop scope and rationale sections of draft next generation SM white paper | EB | 2010-02-18 | Closed | See email of 05 March 2010
0301009-03 | Identify types of extensibility points ofr NG WM White paper | CH/AC | 2010-03-17 | CLOSED
0301009-04 | Determine if specification can be developed inside formal modelling tool (M.Draw ) | AC | Spring 2012 meeting | CLOSED 16-Apr-12 | Originally 10-Feb-10. OBE
0301009-05 | Complete trial core book production | AC | on hold | CLOSED 16-Apr-12 | Originally 3-Mar-10 On hold pending further consideration. OBE
0301009-06 | Perform analysis re suitability/check re current managed services against trial core book | CH/AC | 2010-09-30 | CLOSED in London 2010 | Originally 12-May-10
0301009-07 | Perform identification analysis re managemed parameter for MD-CSTS | JP | 2010-08-06 | CLOSED 4 Aug 2010 | CLOSED 4 Aug 2010
0301009-08 | Perform identification analysis re managemed parameter for TD-CSTS | JP | 2010-08-06 | CLOSED 4 Aug 2010 | CLOSED 4 Aug 2010
0301009-09 | Perform identification analysis re managed parameters for PN (CCSDS) Ranging (for Spacelink) (first PN book) | EB/MD | Fall meeting | CLOSED 4 Nov 2011 | Originally 16-Apr-10 MD part is done
0301009-10 | Develop service specific book production guidelines= | CH/AC | on hold | CLOSED 16-Apr-12 | Originally 30-Apr-10. OBE
0301009-11 | Perform analyis re extracing document exchange as its own entity | SG/NC | 2010-04-30 | Closed
SMWG Telecon, March 2010
032210-01 | Determine if there are sections of the draft white paper re technical approach that could be worked in parallel and if so, request assitance form other members of WG | AC | 2010-04-05 | Closed
SMWG Technical Meetings, 03 -- 07 May 2010
030510-01 | Contact Z.K. of DLR to see what is meant by event driven SOE -- please provide some exampless | SG | 2010-06-30 | CLOSED in London 2010 | No information available
030510-02 | Generate a list/solicitation vehicle re what various agencies need for Next Generation SM (e.g., "query all') | JP | 2010-06-30 | CLOSED | email of 30 June 2010
030510-03 | Check current status of Selene parameters in CSSXP and report to JAXA representatives | EB | 2010-06-15 | CLOSED
030510-04 | Provide a copy of JAXA prsentation to JPL reprsentatives | T. ASAMA | 2010-05-07 | Closed
030710-01 | Revise Concept Book to included updated figure 2-3 per concept book review conclusion email of 07 May 2010 and produce "clean" copy with only comments for secretariat | AC | 2010-05-31 | Closed | Emailed to Secretariat on 20-May-10
030710-02 | Update the next generation concept paper and circulate | EB | 2010-07-07 | CLOSED | email of 28 June 2010
030710-03 | Clean up prototype test report and release to sceretariat | EB | 2010-09-01 | CLOSED 31 August | Originally 15-Jun-10 -- transferred to 2010-0831-01
030710-04 | Review DDOR "Implementing Arrangement" and "Service Request" and provide feed back to DDOR + SM WGs re harmonization | EB | 2011-10-06 | CLOSED | Originally 30-Jul-10
030710-05 | Produce technical note describing revised monitored data naming scheme | JP | 2010-10-01 | CLOSED 2010-10-28 | Originally 31-Jul-10
SMWG Telecon, 29 June 2010
2010-0629-001 | Follow-up with NAV WG Chair (D. Berry) as to the definition of “validated” re radiometric service | EB | 2010-06-30 | CLOSED | email of 30 June 2010
2010-0629-002a | To the extent possible, supply descriptions of various agency approaches in relation to arranging multiple or a series of related service packages for member agencies | All (in general) | 2010-08-23 | CLOSED 31 August 10 | Originally 26-Jul-10. SG - DLR does not do this.
2010-0629-002b | Supply description of DSN approach to arranging multiple or a series of related service packages | EB | Spring 2011 meeting | CLOSED (OBE) | Originally 26-Jul-10.
2010-0629-002c | Supply description of NEN approach to arranging multiple or a series of related service packages, e.g., "generic scheduling" | JP | 2010-07-26 | CLOSED | email of 7/28/10
2010-0629-002d | Supply description of ESTRACK approach to arranging multiple or a series of related service packages, e.g., "standing orders" | AC | Spring 2011 meeting | CLOSED (OBE) | Originally 26-Jul-10. Intermediate report made, will follow up with examples.
2010-0629-003 | Clean-up the poll material based inputs, and considering delivery to IOAG | JP | 2010-08-20 | CLOSED 6 August 10 | Original due 7/26/10 email of 2010-08-06
2010-0629-004 | Determine approach for soliciting inputs re NG SM from IOAG | EB | 2010-07-26 | CLOSED
SMWG Telecon, 31 August 2010
2010-0831-01 | Clean up prototype test report and release to JAXA or secretariat, depending on JAXA response (see 2010-0831-02) | EB | 2010-10-15 | CLOSED in London 2010 | Originally 15-Jun-10
2010-0831-02 | Determine if JAXA has the time and respirces to extend the prototype test report | JAXA | 2010-09-30 | CLOSED in London 2010 | JAXA will do it
SMWG Telecon, 5 October 2010
2010-1005-01 | Send email to JAXA asking if they have time and resources to extend the prototype test report | EB | 2010-10-11 | CLOSED 2010-10-25
SMWG London, October 25-29 2010
2010-1026-01 | JAXA will update prototype test report | TA | 2011-12-01 | CLOSED 16-Apr-12 | This report will apply to new testing. Originally due 28-Feb-11. Test report sent to JPL on week of 9-Apr-12
2010-1026-02 | Send a cleaned-up copy of prototype test report to JAXA with instructions for updating it | EB | 2011-10-03 | CLOSED | Originally 20-Nov-2010 | OBE
2010-1026-03 | Review JAXA spreadsheet of discrepancies in SCCS-SM and schema files | JP | 2010-11-20 | CLOSED 18-Nov-2010 | Email to T. Asama with recommended changes to Blue Book and schemas
2010-1029-01 | Develop next stage of resource class diagram and relationships for refactoring | AC | 2010-12-01 | CLOSED 15-Dec-2010
2010-1029-02 | Send overview class diagram to AC | EB | 2010-10-29 | CLOSED 2010-10-29
2010-1029-03 | Distribute concept paper to SMWG | EB | 2011-10-03 | CLOSED | Originally 15-Nov-2010
2010-1029-04 | Arrange Telecon/Webex for Dec 7 | EB | 2010-12-01 | CLOSED 2-Dec-2010
SMWG Telecon, 15 December 2010
2010-1215-01 | Provide a class diagram with component relationships (updated from London version) | EB | 2011-01-10 | CLOSED 22-Dec-10
SMWG Telecon, 1 February 2011
2011-0201-01 | Complete existing test report to reflect Blue-1 validation | EB | 2011-04-15 | CLOSED. Action to be completed as part of 2010-1026-02 | Originally 15-Mar-2011
SMWG Telecon, 15 March 2011
2011-0315-01 | Update description of figure 3-1 in Concept Book to explain scheduledServiceInstance offsets; circulate to SMWG | AC | 2011-03-17 | CLOSED 16 March 2010
SMWG Telecon, 11 April 2011
2011-0411-01 | Distribute concept paper to CESG following review at Spring meeting | EB | on hold | CLOSED 16-Apr-12 | Charter will be distributed to CESG
2011-0411-02 | Identify the logical extension points for adding D-DOR and the current CCSDS PN Ranging using the B-2 formal model elements | EB | 2011-05-06 | CLOSED (see 2011-0520-03)
SMWG Spring 2011 Meeting, 16-20 May 2011
2011-0519-01 | Check if CSSXP can use the updated schema for prototype interactions with JAXA | EB | 2011-06-07 | CLOSED 6/21/11 | Yes, will use V1.1.0 schema
2011-0519-02 | Update schema files with "V1.1.0" and "R1.1" | JP | 2011-06-01 | CLOSED 20 May 2011
2011-0519-03 | Develop approach for integrating externally defined schemas that evolve independently of SCCS-SM | AC/JP | Spring 2015 meeting
2011-0520-01 | Provide categories of activities for the SM lifecycle process | EB | 2011-06-20 | CLOSED 15 June 2011
2011-0520-02 | Provide inputs to E. Barkley on SM lifecycle processes for member Agency networks | WG members | 2011-08-15 | CLOSED 2011-10-04 | Date moved up from 9/1/11
2011-0520-03 | Refactor configuration profiles and service agreements (look at white book), with first emphasis on adding tracking services: present results | AC, JP | Fall 2011 meeting | CLOSED 2011-10-04
2011-0520-04 | MAL - SMWG doc exchange protocol analysis & report | AC, CH | Fall 2011 meeting | CLOSED 2011-10-04
2011-0520-05 | Upload XML schemas to SANA | JP | on hold pending resolution with NavWG | CLOSED 15 Oct 13 OBE | Originally Fall meeting 2011
2011-0520-06 | State policy for schema maintenance regarding SANA and provide writeup of policy. Provide initial input by 13 May. | EB | 2015-01-13 |  | Originally Fall meeting 2011 then 21 Jan 14. Need this for SoS Blue book. Run by XML SIG Noted that this will likely need to be discussed within the context of XSG as part of the overall CCSDS schema management set of considerations. Smaller initial steps agreed to as initial steps to closing the action. Waiting for written version.
SMWG Telecon, 21 June 2011
2011-0621-01 | Update categories of activities for the SM lifecycle process | EB | 2011-06-24 | CLOSED 7/1/2011
2011-0621-02 | Schedule next telecon (target - early to mid-August) | EB | 2011-06-24 | CLOSED 6/27/2011
SMWG Telecon, 26 Sept. 2011
2011-0926-01 | Coordinate with SM&C to discuss MAL-Doc Exchange Protocol | CH | 2011-10-01 | CLOSED
2011-0926-02 | Coordinate with NavWG to discuss schema issues | EB | 2011-10-01 | CLOSED
SMWG Telecon, 12 Oct. 2011
2011-1012-01 | Add discussion of DDOR to Boulder agenda (part of refactoring/ranging discussion) | JP |  | CLOSED
SMWG Boulder, 31 Oct - 5 Nov 2011
2011-1031-01 | JPL completes review of JAXA test report | EB | 2012-07-03 | CLOSED 2-Jul-12 | Depends on JAXA producing report by 1 Dec 2011 (see AI 2010-1026-01)
2011-1103-01 | Assess the current version of the CCSDS Catalog/Service Agreement book with respect to their Agencies' ground stations and services. Send results the HK. | NC, TA, CH, EB, MG | Spring 2012 Meeting | CLOSED 16-Apr-12 | Originally 01 Mar 2012; HK suggests focusing on concept if pressed for time. OBE
2011-1103-2 | Compare the current version of the SA book parameters with Blue-1 SA parameters | WG | 2012-04-18 | CLOSED 18-Apr-12 | Originally 01 Mar 2012
2011-1103-3 | Comment on the breakdown of Service Agreement templates. Send results to HK. | NC, TA, CH, EB, MG | Spring 2012 Meeting | CLOSED 16-Apr-12 | Originally 01 Mar 2012. OBE
2011-1103-4 | Check pcmpskpm error found by JAXA prototyping | JP | 2011-12-01 | 2011-12-15 | email "pcmpskpm element in SM schema", from J Pietras to T Asama
2011-1103-5 | How does ESTRACK disseminate the schedules to the missions? | CH | 2011-12-01 | CLOSED 16 Nov 2011
2011-1103-6 | Discuss NavWG event file work | EB | 2012-01-23 | CLOSED 23-Jan-12 | Email to SMWG
2011-1104-1 | Update charter with new level of effort estimates | EB | 2012-05-29 | CLOSED | Originally 18 Nov 2011 Will be addressd as part of the Project plans once the project has been created
2011-1104-2 | 1st draft description of management constructs elements | JP | 2011-12-15 | CLOSED 5 Dec 2011
2011-1104-3 | White book of framework elements, including candidate extension points. Update - this will now be material for the Green Book. | AC | 2012-10-15 | CLOSED 18-Oct-12 | Originally 15 Mar 2012; Per 15 Mar telecon, agreed to focus on extension mechanism. Part of Green Book production schedule
2011-1104-4 | Determine use of Teamwork server and/or alternate versioning scheme for MagicDraw model | EB, PS | 2012-03-30 | CLOSED. | Originally due 15-Jan-12. MDZIP files will be posted to CWE.
2011-1104-5 | Normalize existing model elements | AC, PP | 2012-02-29 | UML model brought into compliance with Green Book as of 29 Feb. | Originally 15-Dec-2011
2011-1104-6 | Establish biweekly WebEx schedule (tentatively Tuesdays) | EB | 2011-11-15 | CLOSED
2011-1104-7 | Develop UML profile for refactoring | PP | 2012-04-15 | CLOSED. | Originally 15 Mar 2012; Will be a continuing process that AC and PP will control.
2011-1104-8 | Develop preliminary assessment of value of different phases of lifecycle and associated information | EB | 2011-11-14 | CLOSED
SMWG Telecon, 15 Nov 2011
2011-1115-01 | Think about what a Blue Book for an information entity would/should contain | WG members | 2011-12-06 | CLOSED 15 Dec 2011 | Not addressed at 6 Dec 2011 telecon
SMWG Telecon, 19 Jan 2012
2012-0119-1 | Follow up on pcmpskpm email with T. Asama | JP | 2012-01-19 | CLOSED 19-Jan-12 | email sent to T. Asama
2012-0119-2 | Document perceived issue with mutual RFI among spacecraft across multiple (interAgency) Complexes (example: X-band hogs) | AC | 2012-04-15 | CLOSED | Originally 31-Jan-12
2012-0119-3 | Update workplan Gantt chart | EB | 2012-03-30 | CLOSED 28-Mar-12 | Originally 10-Feb-12
2012-0119-4 | Provide mindmap of deliverables | EB | 2012-01-31 | CLOSED 30-Jan-12
SMWG Telecon, 31 Jan 2012
2012-0131-1 | Get schedule information from D. Berry for the NavWG Event File work | EB | 2012-02-03 | CLOSED 13-Feb-12 | email from D. Berry describes NavWG plans for working on Event File
SMWG Telecon, 29 Feb 2012
2012-0229-1 | Post IOAG responses to CWE | JP | 2012-02-29 | Closed
2012-0229-2 | Email overdue AIs to membership | JP | 2012-03-01 | Closed | Needs to be done again; repeat as needed
2012-0229-3 | Post UML model to CWE | JP, PP | 2012-03-05 | Closed
SMWG Telecon, 15 Mar 2012
2012-0315-1 | Contact NAVWG Chair to coordinate joint session at Spring meetings | EB | 2012-03-16 | CLOSED | SMWG invited to sit in on session dealing with Events
2012-0315-1 | Contact JAXA representatives about B-1 prototype test report | EB | 2012-03-16 | CLOSED | JAXA still intends to produce the report
SMWG - Darmstadt, 16-19 April 2012
2012-0418-01 | Collect and submit Agency documents on Network Unused Resource Availability, Visibility/Events, and Schedule formats and explanation | WG members | 2012-05-11 | CLOSED 15-May-12 | Originally 2-May-12
2012-0419-01 | Look at functional resource definitions, whether they are consistent with NGSM concepts | WG members | 2012-05-02 | CLOSED 23-Apr-12
2012-0419-02 | Participate in CSTSWG telecon | WG members | 2012-05-08 | CLOSED
2012-0419-03 | Put folder on CWE for AI #2012-0418-01 inputs | JP | 2012-04-23 | CLOSED 23-Apr-12
2012-0419-04 | Check on CWE access for new members | EB | 2012-05-29 | CLOSED 15-May-12 | Message sent to Secretariat, reminder sent on 2-May-12
2012-0419-05 | Develop framework prioritization options | EB | 2012-08-31 | CLOSED 1-Oct-12 | Orignally 23-April-12. Eric will put out email listing options proposed so far.
2012-0419-06 | Develop Concept overview (section 2) of GB | AC | 2012-07-31 | CLOSED 27-Jun-12 | Originally 18-May-12
2012-0419-07 | Elaborate Lifecyle and Functional resource model sections of 3 | JP | 2012-05-18 | CLOSED 30-May-12
2012-0419-08 | Develop Enterprise Model section of 3 | PP | 2012-09-01 | CLOSED 20-Sept-12 | Originally 18-May-12
2012-0419-09 | First cut visibility section | JP | 2012-06-30 | CLOSED 6-Jun-12 | Originally 22-May-12
2012-0419-10 | Produce Roadmap section of the Green Book | EB | 2012-09-15 | CLOSED 18-Oct-12 | Originally 1-Jun-12. Now part of Green Book production schedule
SMWG Telecon - 2 May 2012
2012-0502-01 | Review use cases for functional resource IDs (instance combinations) | JP | 2012-08-31 | CLOSED 27-Aug-12 | Originally 25-May-12
SMWG Telecon - 19 June 2012
2012-0619-01 | Develop characteristics of events from agency inputs | CH | 2012-12-15 | CLOSED 19-DEC-12 | Originally 18-Jul-12. Emphasis will shift to categorizing classes of events. Awaiting WG review responses
SMWG Telecon - 27 June 2012
2012-0627-01 | Provide Hypothetical Plan section of Concept Green Book (amended on 2 August telecon to include trimming of all Info Entity descriptions) | EB | 2012-10-15 | CLOSED 10/1 | Originally 30 July-12
SMWG Telecon - 18 July 2012
2012-0718-01 | Reply to JPL comments on test report | TA | 2012-08-17 | CLOSED 22-Aug-12 | No response from JAXA. Comments assumed to be accepted and report will be recorded as such.
2012-0718-02 | Send risk to Erik about backward compatibility | JP | 2012-07-20 | CLOSED 20-Jul-12
2012-0718-03 | Update charter based on comments | EB | 2012-07-24 | CLOSED 26-Jul-12
2012-0718-04 | Check with Secretariat about maintaining SMWG archive | JP | 2012-07-20 | CLOSED 20-Jul-12
SMWG Telecon - 5 September 2012
2012-0905-01 | Minor tweaks to JAXA test report, send to Secretariat | EB |  | CLOSED 31Oct 13 | See 2012-1205-01. Received report from JAXA.
Cleveland 15-19 2012
2012-1015-01 | Generate FR type examples from classes in FR section | MG | pending | CLOSED 13 Dec 12 | Originally 15-Nov-12
2012-1016-01 | Trace IOAG SC services through the Extended FR Type diagram | JP | On hold pending feedback on definition of Forward and Return File, Validated Data Radiometric, and Delta DOR services | CLOSED | Originally 15-Nov-12. Review by W. Hell?
2012-1017-01 | Final version of the test report | TA | 2012-10-23 | CLOSED 23-Oct-12 | email to EB
2012-1017-02 | Evaluate alternatives to CSTS OID for FRs | EB | 2012-10-26 | CLOSED 9-Nov-12
2012-1018-01 | Produce WG schedule Gantt chart from Mindmap | EB | 2012-11-07 | CLOSED 1-Nov-12
2012-1018-02 | Review Characteristics of Events tech note and give comments to Colin | All WG members | 2013-06-20 | CLOSED 23-Jul-13 | Originally 15-Nov-12
SMWG Telecon - 5 December 2012
2012-1205-01 | Provide updated Prototype Test Report to EB | TA | 2013-05-01 | CLOSED 1 Oct 13
SMWG Telecon - 13 December 2012
2012-1213-01 | Generate FR type examples for the various TM sync and channel coding options | MG | 2013-01-31 |  | Originally due 17-Jan-13 Email of 30-Jan-13
SMWG Telecon - 17 January 2013
2013-0117-01 | Contact NavWG chair about addressing schema issues at Spring meeting | EB | 2013-01-18 | CLOSED | Email sent on 17 Jan 13
2013-0117-02 | Review the Information Entity descriptions in the Concept Green Book | All CSSMWG members | 2013-01-31 | CLOSED
Bordeaux 14-18 April 2013
2013-0415-01 | Update Enterprise model to reflect changes discussed during review (see meeting summary) | PP | 2013-06-07 | CLOSED 23-Jul-13 | Originally 1-Jun-13
2013-0415-02 | Add Event Sequence into Info Entities | JP | 2013-06-01 | CLOSED 29-May-13 | Included in ESCCS-SM Green Book draft of 29 May 2013
2013-0415-03 | Define frequency bands | MG, CC | 2013-06-20 | CLOSED 20-Jun-13 | Originally 7-May-13
2013-0415-04 | Does the schedule need a unique schedule identifier? | CC | 2013-06-20 | CLOSED 20-Jun-13 | Originally 7-May-13 It is not necessary
2013-0415-05 | Provide examples of use of additional parameters | MG | 2013-06-20 | CLOSED June 13 | Originally 7-May-13
2013-0415-06 | Produce draft model of extensibility for configuration profiles | AC | 2013-10-31 | CLOSED 31Oct 13 | Originally 1-Jun-13
2013-0415-07 | Clean up profile definition extensibility diagram | EB | 2013-05-07 | CLOSED 6 May
2013-0415-08 | Produce description of extensibility approach | JP | 2013-05-14 | CLOSED 29-May-13 | Included in ESCCS-SM Green Book draft of 29 May 2013
2013-0415-09 | Overlay new functional group concept over FR types | JP | 2013-05-07 | CLOSED 6-May-13
2013-0415-10 | Produce draft outline of Service Package Request/Service Package book | JP | 2013-10-28 | CLOSED 31Oct 13
2013-0415-11 | Produce outline of Planning Information book | CH | 2013-10-15 | CLOSED 14 Oct 13 | Originally 1 Aug 13
2013-0415-12 | produce draft outline of SA/Config Profile book | JP | 2013-10-31 | CLOSED 31Oct 13 | Originally 13-Aug-13
2013-0415-13 | Produce draft outline of trajectory prediction book | EB | 2014-11-01 | CLOSED 3-Apr-14 | Originally 17-Sept-13. Have by 2014 Fall meeting. OBE
2013-0415-14 | Produce draft outline of event sequence book | PP/EB | 2014-11-04 | CLOSED 3-NOV-14 | Originally 17-Sept-13.
2013-0415-15 | Review charter for updates and revise charter as needed | EB | 2013-06-04 | CLOSED 3-Jun-13
2013-0415-16 | Update Simple Schedule schema as Annex E | JP | 2013-06-07 | CLOSED 22 April
CSSMWG Telecon 7 May 2013
2013-0507-01 | Develop draft material regarding 3-way support in Enterprise model | PP | 2013-06-01 | CLOSED 20-Jun-13
2013-0507-02 | Explore turning FR Technote into a Yellow Book | JP | 2013-06-01 | CLOSED 31-May-13 | Draft Tech Note will be made available on CSSA Public CWE
CSSMWG Telecon 20 June 2013
2013-0620-01 | Review email from MG on frequency bands | all WG members | 2013-07-18 | CLOSED 23-Jul-13
2013-0620-02 | Check for time code format for SN and NEN | JP | 2013-07-18 | CLOSED 20-Jun-13 | see email of 20 June 2013.
2013-0620-03 | Review CSSMWG project definitions on CWE | all WG members | 2013-06-26 | CLOSED 23-Jul-13
SMWG Telecon - 1 August 2013
2013-0801-01 | Map deliverables onto info entities and lifecycle | JP | 2013-08-13 | CLOSED 12-AUG-13
2013-0801-02 | Review Enterprise Model in GB - does it say everything that we need it to say? | WG | 2013-08-13 | CLOSED
2013-0801-03 | Draft GB Exec Summary | EB | 2013-10-18 | CLOSED 14 Oct 13 | Outlined. Originally 13-Aug-13
2013-0801-04 | Flesh out 4.3 of Green Book | JP | 2013-10-15 | CLOSED | Partially done on 12-Aug-13. Originally 13-Aug-13. This section is being covered with the re-org or the GB.
SMWG Telecon - 13 August 2013
2013-0813-01 | Add Service combinations Magenta Book into Roadmap | EB | 2013-10-15 | CLOSED 14 Oct 13 | Outlined. Originally 10-Sep-13
SMWG Telecon - 17 September 2013
2013-0917-01 | Add Trajectory Prediction Blue Book into Roadmap | EB | 2013-10-15 | CLOSED 18Nov 13
SMWG Telecon - 15 October 2013
No action items
SAN ANTONIO 28-31 Oct 2013
2013-1028-01 | Increase font on the GB executive summary diagram | EB | 2013-11-07 | Closed 18-Nov-13
2013-1028-02 | Review GB to verify that the enterprise model concepts are described/referenced within the rest of the document. | JR | 2013-11-30 | CLOSED 27-Nov-13 | Original due date was 15-Nov-13.
2013-1028-03 | Coordinate Service planning information with MOIMS SM&C and SIS DTN | EB | 2014-10-31 | CLOSED 4-NOV-14
2013-1028-04 | Review GB for a final time and provide comments back to John before Jan 14 telecon. | ALL | 2014-01-08 | Closed 17-Jan-14 | Original due date was 14-Jan-14. Moved so that JP can incorporate changes before telecon
2013-1028-05 | Finalize GB SysML diagrams | JP, PP | 2013-12-09 | CLOSED 9-Dec-13
2013-1029-01 | Add SoS prototype test for unallocated/unused time. NASA will use SN TUT | MG, CA | 2013-11-25 | CLOSED 3-Dec-13
2013-1029-02 | Add the information entity referential model to the GB. | JP | 2013-12-09 | CLOSED 9-Dec-13
2013-1029-03 | Send draft Test Plan out for review | KT | 2014-01-14 | Closed 21-Jan-14 | Original due date was 15-Nov-13.
2013-1029-04 | Send draft Test Report out for review | KT | 2014-01-30 | Closed
2013-1029-05 | Walk through the Functional Groups to determine the different permutations of configuration profiles using the Service Catalog 1 | JP | 2014-03-31 | CLOSED 2-Apr-14
2013-1030-01 | Rework and update the words in the Mission Events section of the GB. Include only input planning | CH, EB | 2014-01-14 | Closed | Original due date was 28-Nov-13. EB to close the loop with Colin. EB will provide input to CH by Jan 31 and then will provide JP
2013-1030-02 | Look at the information entities to see if there are priorities within the information entities relative to the blue books that contains those information entities | EB | 2014-01-14 | Closed | Original due date was 28-Nov-13.
2013-1031-01 | Initial draft survey/compendium of visibility related events | CH, EB | 2014-01-30 | Closed | OBE, this will be addressed as the book is written
2013-1031-02 | Preliminary draft of the Planning Information Book | CH |  | CLOSED 1-Apr-15 | Orginial due date was 28-Feb-14.OBE, new approach see AI 2014-0402-04
2013-1031-03 | Create an abstract model of service package request components | EB | 2014-03-31 | CLOSED 3-Apr-14 | Initial cut was sent out 6 Dec. See AI 2014-0402-05
2013-1031-04 | Create an abstract model of service package result components | JP | 2014-03-31 | CLOSED 3-Apr-14 | See AI 2014-0402-06
2013-1031-05 | JAXA to determine if they can do prototype testing for the SP/SR BB | AT, EB | 2014-03-31 | CLOSED 12-May-14 | OBE. Learned Asama has left CSSM WG.
2013-1031-06 | Use projects and dates from CWE framework to update GB roadmap | JP | 2013-12-09 | Closed 18-Nov-13
2013-1031-07 | Develop engineering concepts for the Events Sequence | EB | 2014-03-31 | CLOSED 3-Apr-14 | AI 2014-0402-13 will include this AI - Close this one?
2013-1031-08 | Complete test report for B-1 | KT | 2013-11-30 | CLOSED 9-Dec-13 | Resend email. Done
SMWG Telecon - 19 November 2013
No Actions
SMWG Telecon - 10 December 2013
No Actions
SMWG Telecon - 22 January 2014
No Actions
SMWG Telecon - 28 January 2014
2014-0128-01 | Determine extensibility of each information entity | All WG | 2014-03-31 | CLOSED 3-Apr-14 | See AI 2014-0402-10?
2014-0128-02 | Review the Simple Schedule in preparation for Feb 11 Telecon | All WG | 2014-02-11 | Closed
SMWG Telecon - 4 March 2014
2014-0304-01 | See how the SoS schema handles the additionalParameter | JP | 2014-03-07 | Closed 5-March-14
2014-0304-02 | Update the SoS Annex B | JP | 2014-03-07 | Closed 5-March-14
2014-0304-03 | Update the ICS and the normative parameter description (null parameters) | CH | 2014-03-05 | Closed 4-March-14
SMWG Telecon - 18 March 2014
No Actions
Noordwijkerhout 31 Mar - 3 Apr 2014
2014-0401-01 | Provide the key reporting metrics or statistical characterizations, with definitions that are reported for each Agency’s networks’ service accounting for the customer (as it relates to the Service Package/Service agreement and recommendations for other metrics reported out weekly/monthly, etc). | EB | 2015-03-21 |  | MG, JPC, MU and CC (for CNES) presented/discussed their agency's service accountability data at the London meeting. Erik will provide the DSN at a later date.Action closed for the others on 13-Nov-14.
2014-0402-03 | Planning Information Draft outline of communications geometry Preliminary draft-output only | CH | 2014-06-30 | CLOSED 15 July 2014 | Original date was April 30
2014-0402-04 | Update Generic File Transfer Concept Paper | CH | 2014-06-30 | CLOSED 10 July 2014 | Original date was April 30
2014-0402-05 | Service Package Request management component writeup | EB | 2015-02-10 |  | A presentation was completed on 8 May. Need to complete writeup
2014-0402-06 | Service Package management component writeup | JP | 2014-05-05 | CLOSED 5-May-14
2014-0402-07 | Generic File Transfer Charter update proposal | EB | 2014-05-20 | CLOSED 2-June-14
2014-0402-08 | Simple Schedule of Services Test Report | KT,MG | 2014-06-02 | CLOSED 2-June-14
2014-0402-09 | Generic File Transfer Project definition | EB | 2014-10-07 | CLOSED 6-OCT-14 | Original date was June 30.
2014-0402-10 | Service Agreement FG definitions, FG specializations, IOAG Services mapped to FGs | JP,AC | 2014-07-01 | CLOSED 1 July 2014
2014-0402-11 | Simple Schedule of Services RID Processing | CH | 2014-11-14 | CLOSED 11-Nov-14 | This date is a placeholder. Date not known until doc release
2014-0402-12 | Trajectory Prediction Draft presentation | Jessica R | 2014-08-05 | CLOSED 13 Aug 2014
2014-0402-13 | Event Sequence Extensibility/component presentation | PP | 2014-08-26 | CLOSED 26-Aug-14 | Actionee changed from EB to PP. Draft presentation sent out on 25-Aug. Presented on 26-Aug.
2014-0402-14 | Define the set of concerns to be coordinated between recommendation development activities and develop a tracking mechanism. Draft Presentation | EB | 2014-07-28 | CLOSED 12 Aug 2014
2014-0402-15 | FG, FRs and IOAG svcs mapping to Service Agreement and service configuration profile | JP,AC | 2014-10-07 | CLOSED 6-OCT-14
2014-0402-16 | Planning Information - Complete draft white book including request | CH | 2014-11-12 | CLOSED 12-Nov-14 | Original due date was 3-Nov-14
2014-0402-17 | Generic File Transfer Preliminary draft white book | CH |  | CLOSE see subsequent action 2014-1114-11 | Will reschedule at the London Meeting. Original due date was 3-Nov-14
2014-0402-18 | Trajectory Prediction Draft white Book (Outline) | Jessica R | 2014-11-10 | CLOSED 12-Nov-14
2014-0402-19 | Event Sequence preliminary draft of book | EB | 2014-11-03 | CLOSED 9/25/2014 | Duplicate of AI 2013-0415-14
2014-0402-20 | Update green book post CESG review | JP | 2014-08-10 | CLOSED 20-Aug-14 | Made all changes but final date will depend on response from SLS area director. SLS area director sent email that he was satisfied with all proposed dispositions.
2014-0402-21 | Remove Trajectory project from CWE framework | EB | 2014-06-30 | CLOSED 28-Apr-14 | OBE - it was determined that the BB needs to be developed
2014-0402-22 | Update green book to reflect Trajectory prediction book deletion | JP | 2014-04-28 | CLOSED 16-Apr-14 | Update was delivered but it was determined that the BB needs to be developed
2014-0402-23 | Update SoS SANA section | CH | 2014-04-28 | CLOSED 28-Apr-14
SMWG Telecon - 28 April 2014
2014-0428-01 | Discuss version info for NDM with Nav WG | EB | 2014-05-14 | CLOSED 8-MAY-14 | JP had a meeting with D. Barry
2014-0428-02 | Update SoS | CH | 2014-04-29 | CLOSED 28-Apr-14
2014-0428-03 | Update Green book - new diagram, add trajectory prediction back in, etc. | JP | 2014-04-29 | CLOSED 28-Apr-14
SMWG Telecon - 14 May 2014
2014-0514-01 | Provide comments to the Service Package writeup and the Service Package Request writeup. | All | 2014-05-30 | CLOSED 3-June-14
SMWG Telecon - 3 June 2014
2014-0603-01 | Review the SoS Prototype Test Plan/Report and provide comments | All | 2014-08-26 | CLOSED 26-Aug-14 | Originally due 15 July 2014. Conclusion is that the test report is in good shape and unless there are significant RIDs that modify the schedule of services recommendation (as a result of the upcoming agency reviews) the document will essentially be used as is for blue book candidacy
2014-0603-02 | Provide write up on metadata for delta dor use case re: service package and service request | EB | 2015-03-21 |  | With regard to DDOR service and a mission using multiple agency TTC networks. Will reschedule at London Meeting. Original due date was 4-Nov-14
2014-0603-03 | Bring in summary of scheduling flexibilities and constraints from the SN | JP and JPC | 2014-06-24 | CLOSED 24 24-Jun-14
SMWG Telecon - 24 June 2014
2014-0624-01 | Propose namespace architecture for CSSA schemas within CCSDS namespace | JP, AC | 2014-12-15 |  | Will be ready for a discussion in London. Original date 10-Nov-14
SMWG Telecon - 15 July 2014
2014-0715-01 | Review the Terrestrial File Transfer Green Book and provide comments | All | 2014-09-25 | CLOSED 25-SEPT-14 | Original date was 5-Aug
2014-0715-02 | Review the draft Planning Data Formats book and provide comments | All | 2014-09-25 | CLOSED 25-SEPT-14 | Orignal date was 25-Aug. Received comments from JPC, EB
SMWG Telecon - 13 August 2014
2014-0813-01 | Look at the updated simple schedule of services recommendation and follow-up re CESG poll condition removal | EB | 2014-08-15 | CLOSED 14-Aug-14
2014-0813-02 | Determine how the NDM does or does not handle "layered" trajectories, discuss with navigation working group chair as appropriate | EB | 2014-09-16 | CLOSED 25-Aug-14 | Originally due 16-Sept. Layered=using a different/unique reference system.
SMWG Telecon - 26 August 2014
2014-0826-01 | A request to the working group membership to check with their appropriate agency representatives with regard to security considerations for protocol selection for GFT; Likely candidate is WebDav | All | 2014-10-04 | CLOSED 6-OCT-14
2014-0826-02 | Follow up with navigation working group chair as to possibility for expression of “layered” (i.e. multi-reference center) sets of trajectories/ephemerides | EB | 2014-09-25 | CLOSED 9/25/2014
2014-0826-03 | Talk with appropriate agency representatives and provide inputs with respect to radio frequency interference (RFI), data volume/data rate estimation, and cost estimate data inputs for consideration in the draft Planning Information recommendation | All | 2014-12-09 |  | Summary of events and parameters/data exchanged. Provide to CH so he can put it in the draft. Will discuss in London.
SMWG Telecon - 25 September 2014
No Actions
SMWG Telecon - 07 October 2014
No Actions
SMWG Telecon - 04 November 2014
No Actions
London - 10-14 November 2014
2014-1110-01 | Put all RIDs in one type of format file to pull all the different formats together | CH |  | Closed 11-Nov-14
2014-1110-02 | Create a diagram to be included in the Simple Schedule introduction to clarify the context of the document (possibly by using the life-cycle diagram) | MG | 2014-12-09
2014-1110-03 | Look at the test report and provide any comments on mapping to SN or NEN items for EUMETSAT RID HH004. (Perform analysis relative to test report and as to abliity to map to proposed standard.) | JPC | 2014-12-09
2014-1110-04 | Send SoS test report to Hayley Higgins | KT | 2014-11-10 | Closed 10-Nov-14
2014-1110-05 | Capture all abbreviations in the SoS | KT | 2014-11-10 | Closed 10-Nov-14
2014-1110-06 | Update the diagram according to CNES RID JMS11 | MG | 2014-12-09
2014-1111-01 | Include in test report that we will not prototype the nesting of AdditionalParameter | MG,KT | 2014-12-09
2014-1111-02 | RE: RID ESA-ESA 11 Think through and come up with an answer. Consider if an optional parameter should be added to the Activity class to indicate the level of commitment to the activity. | CH | 2014-11-21
2014-1111-03 | Look up the frequency for UHF and VHF for the SoS | MG | 2014-12-09
2014-1111-04 | Clarify the note to indicate the information bookmarking function in the case of the antenna free time in para 3.4.2.2. See NASA RID Antenna Freetime | MG | 2014-12-09
2014-1112-01 | Produce text re SANA policy that can be re-used for each CSS area blue book | EB, MdG | 2014-12-01 |  | Urgent
2014-1112-02 | Provide examples of recurrent requests for your agency | MG, CC, MU | 2015-01-13
2014-1113-01 | Produce a graphical model based on the green book planning request | EB | 2014-12-09
2014-1113-02 | Capture the refined details of the planning request using use cases. | CH | 2014-12-09 | CLOSED
2014-1113-03 | Perform an analysis of the accountability data from each of the agencies | JR | 2015-03-21
2014-1113-04 | Do a proof of concept for 1) config profile out of service profiles 2) pare down TC/TM SLE-Plus profile (Bake-off) | JP, AC | 2015-02-10
2014-1113-05 | Develop a standard header | CH | 2014-12-09
2014-1114-01 | Develop the SANA registry considerations/policy | EB | 2015-01-13 |  | Define the namespace for the Simple Schedule
2014-1114-02 | Sort out the abstract request common type for the planning data format | EB, CH, JPC, JP | 2015-02-10
2014-1114-03 | Define the remaining event definitions for the planning data format | All | 2015-01-13
2014-1114-04 | Check communition geometry events for the planning data format | All | 2015-01-13
2014-1114-05 | Update planning data format white book | CH | 2015-03-21
2014-1114-06 | Complete the service request component write-up | EB, JPC | 2015-03-21
2014-1114-07 | Flexibility and Constraints extensibility schema for the service request | JP | 2015-03-21
2014-1114-08 | Service request vs planning request alignment | JPC, CH, JP | 2015-03-21
2014-1114-10 | First draft (white book) of the Trajectory Prediction book | JR | 2015-03-21
2014-1114-11 | List of questions for the Generic File Transfer preliminary draft | Ch | 2015-01-27
2014-1114-12 | First draft (white book) of the Event Sequence | PP, EB | 2015-03-21
2014-1114-13 | Strawman on service package result structuring | JPC, JP | 2015-03-21

## Color Code and Actionees
Color Code
Red text means the item is past its due date
Orange text means that the item is past its original due date, but has been extended.
Black text in orange cells means that the action is on hold with no definite due date
Green text means that this action Item was closed since the last time the Action Item report was issued. Any green items are listed on the Open Actions sheet until they are discussed at a meeting or telecon, after which they are removed fro the Open Actions sheet (they remain on the All Actions sheet)
Meeting/telecon headings are color-coded to reflect the highest level of incompleteness for any action item from that meeting/telecon. For example, if the action items for a particular meeting contain one or more orange (past original date but extended) items and one or more red (past due) items, the heading will be red.
Assignees
Initials | Name
AC | Anthony Crowson
CH | Colin Haddow
CC | Claudia Ciocirlan
EB | Erik Barkley
FB | Fred Brosi
JVP | John Pietras
KT | Karen Tuttle
MD | Michel Dugast
MG | Marcin Gnat
NC | Nicolas Champsavoir
PP | Paul Pechkam
PS | Peter Shames
SG | Sylvain Gully
SZ | Sil Zendejas
TA | Takashi Asama
TB | Tung Bui
YN | Yagi Nobuhiro
JR | Jessica Reinert
JPC | Jean-Pierre Chamoun

## Open Actions by date
AI # | Action | Assignee | Due Date
2014-1112-01 | Produce text re SANA policy that can be re-used for each CSS area blue book | EB, MdG | 2014-12-01
2014-0826-03 | Talk with appropriate agency representatives and provide inputs with respect to radio frequency interference (RFI), data volume/data rate estimation, and cost estimate data inputs for consideration in the draft Planning Information recommendation | ALL | 2014-12-09
2014-1110-02 | Create a diagram to be included in the Simple Schedule introduction to clarify the context of the document (possibly by using the life-cycle diagram) | MG | 2014-12-09
2014-1110-03 | Look at the test report and provide any comments on mapping to SN or NEN items for EUMETSAT RID HH004. (Perform analysis relative to test report and as to abliity to map to proposed standard.) | JPC | 2014-12-09
2014-1110-06 | Update the diagram according to CNES RID JMS11 | MG | 2014-12-09
2014-1111-01 | Include in test report that we will not prototype the nesting of AdditionalParameter | MG,KT | 2014-12-09
2014-1111-03 | Look up the frequency for UHF and VHF for the SoS | MG | 2014-12-09
2014-1111-04 | Clarify the note to indicate the information bookmarking function in the case of the antenna free time in para 3.4.2.2. See NASA RID Antenna Freetime | MG | 2014-12-09
2014-1113-01 | Produce a graphical model based on the green book planning request | EB | 2014-12-09
2014-0624-01 | Propose namespace architecture for CSSA schemas within CCSDS namespace | JVP, AC | 2014-12-15
2014-1209-1 | Double check the SOS RID disposition report prior to release to RID submitters | EB | 2014-12-15
2011-0520-06 | State policy for schema maintenance regarding SANA and provide writeup of policy. Provide initial input by 13 May. | EB | 2015-01-13
2014-1112-02 | Provide examples of recurrent requests for your agency | MG, CC, MU | 2015-01-13
2014-1114-01 | Develop the SANA registry considerations/policy | EB | 2015-01-13
2014-1114-03 | Define the remaining event definitions for the planning data format | All | 2015-01-13
2014-1114-04 | Check communition geometry events for the planning data format | All | 2015-01-13
2014-1209-5 | Provide comments/analysis on each info entity vs. the proposed common request header | EB | 2015-01-13
2014-1209-2 | Process all instances of “network” and see where change to “Provider CSSS” does or does not make sense | CH
2014-1209-3 | Update the revised the antenna free-time diagram re “network” term as determined by C. Haddow | MG
2014-1209-4 | Wordsmith the text for the antenna free time updates from M. Gnat | CH