## Open Actions
AI# | Action | Assignee | Due Date | Status | Notes
SMWG Spring 2011 Meeting, 16-20 May 2011
2011-0520-06 | State policy for schema maintenance regarding SANA and provide writeup of policy. | HD | 2017-11-01 |  | Originally Fall meeting 2011. Need this for SoS Blue book. Run by XML SIG Noted that this will likely need to be discussed within the context of XSG as part of the overall CCSDS schema management set of considerations. Smaller initial steps agreed to as initial steps to closing the action. Waiting for written version. See Peter Shames SoS red book comments. We are going to discuss schema management at the Rome meeting. This was handed over from EB.
SMWG Meeting - Darmstadt 9-12 November 2015 Meeting
2015-1112-16 | Complete draft white book of Event Sequence | PP, EB | 2018-04-02
SMWG Meeting - Rome 17-21 October 2016 Meeting
2016-1017-4 | Check the Planning Event terminology with the CCSDS glossary | CH | 2017-07-17 |  | Original date was 30-Dec-16
2016-1017-5 | Add PIF test case for space-based aperture | JPC | 2017-07-31 |  | JP will think about a test case and report back at the January telecon. Original due date was 30-Jan-17 | X
2016-1021-19 | Produce outline of SMURF Test cases/plan | EB, KT, MG | 2017-08-11
2016-1021-20 | Develop draft TGFT White book | CH, JVP | 2017-08-15 |  | Original date was 8-May-17.
2016-1021-25 | Develop Service Package Data Format First Draft | JPC | ?
SMWG Meeting - San Antonio 8-12 May 2017 Meeting
2017-0512-01 | Provide Planning products from TDRS to user missions. The source is the FDF or the user missions information. This is for the PIF. | JPC | 2017-06-30
2017-0512-02 | Provide Planning Products for the Mars relay to Rover for the PIF | EB | 2017-06-30
2017-0512-03 | Update PIF book and schema based on conclusion re-structuring, etc. | CH | 2017-08-16 |  |  | X
2017-0512-04 | Update AbstractEvent model based on discussion with the NAV WG | CH | 2017-05-19
2017-0512-05 | Add PIF SM Abstract Event in Common Class tab in Inter-recommendation spreadsheet | KT | 2017-05-31 |  | Wait until Colin updates model from the NAV/CSS SM joint meeting
2017-0512-06 | Develop PIF Test case outline for test plan | EB | 2017-07-07
2017-0512-07 | Determine structure of PIF (flat vs structured) | EB, CH | 2017-07-07
2017-0512-08 | Complete inter-operations PIF testing | EB, CH, YFW, UMW | 2017-11-01
2017-0512-09 | Final PIF test plan | KT | 2017-11-01
2017-0512-10 | Exercise: Assume structure similar to DSN; check that events in PIF make sense for DSN | EB | 2017-06-30
2017-0512-11 | Prepare a presentation on service package proposal (re: state machine) | MG | 2017-07-31
2017-0512-13 | Look at SPR, the SMURF, config profile and event sequence and propose how these can fit together | EB | 2017-08-17
2017-0512-14 | OIDS/FRs vs Event Sequences | PP, EB | 2017-11-01
2017-0512-15 | Develop examples of event sequences based on concept being developed for DSN | EB | 2017-11-01
2017-0512-16 | Provide strawman of proposed event sequence structuring | EB | 2017-07-17
2017-0512-17 | Prepare strawman UML diagram of the configuration profile | MG | 2017-07-17
2017-0512-18 | Develop Service Agreement/Config Profile service profiles | MG, AC | 2017-11-01
2017-0512-19 | Provide IOAG modulation recommendations and send to AC | EB | 2017-06-30
2017-0512-20 | Develop preliminary draft Service Agreement/Config Profile white book | MG | 2017-11-01
2017-0512-21 | Complete CWE file restructure | KT | 2017-07-17
2017-0512-23 | Update SoS schema and send to SANA | CH | 2017-08-30
2017-0512-24 | Write a RID to change the SANA Registry section D2.2 of the SoS to replace the last sentence of the section to indicate that the schedule publisher goes into the organization roles registry. Make sure to include the url for the registry. | EB | 2017-06-15
2017-0512-25 | Write a RID to change the SANA Registry section D2.3 of the SoS thefirst paragraph url to spacecraft registry (remove "id" in url) | EB | 2017-06-15
2017-0512-26 | Write a RID to change the SANA Registry section D2.4 of the SoS to clarify that the site name must have at least one aperture field. | EB | 2017-06-15
2017-0512-27 | Write a RID to change the SANA Registry section D2.4 of the SoS to remove fourth paragraph. | EB | 2017-06-15
2017-0512-28 | Write a RID to change the SANA Registry section D2.6 of the SoS to update this section to call out the SANA Registry procedure document as per email agreed to by Audrea and Tom. | EB | 2017-06-15
2017-0512-29 | Write a RID to update the Abstract Event model in the SoS | CH | 2017-05-19
2017-0512-30 | Write a RID to change the SANA Registry section D2.6 of the SoS to change the policy to 3.11b and then to indicate the review authority is CSS area | EB | 2017-06-15
2017-0512-31 | Write a RID to change the SANA Registry section D2.8 of the SoS to edit the listing so that g) follows f) (currently a) follows f)) | EB | 2017-06-15
2017-0512-32 | Dispose SoS RIDs Update Books | CH | 2017-07-21
2017-0512-33 | Update SoS Prototype Test Report | EB | 2017-07-06
2017-0512-34 | Write a tech note to indicate registry update policy for the CSSM for example in the SoS,how is someone to know that they need to change the version number in section D2.8 or how does someone know to clone the section D2.8 and modify it for a different recommendations | EB | 2017-08-17 |  | This is similar to Action 2011-0520-06: State policy for schema maintenance regarding SANA and provide writeup of policy.
2017-0512-35 | Draft initial SMURF schema | CH | 2017-07-17
2017-0512-36 | Update SMURF text to be consistent with UML diagram from San Antonio meeting | CH | 2017-07-17
2017-0512-37 | Coordinate SMURF prototyping environment | MG, CH | 2017-08-18
2017-0512-38 | Complete draft of SMURF test plan | KT | 2017-08-31
2017-0512-39 | Update TGFT white book with XFDU decisions | CH | 2017-07-31
2017-0512-40 | Finalize the TGFT meta data definition | CC | 2017-07-31
2017-0512-41 | Produce strawman outline for ground observation sequence for DDOR | EB | 2017-08-16
2017-0512-42 | Produce 1st cut of DDOR config parameters and indicate where they go in FRM | EB | 2017-08-16
2017-0512-43 | Update Draft TGFT Test Plan with testing details | CC, HL | 2017-07-31
2017-0512-44 | Final TGFT test plan | KT | 2017-11-03
2017-0512-45 | Check the draft restricted XFDU schema supplied by JVP and update as determined | CC | 2017-07-31
2017-0512-46 | Extend the restricted XFDU schema to include TGFT specific meta data | CC | 2017-07-31
2017-0512-47 | Provide Service Catalog inputs on statements for service performance; eg "gain should be provided for 45 deg" | EB | 2017-08-29
2017-0512-48 | Update Service Catalog based on inputs | HK | 2017-11-01
2017-0512-49 | Revise next rev concept book per comments from Cleveland meeting and MG comments | EB | 2018-04-02
2017-0512-50 | Update lifecycle diagram | EB | 2018-04-02
2017-0512-51 | Put comments in master copy of concept book | MG | 2017-07-31
2017-0512-52 | Draft high-level requirements for the Management Services book | AC, HD, CH | 2017-11-01
2017-0512-53 | Draft concept for extensible management services | AC,, HD, CH | 2018-04-02
2017-0512-54 | Produce preliminary draft test plan for management services | MG, KT | 2018-03-12
2017-0512-55 | Clean up the control architecture diagrams and further iterate with CSTS and CSSM | EB | 2017-08-30

## All Actions
AI # | Action | Assignee | Due Date | Status | Notes
SMWG Actions Items, Colorado Springs Meetings, 15 -- 19 January 2007
COS-01 | Provide parameters necessary for configuring of ranging service (for ESA) | KC | 2007-01-19 | Closed administratively | To be subsumed under an broader action for developing a survey for inputs from each agency
COS-02 | Update forward subcarrier frequency parameter to state a set of discrete options in SA, etc. | JP/FB | 2007-12-15 | CLOSED | Transferred to NGSM work items spreadsheet
COS-03 | Identify general time for shadow tracking opportunity for MEX | KC/.AC | 2007-04-20 | Closed administratvely | Prototype plans to be discussed at October meetings
COS-04 | Identify likely supported operations for prototype interoperations | YN | 2007-02-02 | Closed
C0S-05 | Provide complete details on CSSXP prototype limitations | PP | 2007-02-15 | Closed
COS-06 | Revise trajectory analysis with approach for folding ANT and AAT as a single operation | AC or JP | TBD | Closed | Pending discussion at March 2008 meetings
COS-07 | Provide use case information from JSC operations perspective | MP | 2007-12-30 | CLOSED | Overcome by events
COS-08 | Send JAXA represnetatives PQ test plan for original JPL/ESA prototype interoperations | EB | 2007-01-25 | Closed
COS-09 | Compute RID close out times and schedule times for each assignee | EB | 2007-01-19 | Closed | Results captured in RID Tracking Spreadsheet
COS-10 | Update the WG Charter | EB | 2007-10-30 | Closed
COS-11 | Send JP information on tune-in leg parameters | KC | TBD | Closed | Pending discussion at October meetings
SMWG Actions Items, Greenbelt Meetings 07, 08 June 2007
GB-01 | Determine Availabiltiy of JPL prototype Red-1 beyond end of 2007 (info to ESA) | EB | TBD | CLOSED | Overcome by events
GB-02 | State semantics of antennaPreferennece parameter in handover situations. | JP |  | Closed
GB-03 | Provide bullet points on handover concept and other concepts from conceptual analyses done so far. | JP (EB for EVT Seq) | 2007-11-01 | CLOSED | Event Sequence part transferred to NGSM work items spreadsheet
GB-04 | Need to defined what event sequence in conformance with applicable carrier profile means. (CSPC-22) | EB | 2007-11-01 | Closed | Pending check of Red-2
GB-05 | Determine what kind of signal threshold parameter would be stated for combined/dynamic polarization switching? | JM (CNES) | 15-Jul-07 (?) | Closed | Do not add any threshold values; see if any RIDs are produced in review of Red-2
GB-06 | Provide a list of scenarios for the revised green book to HK (e.g., UM "controlled" handovers vs. CM "initiated" handovers…also reserving antenna time followed by resplace service packages with sequence information) | EB | 2007-12-01 | CLOSED | Transferred to NGSM work items spreadsheet
GB-07 | Updated figure C-1 (Red book) to indicate message set; ie it is not a CSP-I message. | EB | 2008-03-14 | CLOSED | Transferred to NGSM work items spreadsheet (for Green Book)
GB-08 | Provide defintion of service package start time | JP | 2007-06-30 | Closed
GB-09 | Confirm ESA's position as to whether simple "yes" or "no" response on PSP is sufficient | AC | 30-Jun-07 (?) | Closed | Answer is simple yes or no should suffice
GB-10 | Put approppriate words in PSP operation description to include provisional scheduling; also put appropriate parameter in service agreement | JP |  | Closed | Pending discussions at October meeting
GB-11 | Check to see if its possible to configure CSSXP to skip production of ACK returns to help support message exchange protocol testing. | TB | 2007-06-30 | CLOSED | Overcome by events
GB-12 | Provide details on security approach for JAXA representatives (ie., e-mail subject line, public key,etc) and estimated availability date. | EB/TB | 2007-06-20 | Closed
GB-13 | Send e-mail to JAXA representatives containing sample xml messages. | EB | 2007-06-20 | Closed
GB-14 | Review JAXA ICD Parameters and SA Parameter documents and provide inputs. | EB | 2007-11-01 | Closed
GB-15 | Examine simplified diagrams to see if they can be formally "UML-ified" | JP | 2007-08-01 | Closed
GB-16 | Add legal CENTER_NAME values for OEM formatted trajectory predictions in the Service Agreement section. | FB | 2007-12-30 | CLOSED | Transferred to NGSM work items spreadsheet
GB-17 | Revise service package definition to allow multiple trajectory references (invocation, return stereotypes) | JP | 2007-07-15 | Closed
SMWG Actions Items, Telecon, Augst 2007
AGT-01 | Confirmation of "may" type requirement on CM vs. "shall" when considering cancellation of SP still needing full elaboration at expiration of minimum service definition lead time. State table to be updated accordingly | AC | 2007-10-01 | Closed
AGT-02 | Need to revise CM requirement CSPC-10 to clearly state that transfer services are not scheduled but that a spacelink aspects of the service package are scheduled. | EB | 2007-10-01 | Closed
AGT-03 | Revision of CM requirements with respect for CM determining aperture sufficiency if required and preferred antenna references are being utilized in the service package invocation (CSP operation) | EB/SZ | 2007-10-30 | Closed
AGT-04 | Revision of CM requirement CSPC-25 such that CM may construct a resultant service package that allows for service request satisfaction via multiple sequential spacelink sessions (i.e. handover situations) solely on the basis of whether or not the handover is allowed as opposed to absolutely requiring CM to do so only if satisfaction of the service request cannot be accomplished via a single continuous spacelink session. The rationale is to avoid precluding adoption of the minimally compliant CSP operation due to internal CM policy considerations (e.g., need for internal load-balancing of network resource utilization, etc.) | EB | 2007-10-01 | Closed
SMWG Actions Items, October 2007
H-01 | Present proposed parameters, approach for tune-in parameters (sweep rate, range, etc) | Michel Dugast | 2007-10-05 | Closed
H-02 | Need to revise reference framework diagram consistent with new event sequence approach, mapping between SLPS and tranfser profiles | AC | 2007-11-30 | Closed
H-03 | Update compliance matrix to indicate new operations | EB | 2007-10-30 | Closed
H-04 | Provide tutorial version of state table diagram for concept book | AC | 2007-11-30 | Closed
H-05 | Provide updated concept material for multi-center trajectory references | EB | 2007-11-30 | CLOSED
H-06 | Supply proper set of modulation options for section 5 | FB | 2007-11-15 | Closed
H-07 | Coordinate JPL DSN adoption of ALOS,including assitance for JAXA radio frequncy license, etc. | EB | ASAP | Closed
SMWG Action Items, March 2008
CC-01 | Check need for RID on document exchange protocol re "Ambiguos Retrns" (See CWE list) | JP | 2008-05-30 | Closed
CC-02 | Re-issue Trajectory Predicition handling paper | JP | 2008-04-20 | Closed
CC-03 | Update refactoring proposal to include at least one example of a service such as telemetry | NC | 2008-10-07 | Closed | (Pending further work…with regard to initial exercises for producing core book in relation to draft framework).
CC-04 | Provide a common briefing that can be used in support agency reviews of Red-2 | EB | 2008-03-24 | Closed
CC-05 | Perform editorial clean-up of Concept Book and post for support of agency reviews of Red-2 | EB | 2008-03-24 | Closed
SMWG Action Items, October 2008
BE-01 | Update timing relationship diagram to show relative event times in proper relations ship (to orange line) | SG | 2008-11-10 | Closed
BE-02 | Provide some concept metrial on event sequences, from a S/C oriented perspective (to A. Crowson) | EB | 2009-05-15 | Closed
BE-03 | Send DDOR WG example of service agreement, configuration profile, service package | EB | 2009-04-22 | Closed
BE-04 | Take a look at Red-3 and determine the set of test points (ascpects of Book that have a bearing on test plan -- ie, [perform operation] validations will likely not be in test plan) | AC | 2008-11-28 | Closed (by EB)
BE-05 | Determine if new WG is to be established for re-facotored SM approach | EB | 2009-01-02 | Closed
BE-06 | Examine XML Schema production from UML tools capabilities and report to SMWG | AC | 2014-10-01 | CLOSED 3-Apr-14 | Orignally 15-Nov-09. Initial focus will be on Info Entity schemas
BE-07 | Produces one or two UML diagrams from Red-3 in MagicDraw and release to WG | AC, PP | 2009-07-15 | Closed | Sept 2009 draft refactored core book
BE-08 | Arrange Telecon for RID Dispostion ~18 Nov 08 | EB | 2009-11-01 | Closed
SMWG Action Items, April 2009
CS-01 | Arrange montly telecons | EB | 2009-04-26 | Closed
SMWG Telecon, June 2009
040609-01 | Produce a diagram outlining the different enterprise models and implications thereof for service management -- for next telecon. | EB | 2009-06-30 | Closed
SMWG Telecon, July 2009
010709-01 | Clean-up Annex D of the Concept Book with proper figure references to the formal recommendation and removal of state machine information, | AC | 2009-07-10 | Closed
010709-02 | Check for hand-over material for concept book | JP | 2009-07-20 | Closed | Contratry to recollections, write-up/material is not immediately available
010709-03 | Provide responses to questions embedded as comments in latest concept book no later than 20 July 2009 (earlier if possible) | JP, EB | 2009-07-20 | Closed
010709-04 | Provide complete draft of test report for WG review. | EB | 2009-07-08 | Closed
SMWG Telecon, August 2009
AI # | Action | Assignee | Due Date
050809-01 | Double check draft test report findings (for omissions, errors, etc.) | AC | 2009-08-12 | Closed
050809-02 | Post copy of CESG approval version of service management recommendation for SMWG | EB | 2009-08-06 | Closed
050809-03 | Provide response re comment AC5 in draft concept book | JP | 2009-08-12 | Closed | Double check AC 5
050809-04 | Revise sections 7.3.1.1 + 7.3.1.3 in draft concept book | AC | 2009-08-12 | Closed
050809-05 | Provide response re comment AC33 in draft concept book |  |  | Closed
SMWG Telecon, October 2009
051009-01 | Review JVP's technical note monitor data naming | ALL | 2009-10-26 | Closed
SMWG Technical Meetings, 26 -- 30 October 2009
301009-01 | Perform analysis of CSTS Framework strucuturing, book approach etc. | JP | 2010-02-02 | Closed | New due date of 9 April 2010
030109-02 | Develop scope and rationale sections of draft next generation SM white paper | EB | 2010-02-18 | Closed | See email of 05 March 2010
0301009-03 | Identify types of extensibility points ofr NG WM White paper | CH/AC | 2010-03-17 | CLOSED
0301009-04 | Determine if specification can be developed inside formal modelling tool (M.Draw ) | AC | Spring 2012 meeting | CLOSED 16-Apr-12 | Originally 10-Feb-10. OBE
0301009-05 | Complete trial core book production | AC | on hold | CLOSED 16-Apr-12 | Originally 3-Mar-10 On hold pending further consideration. OBE
0301009-06 | Perform analysis re suitability/check re current managed services against trial core book | CH/AC | 2010-09-30 | CLOSED in London 2010 | Originally 12-May-10
0301009-07 | Perform identification analysis re managemed parameter for MD-CSTS | JP | 2010-08-06 | CLOSED 4 Aug 2010 | CLOSED 4 Aug 2010
0301009-08 | Perform identification analysis re managemed parameter for TD-CSTS | JP | 2010-08-06 | CLOSED 4 Aug 2010 | CLOSED 4 Aug 2010
0301009-09 | Perform identification analysis re managed parameters for PN (CCSDS) Ranging (for Spacelink) (first PN book) | EB/MD | Fall meeting | CLOSED 4 Nov 2011 | Originally 16-Apr-10 MD part is done
0301009-10 | Develop service specific book production guidelines= | CH/AC | on hold | CLOSED 16-Apr-12 | Originally 30-Apr-10. OBE
0301009-11 | Perform analyis re extracing document exchange as its own entity | SG/NC | 2010-04-30 | Closed
SMWG Telecon, March 2010
032210-01 | Determine if there are sections of the draft white paper re technical approach that could be worked in parallel and if so, request assitance form other members of WG | AC | 2010-04-05 | Closed
SMWG Technical Meetings, 03 -- 07 May 2010
030510-01 | Contact Z.K. of DLR to see what is meant by event driven SOE -- please provide some exampless | SG | 2010-06-30 | CLOSED in London 2010 | No information available
030510-02 | Generate a list/solicitation vehicle re what various agencies need for Next Generation SM (e.g., "query all') | JP | 2010-06-30 | CLOSED | email of 30 June 2010
030510-03 | Check current status of Selene parameters in CSSXP and report to JAXA representatives | EB | 2010-06-15 | CLOSED
030510-04 | Provide a copy of JAXA prsentation to JPL reprsentatives | T. ASAMA | 2010-05-07 | Closed
030710-01 | Revise Concept Book to included updated figure 2-3 per concept book review conclusion email of 07 May 2010 and produce "clean" copy with only comments for secretariat | AC | 2010-05-31 | Closed | Emailed to Secretariat on 20-May-10
030710-02 | Update the next generation concept paper and circulate | EB | 2010-07-07 | CLOSED | email of 28 June 2010
030710-03 | Clean up prototype test report and release to sceretariat | EB | 2010-09-01 | CLOSED 31 August | Originally 15-Jun-10 -- transferred to 2010-0831-01
030710-04 | Review DDOR "Implementing Arrangement" and "Service Request" and provide feed back to DDOR + SM WGs re harmonization | EB | 2011-10-06 | CLOSED | Originally 30-Jul-10
030710-05 | Produce technical note describing revised monitored data naming scheme | JP | 2010-10-01 | CLOSED 2010-10-28 | Originally 31-Jul-10
SMWG Telecon, 29 June 2010
2010-0629-001 | Follow-up with NAV WG Chair (D. Berry) as to the definition of “validated” re radiometric service | EB | 2010-06-30 | CLOSED | email of 30 June 2010
2010-0629-002a | To the extent possible, supply descriptions of various agency approaches in relation to arranging multiple or a series of related service packages for member agencies | All (in general) | 2010-08-23 | CLOSED 31 August 10 | Originally 26-Jul-10. SG - DLR does not do this.
2010-0629-002b | Supply description of DSN approach to arranging multiple or a series of related service packages | EB | Spring 2011 meeting | CLOSED (OBE) | Originally 26-Jul-10.
2010-0629-002c | Supply description of NEN approach to arranging multiple or a series of related service packages, e.g., "generic scheduling" | JP | 2010-07-26 | CLOSED | email of 7/28/10
2010-0629-002d | Supply description of ESTRACK approach to arranging multiple or a series of related service packages, e.g., "standing orders" | AC | Spring 2011 meeting | CLOSED (OBE) | Originally 26-Jul-10. Intermediate report made, will follow up with examples.
2010-0629-003 | Clean-up the poll material based inputs, and considering delivery to IOAG | JP | 2010-08-20 | CLOSED 6 August 10 | Original due 7/26/10 email of 2010-08-06
2010-0629-004 | Determine approach for soliciting inputs re NG SM from IOAG | EB | 2010-07-26 | CLOSED
SMWG Telecon, 31 August 2010
2010-0831-01 | Clean up prototype test report and release to JAXA or secretariat, depending on JAXA response (see 2010-0831-02) | EB | 2010-10-15 | CLOSED in London 2010 | Originally 15-Jun-10
2010-0831-02 | Determine if JAXA has the time and respirces to extend the prototype test report | JAXA | 2010-09-30 | CLOSED in London 2010 | JAXA will do it
SMWG Telecon, 5 October 2010
2010-1005-01 | Send email to JAXA asking if they have time and resources to extend the prototype test report | EB | 2010-10-11 | CLOSED 2010-10-25
SMWG London, October 25-29 2010
2010-1026-01 | JAXA will update prototype test report | TA | 2011-12-01 | CLOSED 16-Apr-12 | This report will apply to new testing. Originally due 28-Feb-11. Test report sent to JPL on week of 9-Apr-12
2010-1026-02 | Send a cleaned-up copy of prototype test report to JAXA with instructions for updating it | EB | 2011-10-03 | CLOSED | Originally 20-Nov-2010 | OBE
2010-1026-03 | Review JAXA spreadsheet of discrepancies in SCCS-SM and schema files | JP | 2010-11-20 | CLOSED 18-Nov-2010 | Email to T. Asama with recommended changes to Blue Book and schemas
2010-1029-01 | Develop next stage of resource class diagram and relationships for refactoring | AC | 2010-12-01 | CLOSED 15-Dec-2010
2010-1029-02 | Send overview class diagram to AC | EB | 2010-10-29 | CLOSED 2010-10-29
2010-1029-03 | Distribute concept paper to SMWG | EB | 2011-10-03 | CLOSED | Originally 15-Nov-2010
2010-1029-04 | Arrange Telecon/Webex for Dec 7 | EB | 2010-12-01 | CLOSED 2-Dec-2010
SMWG Telecon, 15 December 2010
2010-1215-01 | Provide a class diagram with component relationships (updated from London version) | EB | 2011-01-10 | CLOSED 22-Dec-10
SMWG Telecon, 1 February 2011
2011-0201-01 | Complete existing test report to reflect Blue-1 validation | EB | 2011-04-15 | CLOSED. Action to be completed as part of 2010-1026-02 | Originally 15-Mar-2011
SMWG Telecon, 15 March 2011
2011-0315-01 | Update description of figure 3-1 in Concept Book to explain scheduledServiceInstance offsets; circulate to SMWG | AC | 2011-03-17 | CLOSED 16 March 2010
SMWG Telecon, 11 April 2011
2011-0411-01 | Distribute concept paper to CESG following review at Spring meeting | EB | on hold | CLOSED 16-Apr-12 | Charter will be distributed to CESG
2011-0411-02 | Identify the logical extension points for adding D-DOR and the current CCSDS PN Ranging using the B-2 formal model elements | EB | 2011-05-06 | CLOSED (see 2011-0520-03)
SMWG Spring 2011 Meeting, 16-20 May 2011
2011-0519-01 | Check if CSSXP can use the updated schema for prototype interactions with JAXA | EB | 2011-06-07 | CLOSED 6/21/11 | Yes, will use V1.1.0 schema
2011-0519-02 | Update schema files with "V1.1.0" and "R1.1" | JP | 2011-06-01 | CLOSED 20 May 2011
2011-0519-03 | Develop suggested guidelines of what we would expect to find in external schemas. | AC/JVP | 2016-03-30 | Closed | Previously phased as: Develop approach for integrating externally defined schemas that evolve independently of SCCS-SM. To avoid problems, for example, like with multiple NAV schema versions.
2011-0520-01 | Provide categories of activities for the SM lifecycle process | EB | 2011-06-20 | CLOSED 15 June 2011
2011-0520-02 | Provide inputs to E. Barkley on SM lifecycle processes for member Agency networks | WG members | 2011-08-15 | CLOSED 2011-10-04 | Date moved up from 9/1/11
2011-0520-03 | Refactor configuration profiles and service agreements (look at white book), with first emphasis on adding tracking services: present results | AC, JP | Fall 2011 meeting | CLOSED 2011-10-04
2011-0520-04 | MAL - SMWG doc exchange protocol analysis & report | AC, CH | Fall 2011 meeting | CLOSED 2011-10-04
2011-0520-05 | Upload XML schemas to SANA | JP | on hold pending resolution with NavWG | CLOSED 15 Oct 13 OBE | Originally Fall meeting 2011
2011-0520-06 | State policy for schema maintenance regarding SANA and provide writeup of policy. | HD | 2017-11-01 |  | Originally Fall meeting 2011. Need this for SoS Blue book. Run by XML SIG Noted that this will likely need to be discussed within the context of XSG as part of the overall CCSDS schema management set of considerations. Smaller initial steps agreed to as initial steps to closing the action. Waiting for written version. See Peter Shames SoS red book comments. We are going to discuss schema management at the Rome meeting. This was handed over from EB.
SMWG Telecon, 21 June 2011
2011-0621-01 | Update categories of activities for the SM lifecycle process | EB | 2011-06-24 | CLOSED 7/1/2011
2011-0621-02 | Schedule next telecon (target - early to mid-August) | EB | 2011-06-24 | CLOSED 6/27/2011
SMWG Telecon, 26 Sept. 2011
2011-0926-01 | Coordinate with SM&C to discuss MAL-Doc Exchange Protocol | CH | 2011-10-01 | CLOSED
2011-0926-02 | Coordinate with NavWG to discuss schema issues | EB | 2011-10-01 | CLOSED
SMWG Telecon, 12 Oct. 2011
2011-1012-01 | Add discussion of DDOR to Boulder agenda (part of refactoring/ranging discussion) | JP |  | CLOSED
SMWG Boulder, 31 Oct - 5 Nov 2011
2011-1031-01 | JPL completes review of JAXA test report | EB | 2012-07-03 | CLOSED 2-Jul-12 | Depends on JAXA producing report by 1 Dec 2011 (see AI 2010-1026-01)
2011-1103-01 | Assess the current version of the CCSDS Catalog/Service Agreement book with respect to their Agencies' ground stations and services. Send results the HK. | NC, TA, CH, EB, MG | Spring 2012 Meeting | CLOSED 16-Apr-12 | Originally 01 Mar 2012; HK suggests focusing on concept if pressed for time. OBE
2011-1103-2 | Compare the current version of the SA book parameters with Blue-1 SA parameters | WG | 2012-04-18 | CLOSED 18-Apr-12 | Originally 01 Mar 2012
2011-1103-3 | Comment on the breakdown of Service Agreement templates. Send results to HK. | NC, TA, CH, EB, MG | Spring 2012 Meeting | CLOSED 16-Apr-12 | Originally 01 Mar 2012. OBE
2011-1103-4 | Check pcmpskpm error found by JAXA prototyping | JP | 2011-12-01 | 2011-12-15 | email "pcmpskpm element in SM schema", from J Pietras to T Asama
2011-1103-5 | How does ESTRACK disseminate the schedules to the missions? | CH | 2011-12-01 | CLOSED 16 Nov 2011
2011-1103-6 | Discuss NavWG event file work | EB | 2012-01-23 | CLOSED 23-Jan-12 | Email to SMWG
2011-1104-1 | Update charter with new level of effort estimates | EB | 2012-05-29 | CLOSED | Originally 18 Nov 2011 Will be addressd as part of the Project plans once the project has been created
2011-1104-2 | 1st draft description of management constructs elements | JP | 2011-12-15 | CLOSED 5 Dec 2011
2011-1104-3 | White book of framework elements, including candidate extension points. Update - this will now be material for the Green Book. | AC | 2012-10-15 | CLOSED 18-Oct-12 | Originally 15 Mar 2012; Per 15 Mar telecon, agreed to focus on extension mechanism. Part of Green Book production schedule
2011-1104-4 | Determine use of Teamwork server and/or alternate versioning scheme for MagicDraw model | EB, PS | 2012-03-30 | CLOSED. | Originally due 15-Jan-12. MDZIP files will be posted to CWE.
2011-1104-5 | Normalize existing model elements | AC, PP | 2012-02-29 | UML model brought into compliance with Green Book as of 29 Feb. | Originally 15-Dec-2011
2011-1104-6 | Establish biweekly WebEx schedule (tentatively Tuesdays) | EB | 2011-11-15 | CLOSED
2011-1104-7 | Develop UML profile for refactoring | PP | 2012-04-15 | CLOSED. | Originally 15 Mar 2012; Will be a continuing process that AC and PP will control.
2011-1104-8 | Develop preliminary assessment of value of different phases of lifecycle and associated information | EB | 2011-11-14 | CLOSED
SMWG Telecon, 15 Nov 2011
2011-1115-01 | Think about what a Blue Book for an information entity would/should contain | WG members | 2011-12-06 | CLOSED 15 Dec 2011 | Not addressed at 6 Dec 2011 telecon
SMWG Telecon, 19 Jan 2012
2012-0119-1 | Follow up on pcmpskpm email with T. Asama | JP | 2012-01-19 | CLOSED 19-Jan-12 | email sent to T. Asama
2012-0119-2 | Document perceived issue with mutual RFI among spacecraft across multiple (interAgency) Complexes (example: X-band hogs) | AC | 2012-04-15 | CLOSED | Originally 31-Jan-12
2012-0119-3 | Update workplan Gantt chart | EB | 2012-03-30 | CLOSED 28-Mar-12 | Originally 10-Feb-12
2012-0119-4 | Provide mindmap of deliverables | EB | 2012-01-31 | CLOSED 30-Jan-12
SMWG Telecon, 31 Jan 2012
2012-0131-1 | Get schedule information from D. Berry for the NavWG Event File work | EB | 2012-02-03 | CLOSED 13-Feb-12 | email from D. Berry describes NavWG plans for working on Event File
SMWG Telecon, 29 Feb 2012
2012-0229-1 | Post IOAG responses to CWE | JP | 2012-02-29 | Closed
2012-0229-2 | Email overdue AIs to membership | JP | 2012-03-01 | Closed | Needs to be done again; repeat as needed
2012-0229-3 | Post UML model to CWE | JP, PP | 2012-03-05 | Closed
SMWG Telecon, 15 Mar 2012
2012-0315-1 | Contact NAVWG Chair to coordinate joint session at Spring meetings | EB | 2012-03-16 | CLOSED | SMWG invited to sit in on session dealing with Events
2012-0315-1 | Contact JAXA representatives about B-1 prototype test report | EB | 2012-03-16 | CLOSED | JAXA still intends to produce the report
SMWG - Darmstadt, 16-19 April 2012
2012-0418-01 | Collect and submit Agency documents on Network Unused Resource Availability, Visibility/Events, and Schedule formats and explanation | WG members | 2012-05-11 | CLOSED 15-May-12 | Originally 2-May-12
2012-0419-01 | Look at functional resource definitions, whether they are consistent with NGSM concepts | WG members | 2012-05-02 | CLOSED 23-Apr-12
2012-0419-02 | Participate in CSTSWG telecon | WG members | 2012-05-08 | CLOSED
2012-0419-03 | Put folder on CWE for AI #2012-0418-01 inputs | JP | 2012-04-23 | CLOSED 23-Apr-12
2012-0419-04 | Check on CWE access for new members | EB | 2012-05-29 | CLOSED 15-May-12 | Message sent to Secretariat, reminder sent on 2-May-12
2012-0419-05 | Develop framework prioritization options | EB | 2012-08-31 | CLOSED 1-Oct-12 | Orignally 23-April-12. Eric will put out email listing options proposed so far.
2012-0419-06 | Develop Concept overview (section 2) of GB | AC | 2012-07-31 | CLOSED 27-Jun-12 | Originally 18-May-12
2012-0419-07 | Elaborate Lifecyle and Functional resource model sections of 3 | JP | 2012-05-18 | CLOSED 30-May-12
2012-0419-08 | Develop Enterprise Model section of 3 | PP | 2012-09-01 | CLOSED 20-Sept-12 | Originally 18-May-12
2012-0419-09 | First cut visibility section | JP | 2012-06-30 | CLOSED 6-Jun-12 | Originally 22-May-12
2012-0419-10 | Produce Roadmap section of the Green Book | EB | 2012-09-15 | CLOSED 18-Oct-12 | Originally 1-Jun-12. Now part of Green Book production schedule
SMWG Telecon - 2 May 2012
2012-0502-01 | Review use cases for functional resource IDs (instance combinations) | JP | 2012-08-31 | CLOSED 27-Aug-12 | Originally 25-May-12
SMWG Telecon - 19 June 2012
2012-0619-01 | Develop characteristics of events from agency inputs | CH | 2012-12-15 | CLOSED 19-DEC-12 | Originally 18-Jul-12. Emphasis will shift to categorizing classes of events. Awaiting WG review responses
SMWG Telecon - 27 June 2012
2012-0627-01 | Provide Hypothetical Plan section of Concept Green Book (amended on 2 August telecon to include trimming of all Info Entity descriptions) | EB | 2012-10-15 | CLOSED 10/1 | Originally 30 July-12
SMWG Telecon - 18 July 2012
2012-0718-01 | Reply to JPL comments on test report | TA | 2012-08-17 | CLOSED 22-Aug-12 | No response from JAXA. Comments assumed to be accepted and report will be recorded as such.
2012-0718-02 | Send risk to Erik about backward compatibility | JP | 2012-07-20 | CLOSED 20-Jul-12
2012-0718-03 | Update charter based on comments | EB | 2012-07-24 | CLOSED 26-Jul-12
2012-0718-04 | Check with Secretariat about maintaining SMWG archive | JP | 2012-07-20 | CLOSED 20-Jul-12
SMWG Telecon - 5 September 2012
2012-0905-01 | Minor tweaks to JAXA test report, send to Secretariat | EB |  | CLOSED 31Oct 13 | See 2012-1205-01. Received report from JAXA.
Cleveland 15-19 2012
2012-1015-01 | Generate FR type examples from classes in FR section | MG | pending | CLOSED 13 Dec 12 | Originally 15-Nov-12
2012-1016-01 | Trace IOAG SC services through the Extended FR Type diagram | JP | On hold pending feedback on definition of Forward and Return File, Validated Data Radiometric, and Delta DOR services | CLOSED | Originally 15-Nov-12. Review by W. Hell?
2012-1017-01 | Final version of the test report | TA | 2012-10-23 | CLOSED 23-Oct-12 | email to EB
2012-1017-02 | Evaluate alternatives to CSTS OID for FRs | EB | 2012-10-26 | CLOSED 9-Nov-12
2012-1018-01 | Produce WG schedule Gantt chart from Mindmap | EB | 2012-11-07 | CLOSED 1-Nov-12
2012-1018-02 | Review Characteristics of Events tech note and give comments to Colin | All WG members | 2013-06-20 | CLOSED 23-Jul-13 | Originally 15-Nov-12
SMWG Telecon - 5 December 2012
2012-1205-01 | Provide updated Prototype Test Report to EB | TA | 2013-05-01 | CLOSED 1 Oct 13
SMWG Telecon - 13 December 2012
2012-1213-01 | Generate FR type examples for the various TM sync and channel coding options | MG | 2013-01-31 |  | Originally due 17-Jan-13 Email of 30-Jan-13
SMWG Telecon - 17 January 2013
2013-0117-01 | Contact NavWG chair about addressing schema issues at Spring meeting | EB | 2013-01-18 | CLOSED | Email sent on 17 Jan 13
2013-0117-02 | Review the Information Entity descriptions in the Concept Green Book | All CSSMWG members | 2013-01-31 | CLOSED
Bordeaux 14-18 April 2013
2013-0415-01 | Update Enterprise model to reflect changes discussed during review (see meeting summary) | PP | 2013-06-07 | CLOSED 23-Jul-13 | Originally 1-Jun-13
2013-0415-02 | Add Event Sequence into Info Entities | JP | 2013-06-01 | CLOSED 29-May-13 | Included in ESCCS-SM Green Book draft of 29 May 2013
2013-0415-03 | Define frequency bands | MG, CC | 2013-06-20 | CLOSED 20-Jun-13 | Originally 7-May-13
2013-0415-04 | Does the schedule need a unique schedule identifier? | CC | 2013-06-20 | CLOSED 20-Jun-13 | Originally 7-May-13 It is not necessary
2013-0415-05 | Provide examples of use of additional parameters | MG | 2013-06-20 | CLOSED June 13 | Originally 7-May-13
2013-0415-06 | Produce draft model of extensibility for configuration profiles | AC | 2013-10-31 | CLOSED 31Oct 13 | Originally 1-Jun-13
2013-0415-07 | Clean up profile definition extensibility diagram | EB | 2013-05-07 | CLOSED 6 May
2013-0415-08 | Produce description of extensibility approach | JP | 2013-05-14 | CLOSED 29-May-13 | Included in ESCCS-SM Green Book draft of 29 May 2013
2013-0415-09 | Overlay new functional group concept over FR types | JP | 2013-05-07 | CLOSED 6-May-13
2013-0415-10 | Produce draft outline of Service Package Request/Service Package book | JP | 2013-10-28 | CLOSED 31Oct 13
2013-0415-11 | Produce outline of Planning Information book | CH | 2013-10-15 | CLOSED 14 Oct 13 | Originally 1 Aug 13
2013-0415-12 | produce draft outline of SA/Config Profile book | JP | 2013-10-31 | CLOSED 31Oct 13 | Originally 13-Aug-13
2013-0415-13 | Produce draft outline of trajectory prediction book | EB | 2014-11-01 | CLOSED 3-Apr-14 | Originally 17-Sept-13. Have by 2014 Fall meeting. OBE
2013-0415-14 | Produce draft outline of event sequence book | PP/EB | 2014-11-04 | CLOSED 3-NOV-14 | Originally 17-Sept-13.
2013-0415-15 | Review charter for updates and revise charter as needed | EB | 2013-06-04 | CLOSED 3-Jun-13
2013-0415-16 | Update Simple Schedule schema as Annex E | JP | 2013-06-07 | CLOSED 22 April
CSSMWG Telecon 7 May 2013
2013-0507-01 | Develop draft material regarding 3-way support in Enterprise model | PP | 2013-06-01 | CLOSED 20-Jun-13
2013-0507-02 | Explore turning FR Technote into a Yellow Book | JP | 2013-06-01 | CLOSED 31-May-13 | Draft Tech Note will be made available on CSSA Public CWE
CSSMWG Telecon 20 June 2013
2013-0620-01 | Review email from MG on frequency bands | all WG members | 2013-07-18 | CLOSED 23-Jul-13
2013-0620-02 | Check for time code format for SN and NEN | JP | 2013-07-18 | CLOSED 20-Jun-13 | see email of 20 June 2013.
2013-0620-03 | Review CSSMWG project definitions on CWE | all WG members | 2013-06-26 | CLOSED 23-Jul-13
SMWG Telecon - 1 August 2013
2013-0801-01 | Map deliverables onto info entities and lifecycle | JP | 2013-08-13 | CLOSED 12-AUG-13
2013-0801-02 | Review Enterprise Model in GB - does it say everything that we need it to say? | WG | 2013-08-13 | CLOSED
2013-0801-03 | Draft GB Exec Summary | EB | 2013-10-18 | CLOSED 14 Oct 13 | Outlined. Originally 13-Aug-13
2013-0801-04 | Flesh out 4.3 of Green Book | JP | 2013-10-15 | CLOSED | Partially done on 12-Aug-13. Originally 13-Aug-13. This section is being covered with the re-org or the GB.
SMWG Telecon - 13 August 2013
2013-0813-01 | Add Service combinations Magenta Book into Roadmap | EB | 2013-10-15 | CLOSED 14 Oct 13 | Outlined. Originally 10-Sep-13
SMWG Telecon - 17 September 2013
2013-0917-01 | Add Trajectory Prediction Blue Book into Roadmap | EB | 2013-10-15 | CLOSED 18Nov 13
SMWG Telecon - 15 October 2013
No action items
SAN ANTONIO 28-31 Oct 2013
2013-1028-01 | Increase font on the GB executive summary diagram | EB | 2013-11-07 | Closed 18-Nov-13
2013-1028-02 | Review GB to verify that the enterprise model concepts are described/referenced within the rest of the document. | JR | 2013-11-30 | CLOSED 27-Nov-13 | Original due date was 15-Nov-13.
2013-1028-03 | Coordinate Service planning information with MOIMS SM&C and SIS DTN | EB | 2014-10-31 | CLOSED 4-NOV-14
2013-1028-04 | Review GB for a final time and provide comments back to John before Jan 14 telecon. | ALL | 2014-01-08 | Closed 17-Jan-14 | Original due date was 14-Jan-14. Moved so that JP can incorporate changes before telecon
2013-1028-05 | Finalize GB SysML diagrams | JP, PP | 2013-12-09 | CLOSED 9-Dec-13
2013-1029-01 | Add SoS prototype test for unallocated/unused time. NASA will use SN TUT | MG, CA | 2013-11-25 | CLOSED 3-Dec-13
2013-1029-02 | Add the information entity referential model to the GB. | JP | 2013-12-09 | CLOSED 9-Dec-13
2013-1029-03 | Send draft Test Plan out for review | KT | 2014-01-14 | Closed 21-Jan-14 | Original due date was 15-Nov-13.
2013-1029-04 | Send draft Test Report out for review | KT | 2014-01-30 | Closed
2013-1029-05 | Walk through the Functional Groups to determine the different permutations of configuration profiles using the Service Catalog 1 | JP | 2014-03-31 | CLOSED 2-Apr-14
2013-1030-01 | Rework and update the words in the Mission Events section of the GB. Include only input planning | CH, EB | 2014-01-14 | Closed | Original due date was 28-Nov-13. EB to close the loop with Colin. EB will provide input to CH by Jan 31 and then will provide JP
2013-1030-02 | Look at the information entities to see if there are priorities within the information entities relative to the blue books that contains those information entities | EB | 2014-01-14 | Closed | Original due date was 28-Nov-13.
2013-1031-01 | Initial draft survey/compendium of visibility related events | CH, EB | 2014-01-30 | Closed | OBE, this will be addressed as the book is written
2013-1031-02 | Preliminary draft of the Planning Information Book | CH |  | CLOSED 1-Apr-15 | Orginial due date was 28-Feb-14.OBE, new approach see AI 2014-0402-04
2013-1031-03 | Create an abstract model of service package request components | EB | 2014-03-31 | CLOSED 3-Apr-14 | Initial cut was sent out 6 Dec. See AI 2014-0402-05
2013-1031-04 | Create an abstract model of service package result components | JP | 2014-03-31 | CLOSED 3-Apr-14 | See AI 2014-0402-06
2013-1031-05 | JAXA to determine if they can do prototype testing for the SP/SR BB | AT, EB | 2014-03-31 | CLOSED 12-May-14 | OBE. Learned Asama has left CSSM WG.
2013-1031-06 | Use projects and dates from CWE framework to update GB roadmap | JP | 2013-12-09 | Closed 18-Nov-13
2013-1031-07 | Develop engineering concepts for the Events Sequence | EB | 2014-03-31 | CLOSED 3-Apr-14 | AI 2014-0402-13 will include this AI - Close this one?
2013-1031-08 | Complete test report for B-1 | KT | 2013-11-30 | CLOSED 9-Dec-13 | Resend email. Done
SMWG Telecon - 19 November 2013
No Actions
SMWG Telecon - 10 December 2013
No Actions
SMWG Telecon - 22 January 2014
No Actions
SMWG Telecon - 28 January 2014
2014-0128-01 | Determine extensibility of each information entity | All WG | 2014-03-31 | CLOSED 3-Apr-14 | See AI 2014-0402-10?
2014-0128-02 | Review the Simple Schedule in preparation for Feb 11 Telecon | All WG | 2014-02-11 | Closed
SMWG Telecon - 4 March 2014
2014-0304-01 | See how the SoS schema handles the additionalParameter | JP | 2014-03-07 | Closed 5-March-14
2014-0304-02 | Update the SoS Annex B | JP | 2014-03-07 | Closed 5-March-14
2014-0304-03 | Update the ICS and the normative parameter description (null parameters) | CH | 2014-03-05 | Closed 4-March-14
SMWG Telecon - 18 March 2014
No Actions
Noordwijkerhout 31 Mar - 3 Apr 2014
2014-0401-01 | Provide the key reporting metrics or statistical characterizations, with definitions that are reported for each Agency’s networks’ service accounting for the customer (as it relates to the Service Package/Service agreement and recommendations for other metrics reported out weekly/monthly, etc). | EB | 2016-06-30 | Closed 23-Jun-16 | MG, JPC, MU and CC (for CNES) presented/discussed their agency's service accountability data at the London meeting. Erik will provide the DSN at a later date.Action closed for the others on 13-Nov-14.
2014-0402-03 | Planning Information Draft outline of communications geometry Preliminary draft-output only | CH | 2014-06-30 | CLOSED 15 July 2014 | Original date was April 30
2014-0402-04 | Update Generic File Transfer Concept Paper | CH | 2014-06-30 | CLOSED 10 July 2014 | Original date was April 30
2014-0402-05 | Service Package Request management component writeup | EB | 2015-03-10 | Closed 10-Mar-15 | A presentation was completed on 8 May. Need to complete writeup | x
2014-0402-06 | Service Package management component writeup | JP | 2014-05-05 | CLOSED 5-May-14
2014-0402-07 | Generic File Transfer Charter update proposal | EB | 2014-05-20 | CLOSED 2-June-14
2014-0402-08 | Simple Schedule of Services Test Report | KT,MG | 2014-06-02 | CLOSED 2-June-14
2014-0402-09 | Generic File Transfer Project definition | EB | 2014-10-07 | CLOSED 6-OCT-14 | Original date was June 30.
2014-0402-10 | Service Agreement FG definitions, FG specializations, IOAG Services mapped to FGs | JP,AC | 2014-07-01 | CLOSED 1 July 2014
2014-0402-11 | Simple Schedule of Services RID Processing | CH | 2014-11-14 | CLOSED 11-Nov-14 | This date is a placeholder. Date not known until doc release
2014-0402-12 | Trajectory Prediction Draft presentation | Jessica R | 2014-08-05 | CLOSED 13 Aug 2014
2014-0402-13 | Event Sequence Extensibility/component presentation | PP | 2014-08-26 | CLOSED 26-Aug-14 | Actionee changed from EB to PP. Draft presentation sent out on 25-Aug. Presented on 26-Aug.
2014-0402-14 | Define the set of concerns to be coordinated between recommendation development activities and develop a tracking mechanism. Draft Presentation | EB | 2014-07-28 | CLOSED 12 Aug 2014
2014-0402-15 | FG, FRs and IOAG svcs mapping to Service Agreement and service configuration profile | JP,AC | 2014-10-07 | CLOSED 6-OCT-14
2014-0402-16 | Planning Information - Complete draft white book including request | CH | 2014-11-12 | CLOSED 12-Nov-14 | Original due date was 3-Nov-14
2014-0402-17 | Generic File Transfer Preliminary draft white book | CH |  | CLOSE see subsequent action 2014-1114-11 | Will reschedule at the London Meeting. Original due date was 3-Nov-14
2014-0402-18 | Trajectory Prediction Draft white Book (Outline) | Jessica R | 2014-11-10 | CLOSED 12-Nov-14
2014-0402-19 | Event Sequence preliminary draft of book | EB | 2014-11-03 | CLOSED 9/25/2014 | Duplicate of AI 2013-0415-14
2014-0402-20 | Update green book post CESG review | JP | 2014-08-10 | CLOSED 20-Aug-14 | Made all changes but final date will depend on response from SLS area director. SLS area director sent email that he was satisfied with all proposed dispositions.
2014-0402-21 | Remove Trajectory project from CWE framework | EB | 2014-06-30 | CLOSED 28-Apr-14 | OBE - it was determined that the BB needs to be developed
2014-0402-22 | Update green book to reflect Trajectory prediction book deletion | JP | 2014-04-28 | CLOSED 16-Apr-14 | Update was delivered but it was determined that the BB needs to be developed
2014-0402-23 | Update SoS SANA section | CH | 2014-04-28 | CLOSED 28-Apr-14
SMWG Telecon - 28 April 2014
2014-0428-01 | Discuss version info for NDM with Nav WG | EB | 2014-05-14 | CLOSED 8-MAY-14 | JP had a meeting with D. Barry
2014-0428-02 | Update SoS | CH | 2014-04-29 | CLOSED 28-Apr-14
2014-0428-03 | Update Green book - new diagram, add trajectory prediction back in, etc. | JP | 2014-04-29 | CLOSED 28-Apr-14
SMWG Telecon - 14 May 2014
2014-0514-01 | Provide comments to the Service Package writeup and the Service Package Request writeup. | All | 2014-05-30 | CLOSED 3-June-14
SMWG Telecon - 3 June 2014
2014-0603-01 | Review the SoS Prototype Test Plan/Report and provide comments | All | 2014-08-26 | CLOSED 26-Aug-14 | Originally due 15 July 2014. Conclusion is that the test report is in good shape and unless there are significant RIDs that modify the schedule of services recommendation (as a result of the upcoming agency reviews) the document will essentially be used as is for blue book candidacy
2014-0603-02 | Provide write up on metadata for delta dor use case re: service package and service request | EB | 2017-04-15 | Closed OBE | With regard to DDOR service and a mission using multiple agency TTC networks. Will reschedule at London Meeting. Original due date was 4-Nov-14. See workplan from Cleveland meetings action to conclude 1-Aug-16. As of 29-Aug-16, the response for the lifecycle and info entities is sufficient until Spring 2017 meeting
2014-0603-03 | Bring in summary of scheduling flexibilities and constraints from the SN | JP and JPC | 2014-06-24 | CLOSED 24 24-Jun-14
SMWG Telecon - 24 June 2014
2014-0624-01 | Propose namespace architecture for CSSA schemas within CCSDS namespace | JVP, AC | 2014-12-15 | CLOSED 12-Jan-15 | Will be ready for a discussion in London. Original date 10-Nov-14
SMWG Telecon - 15 July 2014
2014-0715-01 | Review the Terrestrial File Transfer Green Book and provide comments | All | 2014-09-25 | CLOSED 25-SEPT-14 | Original date was 5-Aug
2014-0715-02 | Review the draft Planning Data Formats book and provide comments | All | 2014-09-25 | CLOSED 25-SEPT-14 | Orignal date was 25-Aug. Received comments from JPC, EB
SMWG Telecon - 13 August 2014
2014-0813-01 | Look at the updated simple schedule of services recommendation and follow-up re CESG poll condition removal | EB | 2014-08-15 | CLOSED 14-Aug-14
2014-0813-02 | Determine how the NDM does or does not handle "layered" trajectories, discuss with navigation working group chair as appropriate | EB | 2014-09-16 | CLOSED 25-Aug-14 | Originally due 16-Sept. Layered=using a different/unique reference system.
SMWG Telecon - 26 August 2014
2014-0826-01 | A request to the working group membership to check with their appropriate agency representatives with regard to security considerations for protocol selection for GFT; Likely candidate is WebDav | All | 2014-10-04 | CLOSED 6-OCT-14
2014-0826-02 | Follow up with navigation working group chair as to possibility for expression of “layered” (i.e. multi-reference center) sets of trajectories/ephemerides | EB | 2014-09-25 | CLOSED 9/25/2014
2014-0826-03 | Talk with appropriate agency representatives and provide inputs with respect to radio frequency interference (RFI), data volume/data rate estimation, and cost estimate data inputs for consideration in the draft Planning Information recommendation | ALL | 2015-01-27 | Closed 27-Jan-15 | Original date was London 2014 meeting. Summary of events and parameters/data exchanged. Provide to CH so he can put it in the draft. CNES, NASA SN, NASA DSN RFI inputs still pending. AI will close on 27 Jan.
SMWG Telecon - 25 September 2014
No Actions
SMWG Telecon - 07 October 2014
No Actions
SMWG Telecon - 04 November 2014
No Actions
London - 10-14 November 2014
2014-1110-01 | Put all RIDs in one type of format file to pull all the different formats together | CH |  | Closed 11-Nov-14
2014-1110-02 | Create a diagram to be included in the Simple Schedule introduction to clarify the context of the document (possibly by using the life-cycle diagram) | MG | 2014-12-09 | CLOSED 02-Jan-15
2014-1110-03 | Look at the test report and provide any comments on mapping to SN or NEN items for EUMETSAT RID HH004. (Perform analysis relative to test report and as to abliity to map to proposed standard.) | JPC | 2014-12-09 | CLOSED
2014-1110-04 | Send SoS test report to Hayley Higgins | KT | 2014-11-10 | Closed 10-Nov-14
2014-1110-05 | Capture all abbreviations in the SoS | KT | 2014-11-10 | Closed 10-Nov-14
2014-1110-06 | Update the diagram according to CNES RID JMS11 | MG | 2014-12-09 | CLOSED 02-Jan-15
2014-1111-01 | Include in test report that we will not prototype the nesting of AdditionalParameter | MG,KT | 2014-12-09 | CLOSED 02-Jan-15
2014-1111-02 | RE: RID ESA-ESA 11 Think through and come up with an answer. Consider if an optional parameter should be added to the Activity class to indicate the level of commitment to the activity. | CH | 2014-11-21 | CLOSED 19-Nov-14
2014-1111-03 | Look up the frequency for UHF and VHF for the SoS | CH | 2014-12-09 | CLOSED 02-Jan-15
2014-1111-04 | Clarify the note to indicate the information bookmarking function in the case of the antenna free time in para 3.4.2.2. See NASA RID Antenna Freetime | MG | 2014-12-09 | CLOSED 02-Jan-15
2014-1112-01 | Produce text re SANA policy that can be re-used for each CSS area blue book | EB, MdG | 2014-12-01 | CLOSED 08-Dec-14 | Urgent
2014-1112-02 | Provide examples of recurrent requests for your agency | CC | 2015-03-09 | Closed | Original date was 13 Jan 2015. Waiting for MU's inputs. MG and CC provided comments | X
2014-1113-01 | Produce a graphical model based on the green book planning request | EB | 2015-03-10 | Closed- OBE 10-Mar-15 | Original date was 9 Dec 2014. This may be over come by events of the request engineering group efforts | X
2014-1113-02 | Capture the refined details of the planning request using use cases. | CH | 2014-12-09 | CLOSED
2014-1113-03 | Perform an analysis of the accountability data from each of the agencies | JR | 2015-03-21 | Closed
2014-1113-04 | Do a proof of concept for 1) config profile out of service profiles 2) pare down TC/TM SLE-Plus profile (Bake-off) | JVP, AC | 2015-03-23 | Closed | Progress report provided. Futher analysis still pending. JVP is determining what to pare down. | X
2014-1113-05 | Develop a standard header | CH | 2014-12-09 | CLOSED 18-Nov-14
2014-1114-01 | Develop the SANA registry considerations/policy | EB | 2015-01-13 | CLOSED | Define the namespace for the Simple Schedule. Duplicate
2014-1114-02 | Sort out the abstract request common type for the planning data format | EB, CH, JPC, JVP. MG | 2015-03-23 | Closed | JPC sent out slides around Dec 10. Sub team will discuss and provide inputs at the Spring meeting | X
2014-1114-03 | Define the remaining event definitions for the planning data format | All | 2015-03-23 | Closed -OBE | Original date was 13 Jan 2015. Review the current planning information draft and see if there are any event definitions missions. Check with Colin. | X
2014-1114-04 | Check communition geometry events for the planning data format | All | 2015-03-09 | Closed 10-Mar-15 | Original date was 13 Jan 2015. Review the current planning information draft and provide input on current communication geometry event definitions. EB will create a spreadsheet to collect input
2014-1114-05 | Update planning data format white book | CH | 2015-08-31
2014-1114-06 | Complete the service request component write-up | EB, JPC | 2015-03-21 | Closed -OBE
2014-1114-07 | Flexibility and Constraints extensibility schema for the service request | JVP | 2015-03-21 | Closed -OBE
2014-1114-08 | Service request vs planning request alignment | JPC, CH, JVP | 2015-03-21 | Closed -OBE
2014-1114-10 | First draft (white book) of the Trajectory Prediction book | JR | 2015-03-21 | Closed
2014-1114-11 | List of questions for the Generic File Transfer preliminary draft | CH | 2015-03-21 | Closed 24-Mar-15 | Original due date was 27-Jan.
2014-1114-12 | First draft (white book) of the Event Sequence | PP, EB | 2015-03-21 | Closed 10-Mar-15
2014-1114-13 | Strawman on service package result structuring | JPC, JVP | Fall 2015 meeting | Closed | Originally due 15 March 2015.
SMWG Telecon - 9 December 2014
2014-1209-1 | Double check the SOS RID disposition report prior to release to RID submitters | EB | 2014-12-15 | Closed
2014-1209-2 | Process all instances of “network” and see where change to “Provider CSSS” does or does not make sense | CH |  | Closed | To be consistent with CSA ADD
2014-1209-3 | Update the revised the antenna free-time diagram re “network” term as determined by C. Haddow | MG | 2015-01-16 | Closed 27-Jan-15 | Original date was 13 Jan 2015. Ask Colin if MG needs to put it directly in the document or just send it to Colin
2014-1209-4 | Wordsmith the text for the antenna free time updates from M. Gnat | CH |  | Closed
2014-1209-5 | Provide comments/analysis on each info entity vs. the proposed common request header | EB | 2015-01-13 | CLOSED 12-Jan-15 | Basic idea is good
SMWG Telecon - 13 January 2015
2015-0113-1 | Provide exact report section reference to close out response for consolidated RID CSSM-050 | JPC | 2015-01-27 | Closed 27-Jan-15
2015-0113-2 | Look at the two SoS versions, R1 for agency review and current updated book, and render an opinion as to the need for prototyping | EB | 2015-02-19 | Closed | If prototyping needed MG will generate an instance document and send to EB to determine if what the originator of message meant is interpreted properly by recipient. Original due date was 27-Jan. Further analysis/crosscheck needs to be done with the various values that are potentially co-constraining to ensure that all combinations are reasonable | X
2015-0113-3 | Produce the 902.x numbers for the suite of SM books given that .1 is SoS, .2 is Planning Information and .3 is the Trajectory Predictions BBs, with all subsequent numbers based on the roadmap order per the GB | MG | 2015-01-27 | Closed 27-Jan-15 | Uploaded to CWE
2015-0113-4 | Add tab for book numbers in inter-recommendation spreadsheet | KT | 2015-01-27 | Closed 27-Jan-15
2015-0113-5 | Review Erik's standard header vs information entities analysis spreadsheet and provide comments | All | 2015-02-23 | Closed | "status" could be left up to each information entitiy to define; should be a string? "version #" seen as being applicable for all info entities. Original due date was 27-Jan. See email on 12-Jan-15, subject "Response to AI2014-1209-5". EB's spreadsheet will be updated with analysis produced to date and circulated to the WG for comment at the Feb 23 telecon | X
2015-0113-6 | Review and provide comments on schema namespace charts prepared by JVP | All | 2015-03-23 | Closed-OBE | Original due date was 27-Jan.
SMWG Telecon - 27 January 2015
2015-0127-1 | Provide examples that utilize the proposed namespace structuring | EB, JVP, AC | 2015-03-23 | Closed
2015-0127-2 | Upload SN presentation on RFI reports to the CWE | JPC | 2015-02-10 | Closed!!
SMWG Telecon - 10 February 2015
2015-0210-1 | Create spreadsheet to collect event definitions and geometry events for planning data format | EB | 2015-02-13 | Closed | We will circulate this spreadsheet and discuss in 2 weeks on March 9. See AI 2014-11-03 and -04
Pasadena - 23-27 March 2015
2015-0323-1 | Prepare a response to DDor WG to mesh their needs into the CSSM Service Request | EB, JPC | 2016-10-18 | Closed | Would like to get this to the DDor WG sooner than later to get their feed back.Would like to get this to the DDor WG sooner than later to get their feed back. Will discuss at the 18-Jun meeting to see if we are close, (Note this topic was delayed from the 18-Jun agenda). JPC input complete.EB to write and send response. See workplan from Cleveland meetings action to conclude 1-Aug-16.
2015-0325-1 | Review the CSTS book while CSS-CSTS members will look at the Event Sequence book | EB, PP, HD | 2015-09-01 | CLOSED 8/25/15 | Administratively closed. See Ais 2015-0825-1 and 2015-0825-2.
2015-0325-2 | Think about the Trajectory Prediction approach and provide a solution - Bilateral? | EB, CH, JR | 2015-05-05 | Closed 5-May-15 | Jessica will send out an email concerning the approach and get the WG agreement.
2015-0325-3 | Add namespaces to the SoS schema | JVP | 2015-04-13 | Closed 14-Apr-15
2015-0325-4 | Send email out to JVP capturing what is needed for the SoS schema namespace | CH |  | Closed
2015-0325-5 | Change labels, include a referential framework and create relationships with JP's servicepackagerequest diagram | JPC |  | Closed
2015-0325-6 | Produce a overview diagram showing how the functional resources model is managed within CSS including engineering maintenance, release to SANA, for registered model | JVP, AC, HD | Fall 2015 meeting | Closed | Basic cartoon that CMC can understand
2015-0326-1 | Convert the document relationship model from visio to ppt | MC |  | Closed
2015-0326-2 | Revise Stnd Header Analysis spreadsheet for inter-relation tracker spreadsheet | EB | 2015-04-17 | Closed
2015-0326-3 | Fill the Class tab within the inter-relationship tracker for the SoS | KT |  | Closed
2015-0326-4 | Get a new number series for the Generic File Transfer book from Tom | KT |  | Closed | JVP will check emails to see if he got one from Tom
2015-0326-5 | Create "container" sub folders to hold the latest version of each model referenced in the inter-relationship tracker | KT |  | Closed
2015-0326-6 | Provide a first cut of metrics of service definitions for telemetry command data accountability | EB | Fall 2015 meeting | Closed | Replaced with 2015-0327-19
2015-0327-1 | Provide HK with each agency’s Service Catalog or similar information | All | 2015-06-25 | Closed | JPC will provide additional information. CC provided input on 24 Jun. This was previously due 15-May-15
2015-0327-2 | Is range rate required for the communication geometry | EB, CH, MU | 2015-06-02 | Closed | Original due date was 5 May. Change in range rate - m/s/s?
2015-0327-3 | Investigate use of IAU for Celestial Body naming | CH | 2015-04-13 | Closed 2-Apr-15
2015-0327-4 | State use cases for forward and return file transfer | EB | Fall 2015 meeting | Closed | OBE
2015-0327-5 | Update Header Analysis tab in inter-recommendation tracker | KT | 2015-04-13 | Closed 5-May-15
2015-0327-6 | Finalize SoS book and schema | CH, JVP | 2015-04-13 | Closed | Send email to SANA to request URLs for registries. Colin will look over JVPs changes to the document.
2015-0327-7 | Develop 1st cut abstract service request model | CH, JPC | 2015-04-13 | Closed 14-Apr-15
2015-0327-8 | Analyze DDOR service request and indicate mapping to CSSM per Green Book info entities | EB, JPC | 2015-06-02 | CLOSED 16-Jun-15 | JPC will do mapping
2015-0327-9 | Add diagrams into model and class tabs in inter-recommendation tracker | KT | Fall 2015 meeting | Closed | Was due 2-May-15
2015-0327-10 | Analyze the abstract service request model re: targets (planning/service request) | CH, JPC, EB, MG | 2015-07-15 | Closed | JPC, CH - See meeting summary to review. Need a splinter meeting on June 30 to get this effort going again.
2015-0327-11 | Analyze DDOR service request and indicate mapping to CSSM re: abstract service request | EB | 2016-02-02 | CLOSED | EB agreed to provide mapping verbiage and some suggested instance output to the DDOR WG. Was due 25-May-15. Related to 2015-0323-1. EB will do the mapping.
2015-0327-12 | Update table of contents comparison in inter-recommendation tracker | KT | 2015-05-29 | Closed 27-May-15
2015-0327-13 | Identify Planning Book test cases | EB, MG | 2015-07-15 | Closed | Was due 29-May-15
2015-0327-14 | Develop Planning Book test plan white book based on test cases | KT | Fall 2015 meeting | Closed | Was due 15-Jun-15. Use the comm geometry test cases.
2015-0327-15 | Finalize abstract service request model | EB |  | Closed | Was due 22-Jun-15. EB: To update the mindmap for a high level model. | X
2015-0327-16 | Research c 2012 service catalog material. Collect examples and develop preliminary comparative analysis. | HK | Fall 2015 meeting | Closed | Received inputs from NASA, ESA and CNES. Will be working on action 2015-0327-16 in the week beginning 27 July with the aim of having an initial analysis of the service catalog material by 31 July. Was due 28 August 2015. | X
2015-0327-17 | Complete Planning Book draft Red 1 | CH | Fall 2015 meeting | Closed | Was due 31 Aug
2015-0327-18 | Complete Trajectory Prediction draft white book | JR | Fall 2015 meeting | Closed | Was due 21 Sep
2015-0327-19 | Develop initial list of accountability metrics for services for accountability book development | EB | 2016-03-30 | Closed see Cleveland Action | Per IOAG service catalog? Or more abstract; at a minimum, TLM, CMD, RNG
2015-0327-20 | Complete event sequence draft white book | PP | Fall 2015 meeting | Close | Was due 30-Oct
2015-0327-21 | Develop service profiles for Service Agreement/Config Profile development | AC, JVP | Fall 2015 meeting | Closed | All combinations of TLM, CMD, RNG, DDOR. What about MD-CSTS?CS-CSTS? Provide a plan/guidance.
2015-0327-22 | Develop outline of Service Agreement/Config Profile whitebook | JVP | 2015-10-30 | Closed 30-Sept-15
2015-0327-23 | Study and outline Trajectory test plan based on NAVWG input | EB, KT | Fall 2015 meeting | Closed OBE | Get NDM test plan, discuss with Dave Berry. KT will send EB test plan.
2015-0327-24 | Develop Service Package Request outline consistent with abstract engineering | JPC, EB, CH, MG, JVP | Fall 2015 meeting | Closed |  | X
2015-0327-25 | Develop Service Package (result) outline | JPC, EB, CH, MG, JVP | Fall 2015 meeting | Closed |  | X
2015-0327-26 | Develop TGFT draft white book -- protocol emphasis (minus meta-data) | CH | Fall 2015 meeting | Closed
2015-0327-27 | Draft proposal options for management service concept | AC, UM-W | Fall 2015 meeting | Closed | REST, SOAP, etc? What is good about the approach, what is bad, (ie a bit of trade study). Was 10/30/2015
SMWG Telecon - 14 April 2015
2015-0414-1 | Review and provide comments to SoS and Standard Header definitions | All | 2015-04-17 | Closed
2015-0414-2 | Research and create SANA registries for the CSSM schemas and data | CH, JVP, EB | 2015-07-28 | Closed | Closed except for the creation of the registries
SMWG Telecon - 2 June 2015 Telecon
2015-0602-1 | Check the semantics of the Nav Stds multiple segments and start/end time and report to WG as it applies to the Trajectory Prediction Format | JR | 2015-10-13 | Closed | Due date was 15-Sep
42290
No Actions taken for this telecon
SMWG Telecon - 16 July 2015 Telecon
2015-0716-1 | Provide updated text for SANA section of SoS concerning Site and Apertures registry | EB | 2015-07-22 | Closed 27-Jul-15
2015-0716-2 | Circulate draft YB on updated registry management policy to the working group | EB | 2015-07-20 | Closed
2015-0716-3 | Review the "E2.5 Use Of Values Not Contained in The Registries" paragraph in the SoS and provide comments back to CH | All | 2015-07-27 | Closed
2015-0716-4 | Identify any management considerations with regard to CSTS Forward Frame | JVP | 2015-07-28 | Closed 27-Jul-15
SMWG Telecon - 28 July 2015 Telecon
2015-0728-1 | Request the schema and the "Sites and Apertures" registries | EB | 2015-08-04 | Closed
2015-0728-2 | Determine if a namespace registry should be created. Discuss with SEA | EB | 2016-03-30 | Closed - OBE | Originally due 11 August 2015. | X
SMWG Telecon - 11 August 2015 Telecon
2015-0811-1 | Prepare a preliminary draft agenda for the fall meeting | EB | 2015-09-15 | Closed 14-Sep-15
SMWG Telecon - 25 August 2015 Telecon
2015-0825-1 | (CSSMWG) Review pertientent material for SC-CSTS | EB, PP,JVP, CH | 2015-10-12 | Closed | Original due date was 29-Sept-15
2015-0825-2 | (CSTSWG) Review Event Sequence White Book | HD, WH, MDG | 2015-10-12 | Closed | Original due date was 25-Sept-16
SMWG Telecon - 15 September 2015 Telecon
No actions
SMWG Telecon - 29 September 2015 Telecon
No actions
SMWG Telecon - 13 October 2015 Telecon
2015-1013-1 | Follow up on schema registration for SoS book | EB | 2015-12-01 | Closed | See 2015-1112-3
2015-1013-2 | Contact David Berry (NAVWG) concerning the Trajectory Prediction book dependency with the OEM | EB | 2015-10-29 | Closed
SMWG Telecon - 27 October 2015 Telecon
No actions
SMWG Telecon - Darmstadt 9-12 November 2015 Meeting
2015-1112-1 | Get production copy of the Concept Book from Tom | JVP |  | Closed
2015-1112-2 | Update the Concept Book for the revision of the service management request | EB | 2016-06-27 | Closed | See Action 2016-0408-20
2015-1112-3 | Hold telecon with SANA to get registries created to finalize the SoS | EB, CH | 2015-12-04 | Closed
2015-1112-4 | Update highly abstract model re:management service considerations | EB | 2016-02-29 | Closed | Revisit after SMURF discussion | x
2015-1112-5 | Update the SM Request format draft book | CH | 2015-12-08 | Closed | Date set for the first telecon after Darmstadt
2015-1112-6 | Update DDOR CSSM service package mapping based on latest service request definitions | JPC | 2016-02-02 | Closed | Presentation uploaded to the CWE. | X
2015-1112-7 | DDOR WG to send feedback on inputs and also provide some more complicated examples of DDOR requests | EB, DDOR | 2016-08-31 | Closed 29-Aug-2016 | Closed administratively. See AI 2015-0323-1
2015-1112-8 | Develop Service Package result draft write-up | MG,JPC | 2016-03-30 | Closed | JPC will write and MG will help. See Cleveland Action | X
2015-1112-9 | Update Planning book to make basic event definition more "universal" for further input to NAVWG and also some editoral notes | CH | 2015-12-07 | Closed
2015-1112-10 | Develop the Planning Data Format test descriptions | MG, KT | 2016-03-30 | Closed
2015-1112-11 | Complete TGFT Draft White Book | CH | 2016-08-30 | Closed | Mostly this is about figuring out what to do for XFDU. See Cleveland Actions
2015-1112-12 | Make changes discussed at Darmstadt and make materal available for inclusion in the SM Request Book | JR | 2016-01-19 | Closed 10-Jan-16 |  | X
2015-1112-13 | Produce draft SM Request Format (SMURF) | CH | 2016-03-30 | Closed
2015-1112-14 | Create SM Request Format Test Plan outline and test cases | KT, MG, EB, CH | 2016-03-30 | Closed | See Cleveland meeting actions
2015-1112-15 | Further analysis re: "hiding" port complexity and how to present in the Service Agreement/Config Profile recommended standard | AC, JVP | 2016-03-30 | Closed
2015-1112-16 | Complete draft white book of Event Sequence | PP, EB | 2018-04-02
2015-1112-17 | Develop strawman outline of Service Catalog "magenta-ish" book | HK | 2016-03-30 | Closed
2015-1112-18 | Develop draft concept for extensible management service | AC, UMW | 2016-03-30 | Closed | See Cleveland meeting actions
2015-1112-19 | Abstract B1 management service | EB | 2016-01-19 | Closed 10-Jan-16 |  | X
2015-1112-20 | Develop high-level management service requirements | AC, UMW | 2016-03-30 | Closed | Original date was 1-Feb-16. Erik to Send Anthony the presention on B-1 MGMT abstraction
2015-1112-21 | Develop TGFT Test Plan | KT, CC,MG, HW | 2017-05-01 | Closed See 2016-1021-22 | Original date was 3 Oct 16. Karen will organize a telecon to discuss the development of this document
2015-1112-22 | Develop XML Schema for Planning Book | UMW, AC, CH, JVP | 2016-05-02 | Closed | Original date was 29-Jan-16. Update XML schema based on input from Cleveland
2015-1112-23 | Develop XFDU usage overview for TGFT | CH, JR | 2016-06-30 | Closed | Original date was 16-Feb-16. present to WG. See Action 2016-0408-29
2015-1112-24 | Coordinate with SEA re: definition of Svc Site & Aperture registry | EB | 2016-01-18 | Closed 19-Jan-16 |  | X
SMWG Telecon - 08 December 2015 Telecon
2015-1208-1 | Determine how to define the return Trajectory Prediction format as a result of the TP request (the information entities, XML format, header, etc.) | EB, CH, JVP, JR | 2016-02-02 | Closed | Need to look at what is returned for trajectories information for queries. Might be missing a future book (dealing with trajectory packaging in general). Need to examine what current Blue-1 does with regard to extending trajectory prediction and the information that is returned and determine if some sort of recommendation (but not trajectory prediction per se) is needed. This ties back to general action of summarizing current B-1 management service -- see response in email fromi EB. | X
2015-1208-2 | Follow up with Marc Blanchet to determine the timeline for the SANA registries creation. | EB | 2016-01-19 | Closed 10-Dec-15 | we can expect the SANA registries for the Simple Schedule Format to be created by late January 2016 at the latest and possibly by mid-January 2016 | X
2015-1208-3 | Review SMURF White book in preparation for review | All | 2016-02-02 | Closed | Will be reviewed at the 19-Jan and 2-Feb telecons | X
2015-1208-4 | Review the Planning Data Format White book and provide comments to CH. | All | 2016-02-02 | Closed | Will be reviewed at the 19-Jan telecon | X
SMWG Telecon - 19 January 2016 Telecon
2016-0119-1 | Update SoS to include the RMP yellow book reference | EB | 2016-09-10 | Closed 23-Sept-16 | Original date was 2-Feb-16. EB does have latest book from TG.
SMWG Telecon - 02 February 2016 Telecon
2016-0202-1 | Send AC the B-1 mgmt abstraction slides | EB | 2016-02-03 | Closed
2016-0202-2 | Check the enhanced constraints defintion in the SMURF and be prepared to discuss fit realtive to your agency/operation. | All | 2016-03-30 | Closed | Comment can also be sent to C. Haddow at your earliest opportunity.
SMWG Meeting - Cleveland 4-8 April 2016 Meeting
2016-0405-1 | Review the Concept Book for Service Agreement and Configuration Profile extensibility and check for consistency with the current concepts | MG | 2017-05-08 | Closed | Original date 10-Oct-16. "PLANNING_INFO" does not align with current information entities in Green Book. Talk to AC about taking over role.
2016-0406-1 | Arrange Management Service Splinter Group telecon and determine further planning | EB | 2016-04-18 | Closed
2016-0407-1 | Add something to the extensibiiity technique model within the inter-recommendation doc about accomodating agency-specific extensions such as what was shown in the DSN SoS presentation example | EB | 2016-09-30 | Closed 23-Sept-16 | Original date was 1 Sep 16
2016-0407-2 | Update SM Lifecycle Model with latest document plan | EB | 2017-05-02 | Closed | Original date 30-Aug-16 Will update with DDOR later. Closed with new action 2017-0512-31
2016-0407-3 | Update Abstract Service Request Model | EB | 9/1/2/16 | Closed | OBE | X
2016-0407-4 | Clean up SANA Registry Types in inter-recommendation spreadsheet | EB | 2016-09-30 | Closed 3-Oct-16 | Original date was 1 Sep 16
2016-0408-1 | Update SoS with overview diagram that was produced by Marcin | EB | 2016-09-10 | Closed | Original date 1-Jun-16. Change Document reference model to show PDF was changed to PIF
2016-0408-2 | Tweek/update SoS registry text, including SANA URLs | EB | 2016-09-10 | Closed 23-Sept-16 | Original date 1-Jun-16
2016-0408-3 | Check SoS Annex A for proper list of information entities | EB | 2016-09-10 | Closed 23-Sept-16 | Original date 1-Jun-16
2016-0408-4 | Develop sketch of DDOR SM lifecycle model | EB | 2016-08-31 | Closed | Original date was 30 Jun 16
2016-0408-5 | Based on DDOR sketch of lifecycle, indicate how the SM information entitiies do (or do not) support this | EB | 2016-09-30 | Closed | Original date was 1 Aug 16. Assess closing this by determining if 2016-0408-4 included this.
2016-0408-6 | Arrange a splinter telecon to discuss what is intended to be in the SP result | EB, MG, CH, JPC, JVP, AC | 2016-04-18 | Closed
2016-0408-7 | Service Package Result draft write-up | JPC | 2016-10-05 | Closed
2016-0408-8 | Look at draft Planning Information Prototype test plan and provide comments/ review | EB, CH | 2016-10-18 | Closed | Original date 27-Jun-16. Check with CH about new date
2016-0408-9 | Secure PIF prototyping resources | CH, EB | 2016-10-21 | Closed
2016-0408-10 | Revise draft SMURF | CH | 2016-10-21 | Closed See 2016-1021-17 | Confirm due date with CH
2016-0408-11 | Produce outline of SMURF test case/plan | EB, KT, MG | 2017-05-02 | Closed See 2016-1021-19 | Original date was 3 Oct 16
2016-0408-12 | Develop Service profiles for SA/CP Development | AC JVP | 2016-10-18 | Closed See 2016-1021-23 | TLM, CMD, RNG, DDOR, All combos, MD-CSTS? SC-CSTS? Provide a plan/guidance
2016-0408-13 | Revise draft SA/CP book to remove temporial aspects - more of "static" recommendation. Coordinate with event sequence development | JVP, PP | TBD | Closed OBE | Original date 30-Sep-16 Clarify the coordination with event sequence development with JVP and who should be involved
2016-0408-14 | Provide recommendation as to example profiles to mock-up based on IOAG modulation recommendations | EB | 2016-10-18 | Closed | Original date 27-May-16
2016-0408-15 | Event Sequence complete draft White Book development | PP | TBD | Closed | Duplicate
2016-0408-16 | OIDs/FRs vs Event Sequences | EB, PP | Fall 17 Meeting | Closed | Original date was 10 Oct 16. Still need to work on connection ot configuration profile/functional resources. Closed for new action 2017-0512-27
2016-0408-17 | Develop examples of event sequences based on concept being worked in DSN with regard to relacing the (current) temporal aspects of the CP | EB | 2016-10-18 | Closed See 2016-1021-27 | Original date 27-May-16.
2016-0408-18 | Develop initial list of accountability metrics for services per IOAG service catalog or more abstract; at a minimum | EB | 2017-05-02 | Closed Admin | Original date 3 Oct 16.
2016-0408-19 | Update strawman Service Catalog based on Cleveland meetings input | HK | 2016-08-31 | Closed | Original date 30 June 16
2016-0408-20 | Revise Concept Book Updates per comments from Cleveland Mtg. | EB | 2016-10-18 | Close See 2016-1021-26 | Original date 27-Jun-16
2016-0408-21 | Go through and identify the info entities given latest developments and proposed info entities to working group | EB | 2016-08-17 | Closed | Original date 17-May-16. See email 10-Aug-2016. Inputs requested from WG members. To be discussed at 13-Sept-2016 telecon
2016-0408-22 | Propose definition for sun alignment angle for planning book | EB | 2016-05-30 | Closed?
2016-0408-23 | Look into different "delete" semantics and report back to WG (SMURF) | CH | 2016-10-18 | Closed | Original date 28-Jun-16. Check with CH on due date change
2016-0408-24 | Change title and references of Planning Data Format to Planning Information Format | CH, KT, GN | 2016-09-13 | Closed | Original date 30-May-16. Check with Colin about due date. Verified that PDF was changed to PIF throughout test plan.
2016-0408-25 | Add that all of the other success criteria are conducted in the context of a realistic/real-world use case to the PIF test plan | KT, GN | 2016-05-30 | Closed 6-Jun-16 | Verified that statement was added at Cleveland Meeting. See section 2.3
2016-0408-26 | Further develop an updated CWE directory structure and implement | KT | 2016-10-18 | Closed See 2016-1020-13 | Original date was 7-Jun-16
2016-0408-27 | Update XML Schema for Planning Book based on input from Cleveland Meeting | UMW, JVP | 2016-07-31 | Closed | Original date 2-May-16 Check with UMW about due date since John is no longer working it.
2016-0408-28 | Complete TGFT draft White book | CH | 2017-04-15 | Closed See 2016-1021-18 | Original date 30 Aug 16.
2016-0408-29 | Add overview of XFDU usage to TGFT | CH | 2017-05-02 | Closed | Original date 30-Jun-16. Check with CH on due date change. Closed with new action 2017-0512-10
2016-0408-30 | Update inter-recommendation tracking spreadsheet based on Cleveland meeting | EB, KT | 2016-10-18 | Closed
SMWG Telecon - 10 May 2016 Telecon
2016-0510-1 | Update Sun Alignment Angle presentation with Option A definition and send out to WG | EB |  | Closed 18-May-16
2016-0510-2 | Provide comments on management services definitions in draft updated IOAG service catalog 1 and circulate to WG for input. | EB |  | Closed 18-May-16
SMWG Telecon - 9 Aug 2016 Telecon
2016-0809-1 | Work with the organization of the information entities as listed in the inter-recommendation tracking spreadsheet and factor in the different request types identified in the SMURF | EB | TBD | Closed 3-Oct-16
2016-0809-2 | Revisit AOS type definition assignment in the PIF XML Schema and see if it needs to be corrected | UMW, AC | TBD | Closed | UMW, AC, EB interated/exchanged information; error caught and corrected.
SMWG Meeting - Rome 17-21 October 2016 Meeting
2016-1017-1 | Update PIF per updates discussed in Rome meeting | CH | 2016-12-30 | CLOSED
2016-1017-2 | Provide definition of "Look Angle" for PIF; | JPC | 2016-11-07 | Close -OBE
2016-1017-3 | Provide definition of start and stop comm event for PIF; | JPC | 2016-11-07 | Closed 14-Nov-16
2016-1017-4 | Check the Planning Event terminology with the CCSDS glossary | CH | 2017-07-17 |  | Original date was 30-Dec-16
2016-1017-5 | Add PIF test case for space-based aperture | JPC | 2017-07-31 |  | JP will think about a test case and report back at the January telecon. Original due date was 30-Jan-17 | X
2016-1018-6 | Update PIF XML Schema | HD, CH | 2017-01-31 | Closed
2016-1018-7 | Develop draft PIF Prototype development/inter-op timeline | EB, CH | 2017-02-28
2016-1019-8 | Review Service Catalog draft and provide comments | JPC | 2017-01-15 | Closed | MG, MU has completed action
2016-1019-9 | Revise Service Catalog | HK | 2017-05-08 | Closed with new action | New action 2017-0512-26
2016-1020-10 | Update the SoS schema to reflect changes agreed upon with attributes and namespace approach | HD | 2016-11-30 | Closed
2016-1020-11 | Update SoS Annexes to reflect updated schema | CH | 2016-11-30 | Closed
2016-1020-12 | Add the Event Definition and Parameter Definition to the Common Class tab in the inter-recommendation spreadsheet | KT | 2017-02-15 |  | Original data was 15-Jan-16. Pull from SoS and PIF, Also change Payload Class title to Common Class on tabs and delete Common Class
2016-1020-13 | Create a CWE directory structure diagram and send to WG | KT | 2017-01-17 | Closed | Original date was 14-Nov-16
2016-1020-14 | Develop examples showing DDOR parameters, config profiles, planning requests and service package requests | EB | 2017-05-08 | Closed | Original date was 7-Dec-16. In work.
2016-1021-15 | Produce diagram capturing the conclusions developed with the CSTS concerning the CSS control architecture | EB | 2017-01-30 | Closed
2016-1021-16 | Assess how execution control function can fit into functional resource model | WH, HD | 2017-05-08 | Closed OBE | EB to remind actionees
2016-1021-17 | Revise Draft SMURF white book | CH | 2017-05-08 | Closed with new action | See updated action 2017-0512-09
2016-1021-18 | Develop draft SMURF XML Schema | HD, UMW | 2017-05-08 | Closed
2016-1021-19 | Produce outline of SMURF Test cases/plan | EB, KT, MG | 2017-02-10
2016-1021-20 | Develop draft TGFT White book | CH, JVP | 2017-08-15 |  | Original date was 8-May-17.
2016-1021-21 | Develop proposal for XDFU usage for the TGFT | CH, JVP | 2017-05-08 | Closed
2016-1021-22 | Develop draft TGFT test plan | KT, MG, CC, HW | 2017-08-15 | Closed with new action | Original date was 8-May-17.
2016-1021-23 | Develop service profiles for SA/CP | AC, MG, JVP | 2017-04-28 | CLOSED per 25-Apr telecon notes | TLM, CMD, RNG, DDOR, All combos, etc
2016-1021-24 | Preliminary Draft white book of the SA/CP | MG | 2017-10-16 | Closed with new action | New action is 2017-0512-20
2016-1021-25 | Develop Service Package Data Format First Draft | JPC | 2017-05-02
2016-1021-26 | Revise Concept Book comments from CLE meetings | EB | 2017-05-08 | Closed | Original date was 20-Feb
2016-1021-27 | Develop examples of event sequences based on concept being developed for DSN | EB | Fall 17 Meeting | Closed with new action | New action is 2017-0512-15
2016-1021-28 | Begin development of a very drafty Management Services test plan book | MG, KT | 2017-05-02 | Closed with new action | KT sent the basic template to MG 1-May-17. New action is 2017-0512-54
2016-1021-29 | Develop draft High Level Management Services requirements | AC, HD | 2017-05-08 | CLOSED per 25-Apr telecon notes
2016-1021-30 | Develop draft Concept for Extensible Management Services | AC, HD, CH | 2017-05-08 | Closed with new action | New action is 2017-0512-53
SMWG Meeting - 15 February 2017 Telecon
2017-0215-1 | Check with the DDOR guys concerning the open loop recording Functional Resource possibly needing some additional parameters. | EB | 2017-05-08 | Closed with new action | New action is 2017-0512-42
2017-0215-2 | For planning information output, check with DDOR operations at DSN and DDOR WG concerning how they accommodate inclusion of geometry form multiple objects (e.g. spacecraft 1…n and quasar 1…n)? | EB | 2017-04-25 | CLOSED 1-May-17 | See 15-Feb-17 Telecon note 8d)
SMWG Meeting - 13 March 2017 Telecon
2017-0313-01 | Provide comments to JVP about the XFDU tech note | All | 2017-04-01 | Closed
SMWG Meeting - San Antonio 8-12 May 2017 Meeting
2017-0512-01 | Provide Planning products from TDRS to user missions. The source is the FDF or the user missions information. This is for the PIF. | JPC | 2017-06-30
2017-0512-02 | Provide Planning Products for the Mars relay to Rover for the PIF | EB | 2017-06-30
2017-0512-03 | Update PIF book and schema based on conclusion re-structuring, etc. | CH | 2017-08-16
2017-0512-04 | Update AbstractEvent model based on discussion with the NAV WG | CH | 2017-05-19
2017-0512-05 | Add PIF SM Abstract Event in Common Class tab in Inter-recommendation spreadsheet | KT | 2017-05-31 |  | Wait until Colin updates model from the NAV/CSS SM joint meeting
2017-0512-06 | Develop PIF Test case outline for test plan | EB | 2017-07-07
2017-0512-07 | Determine structure of PIF (flat vs structured) | EB, CH | 2017-07-07
2017-0512-08 | Complete inter-operations PIF testing | EB, CH, YFW, UMW | 2017-11-01
2017-0512-09 | Final PIF test plan | KT | 2017-11-01
2017-0512-10 | Exercise: Assume structure similar to DSN; check that events in PIF make sense for DSN | EB | 2017-06-30
2017-0512-11 | Prepare a presentation on service package proposal (re: state machine) | MG | 2017-07-31
2017-0512-12 | Determine if offline service package needs distinct classes in the service package result. | JPC |  | Closed 10-May-17
2017-0512-13 | Look at SPR, the SMURF, config profile and event sequence and propose how these can fit together | EB | 2017-08-17
2017-0512-14 | OIDS/FRs vs Event Sequences | PP, EB | 2017-11-01
2017-0512-15 | Develop examples of event sequences based on concept being developed for DSN | EB | 2017-11-01
2017-0512-16 | Provide strawman of proposed event sequence structuring | EB | 2017-07-17
2017-0512-17 | Prepare strawman UML diagram of the configuration profile | MG | 2017-07-17
2017-0512-18 | Develop Service Agreement/Config Profile service profiles | MG, AC | 2017-11-01
2017-0512-19 | Provide IOAG modulation recommendations and send to AC | EB | 2017-06-30
2017-0512-20 | Develop preliminary draft Service Agreement/Config Profile white book | MG | 2017-11-01
2017-0512-21 | Complete CWE file restructure | KT | 2017-07-17
2017-0512-22 | Update Referential Framework in the Models tab in the Inter-recommendation spreadsheet | KT |  | Closed | Requested original version from John
2017-0512-23 | Update SoS schema and send to SANA | CH | 2017-08-30
2017-0512-24 | Write a RID to change the SANA Registry section D2.2 of the SoS to replace the last sentence of the section to indicate that the schedule publisher goes into the organization roles registry. Make sure to include the url for the registry. | EB | 2017-06-15
2017-0512-25 | Write a RID to change the SANA Registry section D2.3 of the SoS thefirst paragraph url to spacecraft registry (remove "id" in url) | EB | 2017-06-15
2017-0512-26 | Write a RID to change the SANA Registry section D2.4 of the SoS to clarify that the site name must have at least one aperture field. | EB | 2017-06-15
2017-0512-27 | Write a RID to change the SANA Registry section D2.4 of the SoS to remove fourth paragraph. | EB | 2017-06-15
2017-0512-28 | Write a RID to change the SANA Registry section D2.6 of the SoS to update this section to call out the SANA Registry procedure document as per email agreed to by Audrea and Tom. | EB | 2017-06-15
2017-0512-29 | Write a RID to update the Abstract Event model in the SoS | CH | 2017-05-19
2017-0512-30 | Write a RID to change the SANA Registry section D2.6 of the SoS to change the policy to 3.11b and then to indicate the review authority is CSS area | EB | 2017-06-15
2017-0512-31 | Write a RID to change the SANA Registry section D2.8 of the SoS to edit the listing so that g) follows f) (currently a) follows f)) | EB | 2017-06-15
2017-0512-32 | Dispose SoS RIDs Update Books | CH | 2017-07-21
2017-0512-33 | Update SoS Prototype Test Report | EB | 2017-07-06
2017-0512-34 | Write a tech note to indicate registry update policy for the CSSM for example in the SoS,how is someone to know that they need to change the version number in section D2.8 or how does someone know to clone the section D2.8 and modify it for a different recommendations | EB | 2017-08-17 |  | This is similar to Action 2011-0520-06: State policy for schema maintenance regarding SANA and provide writeup of policy.
2017-0512-35 | Draft initial SMURF schema | CH | 2017-07-17
2017-0512-36 | Update SMURF text to be consistent with UML diagram from San Antonio meeting | CH | 2017-07-17
2017-0512-37 | Coordinate SMURF prototyping environment | MG, CH | 2017-08-18
2017-0512-38 | Complete draft of SMURF test plan | KT | 2017-08-31
2017-0512-39 | Update TGFT white book with XFDU decisions | CH | 2017-07-31
2017-0512-40 | Finalize the TGFT meta data definition | CC | 2017-07-31
2017-0512-41 | Produce strawman outline for ground observation sequence for DDOR | EB | 2017-08-16
2017-0512-42 | Produce 1st cut of DDOR config parameters and indicate where they go in FRM | EB | 2017-08-16 |  | Previous action closed
2017-0512-43 | Update Draft TGFT Test Plan with testing details | CC, HL | 2017-07-31
2017-0512-44 | Final TGFT test plan | KT | 2017-11-03
2017-0512-45 | Check the draft restricted XFDU schema supplied by JVP and update as determined | CC | 2017-07-31
2017-0512-46 | Extend the restricted XFDU schema to include TGFT specific meta data | CC | 2017-07-31
2017-0512-47 | Provide Service Catalog inputs on statements for service performance; eg "gain should be provided for 45 deg" | EB | 2017-08-29
2017-0512-48 | Update Service Catalog based on inputs | HK | 2017-11-01
2017-0512-49 | Revise next rev concept book per comments from Cleveland meeting and MG comments | EB | 2018-04-02
2017-0512-50 | Update lifecycle diagram | EB | 2018-04-02
2017-0512-51 | Put comments in master copy of concept book | MG | 2017-07-31
2017-0512-52 | Draft high-level requirements for the Management Services book | AC, HD, CH | 2017-11-01
2017-0512-53 | Draft concept for extensible management services | AC,, HD, CH | 2018-04-02
2017-0512-54 | Produce preliminary draft test plan for management services | MG, KT | 2018-03-12
2017-0512-55 | Clean up the control architecture diagrams and further iterate with CSTS and CSSM | EB | 2017-08-30

## Color Code and Actionees
Color Code
Red text means the item is past its due date
Orange text means that the item is past its original due date, but has been extended.
Black text in orange cells means that the action is on hold with no definite due date
Green text means that this action Item was closed since the last time the Action Item report was issued. Any green items are listed on the Open Actions sheet until they are discussed at a meeting or telecon, after which they are removed fro the Open Actions sheet (they remain on the All Actions sheet)
Meeting/telecon headings are color-coded to reflect the highest level of incompleteness for any action item from that meeting/telecon. For example, if the action items for a particular meeting contain one or more orange (past original date but extended) items and one or more red (past due) items, the heading will be red.
Assignees
Initials | Name
AC | Anthony Crowson
CH | Colin Haddow
CC | Claudia Ciocirlan
EB | Erik Barkley
FB | Fred Brosi
JVP | John Pietras
KT | Karen Tuttle
MD | Michel Dugast
MG | Marcin Gnat
NC | Nicolas Champsavoir
PP | Paul Pechkam
PS | Peter Shames
SG | Sylvain Gully
SZ | Sil Zendejas
TA | Takashi Asama
TB | Tung Bui
YN | Yagi Nobuhiro
JR | Jessica Reinert
JPC | Jean-Pierre Chamoun
HD | H. Dreihan
HW | Haiyan Wu
HL

## Open Actions by date
AI# | Action | Assignee | Due Date
2017-0512-04 | Update AbstractEvent model based on discussion with the NAV WG | CH | 2017-05-19
2017-0512-29 | Write a RID to update the Abstract Event model in the SoS | CH | 2017-05-19
2017-0512-05 | Add PIF SM Abstract Event in Common Class tab in Inter-recommendation spreadsheet | KT | 2017-05-31
2017-0512-24 | Write a RID to change the SANA Registry section D2.2 of the SoS to replace the last sentence of the section to indicate that the schedule publisher goes into the organization roles registry. Make sure to include the url for the registry. | EB | 2017-06-15
2017-0512-25 | Write a RID to change the SANA Registry section D2.3 of the SoS thefirst paragraph url to spacecraft registry (remove "id" in url) | EB | 2017-06-15
2017-0512-26 | Write a RID to change the SANA Registry section D2.4 of the SoS to clarify that the site name must have at least one aperture field. | EB | 2017-06-15
2017-0512-27 | Write a RID to change the SANA Registry section D2.4 of the SoS to remove fourth paragraph. | EB | 2017-06-15
2017-0512-28 | Write a RID to change the SANA Registry section D2.6 of the SoS to update this section to call out the SANA Registry procedure document as per email agreed to by Audrea and Tom. | EB | 2017-06-15
2017-0512-30 | Write a RID to change the SANA Registry section D2.6 of the SoS to change the policy to 3.11b and then to indicate the review authority is CSS area | EB | 2017-06-15
2017-0512-31 | Write a RID to change the SANA Registry section D2.8 of the SoS to edit the listing so that g) follows f) (currently a) follows f)) | EB | 2017-06-15
2017-0512-01 | Provide Planning products from TDRS to user missions. The source is the FDF or the user missions information. This is for the PIF. | JPC | 2017-06-30
2017-0512-02 | Provide Planning Products for the Mars relay to Rover for the PIF | EB | 2017-06-30
2017-0512-10 | Exercise: Assume structure similar to DSN; check that events in PIF make sense for DSN | EB | 2017-06-30
2017-0512-19 | Provide IOAG modulation recommendations and send to AC | EB | 2017-06-30
2017-0512-33 | Update SoS Prototype Test Report | EB | 2017-07-06
2017-0512-06 | Develop PIF Test case outline for test plan | EB | 2017-07-07
2017-0512-07 | Determine structure of PIF (flat vs structured) | EB, CH | 2017-07-07
2016-1017-4 | Check the Planning Event terminology with the CCSDS glossary | CH | 2017-07-17
2017-0512-16 | Provide strawman of proposed event sequence structuring | EB | 2017-07-17
2017-0512-17 | Prepare strawman UML diagram of the configuration profile | MG | 2017-07-17
2017-0512-21 | Complete CWE file restructure | KT | 2017-07-17
2017-0512-35 | Draft initial SMURF schema | CH | 2017-07-17
2017-0512-36 | Update SMURF text to be consistent with UML diagram from San Antonio meeting | CH | 2017-07-17
2017-0512-32 | Dispose SoS RIDs Update Books | CH | 2017-07-21
2016-1017-5 | Add PIF test case for space-based aperture | JPC | 2017-07-31
2017-0512-11 | Prepare a presentation on service package proposal (re: state machine) | MG | 2017-07-31
2017-0512-39 | Update TGFT white book with XFDU decisions | CH | 2017-07-31
2017-0512-40 | Finalize the TGFT meta data definition | CC | 2017-07-31
2017-0512-43 | Update Draft TGFT Test Plan with testing details | CC, HL | 2017-07-31
2017-0512-45 | Check the draft restricted XFDU schema supplied by JVP and update as determined | CC | 2017-07-31
2017-0512-46 | Extend the restricted XFDU schema to include TGFT specific meta data | CC | 2017-07-31
2017-0512-51 | Put comments in master copy of concept book | MG | 2017-07-31
2016-1021-19 | Produce outline of SMURF Test cases/plan | EB, KT, MG | 2017-08-11
2016-1021-20 | Develop draft TGFT White book | CH, JVP | 2017-08-15
2017-0512-03 | Update PIF book and schema based on conclusion re-structuring, etc. | CH | 2017-08-16
2017-0512-41 | Produce strawman outline for ground observation sequence for DDOR | EB | 2017-08-16
2017-0512-42 | Produce 1st cut of DDOR config parameters and indicate where they go in FRM | EB | 2017-08-16
2017-0512-13 | Look at SPR, the SMURF, config profile and event sequence and propose how these can fit together | EB | 2017-08-17
2017-0512-34 | Write a tech note to indicate registry update policy for the CSSM for example in the SoS,how is someone to know that they need to change the version number in section D2.8 or how does someone know to clone the section D2.8 and modify it for a different recommendations | EB | 2017-08-17
2017-0512-37 | Coordinate SMURF prototyping environment | MG, CH | 2017-08-18
2017-0512-47 | Provide Service Catalog inputs on statements for service performance; eg "gain should be provided for 45 deg" | EB | 2017-08-29
2017-0512-23 | Update SoS schema and send to SANA | CH | 2017-08-30
2017-0512-55 | Clean up the control architecture diagrams and further iterate with CSTS and CSSM | EB | 2017-08-30
2017-0512-38 | Complete draft of SMURF test plan | KT | 2017-08-31
2011-0520-06 | State policy for schema maintenance regarding SANA and provide writeup of policy. | HD | 2017-11-01
2017-0512-08 | Complete inter-operations PIF testing | EB, CH, YFW, UMW | 2017-11-01
2017-0512-09 | Final PIF test plan | KT | 2017-11-01
2017-0512-14 | OIDS/FRs vs Event Sequences | PP, EB | 2017-11-01
2017-0512-15 | Develop examples of event sequences based on concept being developed for DSN | EB | 2017-11-01
2017-0512-18 | Develop Service Agreement/Config Profile service profiles | MG, AC | 2017-11-01
2017-0512-20 | Develop preliminary draft Service Agreement/Config Profile white book | MG | 2017-11-01
2017-0512-48 | Update Service Catalog based on inputs | HK | 2017-11-01
2017-0512-52 | Draft high-level requirements for the Management Services book | AC, HD, CH | 2017-11-01
2017-0512-44 | Final TGFT test plan | KT | 2017-11-03
2017-0512-54 | Produce preliminary draft test plan for management services | MG, KT | 2018-03-12
2015-1112-16 | Complete draft white book of Event Sequence | PP, EB | 2018-04-02
2017-0512-49 | Revise next rev concept book per comments from Cleveland meeting and MG comments | EB | 2018-04-02
2017-0512-50 | Update lifecycle diagram | EB | 2018-04-02
2017-0512-53 | Draft concept for extensible management services | AC,, HD, CH | 2018-04-02
2016-1021-25 | Develop Service Package Data Format First Draft | JPC | ?