## Action Items
AI # | Meeting | Project | Action | Assignee | Due Date | Status | DateClosed | Notes
2017-1109-06 | 2017-Fall | SPKG | Produce and Review Service Package XML Schema | WE, HD | 2018-04-02 | Closed | 2019-06-12 | 22-May-18 comment: in progress? Based on initial version sent from DLR? Check for input from W, E,. late in March. More discussion needed? ; 12-Jun: W. Eddy to post schema in CWE for service package drafts
2018-0410-06 | 2018-Spring | SPKG | Check external reference definition and recommend a modification or deletion for the Service Package book | WE | 2018-08-22 | Closed | 2018-09-17
2016-1017-4 | 2016-Spring | General | Check the Planning Event terminology with the CCSDS glossary | CH | 2018-02-06 | Closed | 2018-01-22 | Original date was 30-Dec-16
2016-1017-5 | 2016-Fall | PIF | Add PIF test case for space-based aperture | JPC | 2017-07-31 | Closed | <unknown> | JP will think about a test case and report back at the January telecon. Original due date was 30-Jan-17
2016-1021-19 | 2016-Fall | SMURF | Produce outline of SMURF Test cases/plan | EB, KT, MG | <unknown> | Closed | <unknown> | Erik needs to review what MG provided and provide feedback. Karen to prepare the test plan to be ready for the test cases by the fall meeting
2016-1021-20 | 2016-Fall | TGFT | Develop draft TGFT White book | CH, JVP | 2017-08-15 | Closed | 2017-08-08 | Original date was 8-May-17.
2017-0512-02 | 2017-Spring | PIF | Provide Planning Products for the Mars relay to Rover for the PIF | EB | 2017-07-30 | Closed | 2017-08-08
2017-0512-03 |  | PIF | Update PIF schema based on conclusion re-structuring, etc. | CH | 2018-02-06 | Closed | <unknown> | This will be done after the SoS update.
2017-0512-04 | 2017-Spring | General | Update AbstractEvent model based on discussion with the NAV WG | CH | 2017-09-15 | Closed | <unknown> | Wait until SoS RID disposition is complete
2017-0512-05 | 2017-Spring | Inter-rec | Add PIF SM Abstract Event in Common Class tab in Inter-recommendation spreadsheet | KT | <unknown> | Closed | <unknown> | Wait until Colin updates model from the NAV/CSS SM joint meeting. The Common lass tab was deleted from the spreadsheet. The Abstract Event will be in the common data entities book. Should it be added to the inter-recommendation spreadsheet in Model tab?
2017-0512-06 | 2017-Spring | PIF | Develop PIF Test case outline for test plan | EB | 2017-12-11 | Closed | 2017-12-11
2017-0512-07 | 2017-Spring | PIF | Determine structure of PIF (flat vs structured) | EB, CH | 2017-07-30 | Closed | <unknown>
2017-0627-04 | WebEx-2017-06-17 | General | Review the latest config profile tech note | All | 2018-04-30 | Closed | 2018-05-22 | 22-May-18: JVP has a new one ready to go; OBE
2017-0512-09 | 2017-Spring | PIF | Draft PIF test plan | KT | 2018-03-20 | Closed | 2018-04-04
2017-0512-10 | 2017-Spring | PIF | Exercise: Assume structure similar to DSN; check that events in PIF make sense for DSN | EB | 2017-08-30 | Closed | <unknown>
2017-0512-11 | 2017-Spring | SPKG | Present a presentation on service package proposal (re: state machine) | MG | 2017-11-08 | Closed | <unknown>
2018-0411-13 | 2018-Spring | Inter-rec | Update the Document Model and add to Interrecommendation Worksheet | MG | 2018-05-04 | Closed | 2018-05-22 | 22-May-18: M. Gnat I added two versions of the diagram ready; WG decided which is the best one
2018-0508-01 | WebEx-2018-05-08 | TGFT | Provide approach to encryption/signature for files delivered via TGFT (ie supply secuirty section 3.3); also suggest approach for idenityfing file types in an encrypted environment | CH | 2018-08-31 | Closed | 2018-08-28 | Need conclusion discussion at Berlin meetings
2017-0512-15 | 2017-Spring | EVSQ | Develop examples of event sequences based on concept being developed for DSN | EB | 2018-04-02 | Closed | <unknown>
2017-0512-16 | 2017-Spring | EVSQ | Provide strawman of proposed event sequence structuring | EB | 2017-11-06 | Closed | 2017-10-17
2017-0512-17 | 2017-Spring | CPSA | Prepare strawman UML diagram of the configuration profile | MG, JVP | 2017-11-08 | Closed | 2017-11-08
2017-0512-18 | 2017-Spring | CPSA | Develop Service Agreement/Config Profile service profiles | MG, AC | <unknown> | Closed | 2018-04-09 | Adminstrattively closed.
2017-0512-19 | 2017-Spring | CPSA | Provide IOAG modulation recommendations and send to AC | EB | 2017-06-30 | Closed | 2017-06-30
2017-0512-20 | 2017-Spring | CPSA | Develop preliminary draft Service Agreement/Config Profile white book | MG | <unknown> | Closed | <unknown> | see AI 2017-1108-02
2017-0512-21 | 2017-Spring | admin | Complete CWE file restructure | KT | 2017-11-06 | Closed | <unknown>
2017-0512-23 | 2017-Spring | SSF | Update SoS schema and send to SANA | CH | 2017-09-15 | Closed | 2017-09-19
2017-0512-32 | 2017-Spring | SSF | Dispose SoS RIDs Update Books | CH | 2017-07-21 | Closed | 2017-08-08
2017-0512-33 | 2017-Spring | SSF | Update SoS Prototype Test Report | EB | 2018-01-16 | Closed | <unknown>
2018-0412-20 | 2018-Spring | PIF | Update PIF Test Plan | EB | 2018-11-30 | Closed | 2018-12-11
2017-0512-35 | 2017-Spring | SMURF | Draft initial SMURF schema | CH | 2018-03-20 | Closed | <unknown>
2017-0512-36 | 2017-Spring | SMURF | Update SMURF text to be consistent with UML diagram from San Antonio meeting | CH | 2018-03-20 | Closed | <unknown>
2017-0512-37 | 2017-Spring | SMURF | Coordinate SMURF prototyping environment | MG, CH | 2018-02-06 | Closed | <unknown>
2017-0512-38 | 2017-Spring | SMURF | Complete draft of SMURF test plan | KT | 2018-03-20 | Closed | <unknown>
2017-0512-44 | 2017-Spring | TGFT | Final TGFT test plan | KT | 2018-02-09 | Closed | <unknown> | Pending
2017-0512-13 | 2017-Spring | General | Look at SPDF, the SMURF, config profile and event sequence and propose how these can fit together (see notes) | EB | 2019-05-01 | Closed | 2019-05-09 | 28-Aug-2018: J. Pietras reports there is material that addresses this, except for EvtSeq, in the update configuration profile technote -- take a look 18-Oct-2018: At Berlin meeting, agreed that this is, in general, a standing cross-check type action; however specific action is for EB to develop some material that show how event sequence can express "simple" timing relationships such carrier b starting 2 minutes after carrier a
2018-1015-01 | 2018-Fall | Abs-Evt | Move epcoh definition to SANA | CH | 2018-12-14 | Closed | 2018-12-14
2017-0512-51 | 2017-Spring |  | Put comments in master copy of concept book | MG | 2017-07-31 | Closed | 2017-08-01
2018-1017-01 | 2018-Fall | SMURF | Update SMURF whitebook, XML Schema, UML model in line with changes agreed at Berlin meetings | CH | 2018-12-14 | Closed | 2018-12-14
2018-0612-01 | WebEx-2018-06-12 | General | Identify the issues for schema management and propose a set of actions to be worked; Note this is to support closure of 2011-0520-06 | EB | 2018-10-10 | Closed | 2018-10-19 | A follow on action has been opened -- 2018-1019-01
2018-1018-01 | 2018-Fall | General | Update recommendations: SMURF, PIF, ABSTRACT Event, with latest diagram re book relationship from Marcin (and also found in the inter-rec spreadsheet) | CH | 2018-12-14 | Closed | 2018-12-14
2018-0410-10 | 2018-Spring | PIF | Send the updated PIF to the Nav group | CH | 2018-06-26 | Closed | 2018-07-10
2018-0411-15 | 2018-Spring | General | Perform an exercise for the scenerio id in the SMURF and Service Package Result | MG | 2018-06-12 | Closed | 2018-06-12 | This action is a result of Marcin's presentation on State Machines
2018-0731-02 | Webex-2018-07-31 | PIF | Follow up re further questions on Mars Relay Coordination data formats - see notes from 31-July-2018 telecon for details | EB | 2018-10-10 | Closed | 2018-10-19
2017-1107-01 | 2017-Fall | SMURF | Update SMURF with updated diagrams for the online Srvpkgreq, constraints and timewindow (should timewindow go in PIF or SMURF) | CH | 2018-03-20 | Closed | <unknown>
2017-1108-01 | 2017-Fall | General | Update the inter recommendation document with new data discussed in the Fall 2017 meeting | KT | 2018-04-13 | Closed | 2018-04-12 | Status: Updates completed include: the SM information event tab (add abstract event and CSSA event); Update SM model tab (wait for CSSA and event doc - Doc model, ref framework - reference book); delete Common Class tab. Needs to be done: update SoS and PIF content tables after update to docs have been completed;
2017-1108-02 | 2017-Fall | General | Update Functional Resource tech note | JVP | 2018-04-02 | Closed | <unknown>
2018-0412-21 | 2018-Spring | SMURF | Update the SMURF Test Plan | MG | 2018-07-10 | Closed | 2018-07-10
2017-1109-01 | 2017-Fall | SMURF | Add Replace Service Package to SMURF | CH | 2018-03-20 | Closed | <unknown>
2017-1109-02 | 2017-Fall | SMURF | Review MG email of the 8-Sept concerning the SMURF | CH | 2018-03-20 | Closed | <unknown>
2017-1109-03 | 2017-Fall | General | Update to config profile "cookie cutter" Tech note | JVP | 2018-03-01 | Closed | <unknown>
2017-1109-05 | 2017-Fall | SPKG | Complete Service Package White Book | JPC | 2018-04-02 | Closed | <unknown>
2018-0411-18 | 2018-Spring | CPSA | Propose how an event sequence can reference information in configuration profiles for the following cases a) the carriers are all in one config profile b) the carriers are mapped one to one with the config profiles (note that both these cases apply to the configuration profile itself) | EB | 2018-07-30 | Closed | 2018-07-31 | Initial analysis per this AI deemed to be closed. Follow-up AI 2018-0731-01 opened.
2017-1109-07 | 2017-Fall | SvcCat | Revise draft of Service Catalogue | HK | 2018-04-02 | Closed | <unknown>
2018-0123-01 | WebEx-2018-01-23 | TGFT | CNES to provide IP address of their server | CNES | 2018-03-05 | Closed | <unknown>
2018-0123-02 | WebEx-2018-01-23 | TGFT | NSSC to provide IP address of their server | NSSC | 2018-03-05 | Closed | <unknown>
2018-0123-03 | WebEx-2018-01-23 | TGFT | Set up directory in CWE to enable exchance of test reports | KT | 2018-03-20 | Closed | <unknown>
2018-0123-04 | WebEx-2018-01-23 | TGFT | Update draft TGFT Test Plan and send to CH | KT | 2018-01-26 | Closed | <unknown>
2018-0123-05 | WebEx-2018-01-23 | TGFT | Distribute updated draft of TGFT Test Plan and send to TGFT Testing Coordination Splinter working group | CH | 2018-02-15 | Closed | <unknown> | Pending final review
2018-206-01 | WebEx-2018-02-06 | General | Check how terms are added to the CCSDS glossary with Tom | EB | 2018-04-13 | Closed | 2018-04-11
2018-206-02 | WebEx-2018-02-06 | PIF | Determine if Mars use case should be accomodated in the PIF | EB | 2018-04-13 | Closed | 2018-04-10
2018-206-03 | WebEx-2018-02-06 | General | Check with SANA about the status and plan for service sites and aperture in registry | EB | 2018-04-13 | Closed | 2018-04-11
2018-206-04 | WebEx-2018-02-06 | SSF | Provide proposed updates from 6-Feb discussion to the Abstract Definition Doc within the document | EB | 2016-04-13 | Closed | <unknown> | Technical corrigendum will be required
2018-1211-01 | Webex-2018-12-11 | TGFT | Clarify constraints on presence of payload and metadata files in an XFDU packages | JVP | 2018-12-17 | Closed | 2018-12-14
2018-0409-01 | 2018-Spring | TGFT | Update the TGFT per discussions at meeting and issues raised in Claudia's emails | JVP | 2018-05-22 | Closed | 2018-05-08
2018-0411-17 | 2018-Spring | Inter-rec | Update inter recommendation with State Machine diagrams once final diagrams are completed | MG | 2018-09-10 | Closed | 2018-10-19
2017-0808-01 | WebEx-2017-08-08 | General | Generate an example that synthesizes Mars relay coordination input along with the structuring discussion for the EventAssociation metadata | EB | 2018-07-30 | Closed | 2018-07-31 | Technically, an example was not generated, however the analysis done provides enough mapping information to guide updates to the PIF -- verified that current PIF format can accomdate Mars Relay examples.
2017-0512-55 | 2017-Spring | General | Clean up the control architecture diagrams and further iterate with CSTS and CSSM | EB | 2019-05-01 | Closed | 2019-05-09
2017-0512-50 | 2017-Spring | Concept | Update lifecycle diagram | EB | 2018-08-25 | Closed | 2018-07-31 | Adminstrattively closed -- to be part of general action of updating concept book.
2018-0410-02 | 2018-Spring | SMURF | Move the time window set into the enhanced constraint in the SMURF | CH | 2018-09-27 | Closed | 2018-08-31
2018-0410-03 | 2018-Spring | SMURF | Update delete service package request to add optional delete Sevice Package in SMURF | CH | 2018-09-27 | Closed | 2018-08-31
2018-0410-04 | 2018-Spring | SMURF | Add an aperture constraint for the report request in SMURF | CH | 2018-09-27 | Closed | 2018-08-31
2018-0410-05 | 2018-Spring | SMURF | Correct/check Table 3-32 Class ReplaceSrvPackage ...in SMURF to see if it needs updating | CH | 2018-09-27 | Closed | 2018-08-31
2018-0410-07 | 2018-Spring | SMURF | Allow for an arbitrary planetary location to be specified in a request in the SMURF for planning information and reported back. | CH | 2018-09-27 | Closed | 2018-08-31
2018-0411-11 | 2018-Spring | admin | Create a "readme" file to describe the folders within CWE-private beta. Also say that the Draft Documents isn't used | KT | 2018-04-11 | Closed | 2018-04-11
2018-0411-12 | 2018-Spring | admin | See if we can rename CWE Private to CWE Private Archive | KT | 2018-04-11 | Closed | 2018-04-11
2018-0410-08 | 2018-Spring | SMURF | Update the SMURF to allow extensibility with respect to the inclusion of service package configuration profile and event sequence | CH | 2018-09-27 | Closed | 2018-08-31
2018-0731-01 | Webex-2018-07-31 | SACP | Perform subsequent analysis to follow up on 2018-0411-18 - in particular in reference to latest config profile technote (see notes) | EB | 2019-05-01 | Closed | 2019-05-09 | Note: per 31-Jul-18 telecon, analysis should be done re latest configuration profile tech note material; diagram developed at Berlin meetings -- use this to update presentation and close out AI; 06-May-19: WTFO ? Need to revist -- what is the concern?
2017-0512-34 | 2017-Spring | General | Write a tech note to indicate registry update policy for the CSSM for example in the SoS,how is someone to know that they need to change the version number in section D2.8 or how does someone know to clone the section D2.8 and modify it for a different recommendations | EB | 2019-08-05 | Closed | 2019-08-06 | This is similar to Action 2011-0520-06: State policy for schema maintenance regarding SANA and provide writeup of policy. That action is for HD and due 9-Apr-18 (what?) 19-Oct-2018: see notes from Berlin meeting -- just need to write up a copy and paste type police with a template; 25-Jun-19: maybe OBE? Lots of recommendations going to agency review, do we still need this? 16-Jul-19: Check again afer the remainder of the books are out for agency review; Adminstratively closed as OBE -- 06-Aug-19
2017-0512-49 | 2017-Spring | Concept | Revise next rev concept book per comments from Cleveland meeting and MG comments | EB | 2018-10-01 | Closed | 2018-09-02 | Closed administratively -- concept book update plan to be discussed at Berlin meetings
2018-1019-01 | 2018-Fall | General | Define concept for version control of schema files | CH | 2018-12-31 | Closed | 2018-11-20
2017-0512-53 | 2017-Spring | MgmtSvc | Draft concept for extensible management services | AC,, HD, CH | 2018-10-01 | Closed | 2018-09-20 | Technote uploaded to CWE
2017-1108-03 | 2017-Fall | CPSA | Develop outline of Service Agreement & Config Profile | MG | 2018-10-01 | Closed | 2018-10-19
2018-0410-09 | 2018-Spring | General | Remove schemas from the Appendix from all books CH is responsible for | CH | 2018-10-01 | Closed | 2018-09-20 | (SMURF and PIF updated)
2018-0411-14 | 2018-Spring | Inter-rec | Update Ref-Framework diagram and add to Interrecommendation Worksheet | MG | 2018-10-01 | Closed | 2018-10-19
2018-0413-01 | 2018-Spring | General | Propose how to establish and maintain repositories for UML models and XML schemas | CH, EB, HD | 2018-10-01 | Closed | 20-Se18 | Closed administratively -- to be discussed at Berlin meetings
2018-0710-01 | WebEx-2018-07-10 | General | Taking the results of the scenario Id analysis into account, develop a proposal as to how scenario can be properly tracked for the use cases identified by M. Gnatt (e.g, default scenario, updates, etc) | CH, EB | 2018-10-01 | Closed | 2018-10-19 | This is subsequent follow to AI 2018-0411-15; the closure for which identified this action.
2018-1019-02 | 2018-Fall | CPSA | Review and provide comments if any on outline of CPSA book | EB, CH, WE | 2019-03-26 | Closed | 2019-04-16 | Activiites are underway re sturucturing of CSPA -- no further comments from assignees.
2018-0411-16 | 2018-Spring | General | Create a draft Tech note for the State Machine for Inter Recommendation Spreadsheet | MG | 2018-10-05 | Closed | 2018-10-19
2011-0520-06 | 2011-Fall | General | State policy for schema maintenance regarding SANA and provide writeup of policy. | HD | 2018-10-09 | Closed | 2018-09-20 | Closed adminstratvely -- working sessions scheduled for Berling meetings. Originally Fall meeting 2011. Need this for SoS Blue book. Run by XML SIG Noted that this will likely need to be discussed within the context of XSG as part of the overall CCSDS schema management set of considerations. Smaller initial steps agreed to as initial steps to closing the action. Waiting for written version. See Peter Shames SoS red book comments. We are going to discuss schema management at the Rome meeting. This was handed over from EB.
2017-0512-54 | 2017-Spring | MgmtSvc | Produce preliminary draft test plan for management services | MG, KT | 2018-11-12 | Closed | 2018-10-19 | Adminstratively closed: Good god what were we thinking?!
2019-0205-02 | Webex-2019-02-05 | TGFT | Perform editorial updates as discussed at Berlin meetings -- cleaning up use case discussion, etc | CH | 2019-05-03 | Closed | 2019-05-03
2018-1019-03 | 2018-Fall | General | Review State Machine Technote | EB, CH, AC, WE | 2019-05-03 | Closed | 2019-05-09 | To be reviewed at the Spring meetings
2018-0412-19 | 2018-Spring | EVSQ | Indicate the directives from the FR model that occur at various state transitions in the event sequence. | EB | 2019-07-15 | Closed | 2019-05-09 | Adminstratively closed: idea of relating FR directives to states is well understood now; the details will part of EVSQ book development no matter what.
2019-0205-01 | Webex-2019-02-05 | PIF | Determine how to represent occultations that are earth-centered vs topographic- centered (is aperture made optional?) | EB, CH, AC | 2019-04-15 | Closed | 2019-04-16 | See email of 15 April; subsequent action pending for updating the book
2017-0512-52 | 2017-Spring | MgmtSvc | Draft high-level requirements for the Management Services book | AC, HD, CH | 2019-05-03 | Closed | 2019-05-03
2018-0206-05 | WebEx-2018-02-06 | General | Create a swimlane diagram of the DDOR process presented at 6-Feb telecon (best effort) | EB | 2019-10-15 | Open
2017-0512-08 | 2017-Spring | PIF | Complete inter-operations PIF testing | EB, CH, YFW, UMW | 2019-05-01 | Closed | 2019-05-09 | Adminstratvely closed; there is no value-added aspect for this AI -- we need to do the prototyping anyway
2017-0512-14 | 2017-Spring | General | OIDS/FRs vs Event Sequences | PP, EB | 2019-10-15 | Closed | 2019-05-09 | 19-Oct-2018: Partially OBE: A general approach of FR Type + Instance Number vs FR Nickname is possible -- which ever approach is finally choosen, it is what the EVSQ will likely have to follow -- re-vist in the future.; 09-May-19: Admin closed; will be part of EVSQ development now that concept between states and FRs is understood.
2018-1019-04 | 2018-Fall | Concept | Develop a list of changes needed for the concept book | EB | 2019-10-14 | Open
2015-1112-16 | 2015-Fall | EVSQ | Draft outline of EVSQ Book | EB | 2019-10-14 | Open |  | 28 Aug 2018: unlikely to occur prior to the Berlin mtgs -- what is the plan? 19-Oct-2018 -- some sort of draft to be produced, but it will not necessarily be complete
2019-0806-01 | Webex-2019-08-06 | SACP | Review SACP Concept outline/draft produced by M. Gnat and provide comments (if any) | All | 2019-09-05 | Open
2019-0326-01 | Webex 2019-03-26 | SACP | Update the outline of the book based on discussions (and input Erik owes you) from webex on 26 March | MG | 2019-05-03 | Closed | 2019-05-03
2019-0326-02 | Webex 2019-03-26 | CPSA | Produce a suggested revision to the CSPA outline re definition of the profiles | EB | 2019-04-02 | Closed | 2019-04-16 | See email re AI -- outline development in progress
2019-0416-01 | Webex 2019-04-16 | PIF | Updated the PIF with suitable verbiage for indicating geocentric apperture ref re occulation start and stop events | CH | 2019-05-03 | Closed | 2019-05-03 | Opened as a resutl of closing 2019-0205-01; Closed via update to UML model/common data structure book
2019-0506-01 | 2019-Spring | SMURF | Check to see if SN still using "chaining" for requesting service | WE | 2019-05-09 | Closed | 2019-05-09 | SN no longer has any present users; support dropped in SGSS.
2019-0508-01 | 2019-Spring | General | Develop a list of roles to be used for CSSM recommendation vis a vis SANA Registry; e.g, SSF has SchedulePublisher, so SMURF has? | CH | 2019-05-31 | Closed | 2019-05-09 | See email of 08-May-19
2019-0509-01 | 2019-Spring | SACP | Develop draft concept paper for project intiation -- capture concepts such as data format only, SA/CP are the data entities, based FRM, profiles used inside CSSA area, predefined cookie cutters for selected profiles, etc | MG | 2019-08-15 | Closed | 2019-08-06 | Concept paper sent to WG on 16-Jul-19.
2019-0509-02 | 2019-Spring | TGFT | Close out Yellow Book for TGFT | CH | 2019-07-15 | Closed | 2019-07-16
2019-0509-03 | 2019-Spring | General | Contact SANA to follow-up re consider Git hosted on SANA | CH, HD, EB | 2019-06-30 | Closed | 2019-07-16 | 25-Jun-19: E. Barkley to contact SANA and propose webex/telecon to discuss. 16-Jul-2019: interested parties contacted; telecon schedule negotation in progress.
4

## Legend
Project Identifiers | Project/Area
admin | Administration
Concept | Concept Book
SACP | Service Agreement/Configuration Profile Data Format
EVSQ | Event Sequence
General | General -- program of work as a whole
Inter-rec | Inter-recommendation tracking
MgmtSvc | Management Service
PIF | Planning Information Format
SMURF | Service Management Utliziation Request Format
SPKG | Service Package
TGFT | Terrestrial Generic File Transfer