## Action Items
AI # | Meeting | Project | Action | Assignee | Due Date | Status | DateClosed | Notes
2016-1017-5 | 2016-Fall | PIF | Add PIF test case for space-based aperture | JPC | 2017-07-31 | Closed | <unknown> | JP will think about a test case and report back at the January telecon. Original due date was 30-Jan-17
2016-1021-19 | 2016-Fall | SMURF | Produce outline of SMURF Test cases/plan | EB, KT, MG | <unknown> | Closed | <unknown> | Erik needs to review what MG provided and provide feedback. Karen to prepare the test plan to be ready for the test cases by the fall meeting
2017-0512-03 |  | PIF | Update PIF schema based on conclusion re-structuring, etc. | CH | 2018-02-06 | Closed | <unknown> | This will be done after the SoS update.
2017-0512-04 | 2017-Spring | General | Update AbstractEvent model based on discussion with the NAV WG | CH | 2017-09-15 | Closed | <unknown> | Wait until SoS RID disposition is complete
2017-0512-05 | 2017-Spring | Inter-rec | Add PIF SM Abstract Event in Common Class tab in Inter-recommendation spreadsheet | KT | <unknown> | Closed | <unknown> | Wait until Colin updates model from the NAV/CSS SM joint meeting. The Common lass tab was deleted from the spreadsheet. The Abstract Event will be in the common data entities book. Should it be added to the inter-recommendation spreadsheet in Model tab?
2017-0512-07 | 2017-Spring | PIF | Determine structure of PIF (flat vs structured) | EB, CH | 2017-07-30 | Closed | <unknown>
2017-0512-10 | 2017-Spring | PIF | Exercise: Assume structure similar to DSN; check that events in PIF make sense for DSN | EB | 2017-08-30 | Closed | <unknown>
2017-0512-11 | 2017-Spring | SPKG | Present a presentation on service package proposal (re: state machine) | MG | 2017-11-08 | Closed | <unknown>
2017-0512-15 | 2017-Spring | EVSQ | Develop examples of event sequences based on concept being developed for DSN | EB | 2018-04-02 | Closed | <unknown>
2017-0512-20 | 2017-Spring | CPSA | Develop preliminary draft Service Agreement/Config Profile white book | MG | <unknown> | Closed | <unknown> | see AI 2017-1108-02
2017-0512-21 | 2017-Spring | admin | Complete CWE file restructure | KT | 2017-11-06 | Closed | <unknown>
2017-0512-33 | 2017-Spring | SSF | Update SoS Prototype Test Report | EB | 2018-01-16 | Closed | <unknown>
2017-0512-35 | 2017-Spring | SMURF | Draft initial SMURF schema | CH | 2018-03-20 | Closed | <unknown>
2017-0512-36 | 2017-Spring | SMURF | Update SMURF text to be consistent with UML diagram from San Antonio meeting | CH | 2018-03-20 | Closed | <unknown>
2017-0512-37 | 2017-Spring | SMURF | Coordinate SMURF prototyping environment | MG, CH | 2018-02-06 | Closed | <unknown>
2017-0512-38 | 2017-Spring | SMURF | Complete draft of SMURF test plan | KT | 2018-03-20 | Closed | <unknown>
2017-0512-44 | 2017-Spring | TGFT | Final TGFT test plan | KT | 2018-02-09 | Closed | <unknown> | Pending
2017-1107-01 | 2017-Fall | SMURF | Update SMURF with updated diagrams for the online Srvpkgreq, constraints and timewindow (should timewindow go in PIF or SMURF) | CH | 2018-03-20 | Closed | <unknown>
2017-1108-02 | 2017-Fall | General | Update Functional Resource tech note | JVP | 2018-04-02 | Closed | <unknown>
2017-1109-01 | 2017-Fall | SMURF | Add Replace Service Package to SMURF | CH | 2018-03-20 | Closed | <unknown>
2017-1109-02 | 2017-Fall | SMURF | Review MG email of the 8-Sept concerning the SMURF | CH | 2018-03-20 | Closed | <unknown>
2017-1109-03 | 2017-Fall | General | Update to config profile "cookie cutter" Tech note | JVP | 2018-03-01 | Closed | <unknown>
2017-1109-05 | 2017-Fall | SPKG | Complete Service Package White Book | JPC | 2018-04-02 | Closed | <unknown>
2017-1109-07 | 2017-Fall | SvcCat | Revise draft of Service Catalogue | HK | 2018-04-02 | Closed | <unknown>
2018-0123-01 | WebEx-2018-01-23 | TGFT | CNES to provide IP address of their server | CNES | 2018-03-05 | Closed | <unknown>
2018-0123-02 | WebEx-2018-01-23 | TGFT | NSSC to provide IP address of their server | NSSC | 2018-03-05 | Closed | <unknown>
2018-0123-03 | WebEx-2018-01-23 | TGFT | Set up directory in CWE to enable exchance of test reports | KT | 2018-03-20 | Closed | <unknown>
2018-0123-04 | WebEx-2018-01-23 | TGFT | Update draft TGFT Test Plan and send to CH | KT | 2018-01-26 | Closed | <unknown>
2018-0123-05 | WebEx-2018-01-23 | TGFT | Distribute updated draft of TGFT Test Plan and send to TGFT Testing Coordination Splinter working group | CH | 2018-02-15 | Closed | <unknown> | Pending final review
2018-206-04 | WebEx-2018-02-06 | SSF | Provide proposed updates from 6-Feb discussion to the Abstract Definition Doc within the document | EB | 2016-04-13 | Closed | <unknown> | Technical corrigendum will be required
2019-1023-04 | 2019-Fall | SACP | Produce configuration profile examples that include DDOR configuration items | EB, MG | 2021-08-31 | Closed | 2021-08-31 | 31-aug-21: M. gnat has developed some profile material; E. Barkley neeeds to review. 06-Oct-20: Insufficent resources to complete in 2020. 25-Feb-2020: make sure this is on the agenda for the Spring 2020 meetings
2021-0511-01 | 2021-Spring-Virtual | SMURF | Prepare a few summary slides to support agency review for SMURF with regard to prototype testing and report | MG | 2021-07-14 | Closed | 2021-08-31 | 13-Jul-21: Almost done -- need to consider latest comments from M. Unal
2019-1022-01 | 2019-Fall | EVSQ | Produce draft for event sequence book; especially ensuring that the rules for relative sequences are captured | EB | 2021-05-05 | Closed | 2021-06-22 | Bits and pieces have been developed; action is to get a more or less complete draft together
2019-1023-03 | 2019-Fall | SMURF | Generate sample request(s) for DDOR time expressed as SMURFs | CH, EB | 2021-05-11 | Closed | 2021-06-22 | 22-Jun-21: Example DDOR request has been included in the latest 902 schema set. 06-Oct-20: Insufficent resources to complete in 2020. 26-May-2020: EB to attempt first cut and send instance doc to CH; EB also to describe adding parameters
2021-0112-02 | Telecon | SPDF | State the success criteria for SPDF prototyping | MG | 2021-05-11 | Closed | 2021-06-22
2021-0517-01 | 2021-Spring-Virtual | EVSQ | Provide an example or two of event sequences (XML instances) | EB | 2021-06-10 | Closed | 2021-06-22
2019-1022-02 | 2019-Fall | BPMB | Produce preliminary draft of the magenta/best practices book -- in relation to capturing behavioral/implementation considerations | CH | 2021-03-30 | Closed | 2021-03-16 | 06-Oct-20: Insufficent resources to complete in 2020. Re action item: E.g., if an Id is to be unique, its not really the data format that requires this -- but rather a behavioral note; Keep these aspects in the inter-recommendation spreadsheet for the time being.
2021-0112-01 | Telecon | SPDF | Harmonize/include SPDF XML Schema into the 902 schema set and fold in the UML model for SPDF into the overall UML model | CH | 2021-02-23 | Closed | 2021-03-16
2020-0707-01 | Telecon | AED, CDE | Get XML Schemas to SANA for inlusion in xml shcema registry | CH | 2020-12-11 | Closed | 2020-12-17 | 06-Oct-20: Makes sense to do only after the AED,CDE books updates are (confirmed) done 02-Dec-20: Due date updated based on CSSM telecon discussion
2020-0804-01 | Telecon | AED,CDE | Implement PID resolutions to get these books published | EB | 2020-10-13 | Closed | 2020-10-29
2020-0826-01 | Telecon | SACP | Follow up re FRM and XML schema inputs for configuration profile schemas | MG | 2020-10-06 | Closed | 2020-10-06 | M. Gnat contacted H. Dreihahn and updates in accordance with request have been done
2019-1023-02 | 2019-Fall | SMURF | Look DDOR MB 506.0-M-2 and consider what information needs to be sent to providers for indicating the scan pattern; use as is? Down-select just the key items? | EB, MU | 2020-09-15 | Closed | 2020-09-15 | 07-May-2020: M. Unal sent an email internal to ESA sometime ago -- will be forwarded for discussion at telecon on May 26. 07-Jul-2020: looks like information to be added to SMURF and SPDF and possibly SACP; action is now to develop this further; 25-Aug-2020: Further discussion still pending; Per 15-Sep-2020 telecon: scan pattern definition to be sent to DDOR WG based on conclusion from telecon
2019-1023-01 | 2019-Fall | SMURF | Review draft SMURF prototyping plan and determine if updates needed | CH, MG | 2020-05-03 | Closed | 2020-05-26
2020-0114-02 | Webex-2020-01-15 | SMURF | Indicate if basic constraints are something that your TTC network handles/processes (ie. Analyze the re-worked basic constraints as to fit/usefulness for your ground stations) | All | 2020-02-27 | Closed | 2020-03-17 | 25- Feb-2020: MG (DLR) -- BASIC constraints okay; WE (NEN) - Okay, but need to clarify siteRef re SN (probably siteRef Is a TDRS (also for ESA's EDRS) and also Mars Orbiter/relays
2019-1210-01 | 2019-Webex-2019-10-12 | TGFT | Provide a presentation (or other equivalent) material on the TGFT XFDU packaging done by CNES as part of the TGFT prototyping | CC | 2020-02-18 | Closed | 2020-03-17 | 04-Feb-20: reviewed initial presentation -- agreed to make a diagram from slides 3/4 (reference annex D of draft blue book). Examples of XFDU packaging given the TGFT restrictions XFDU;
2020-0114-01 | Webex-2020-01-14 | SMURF | Provided update SMURF, including re-worked basic constraints definition | CH | 2020-01-22 | Closed | 2020-02-04
2019-1210-02 | 2019-Webex-2019-10-12 | General | Provide example abbreviations for for consideration in XML Schema file naming convention, and provide examples of file names, taking into account that some books will have "sub-schemas" | EB | 2019-12-12 | Closed | 2020-01-14
2019-1210-03 | 2019-Webex-2019-10-12 | General | Check with SANA to see if it is possible to add other enumeration values such as "Deprecated" rather than "Expired" -- especially re SM XML Schema management | EB | 2020-01-14 | Closed | 2020-01-14 | C. Haddow sent an email to P. Shames requesting this.
2019-1008-01 | Webex-2019-10-08 | General | Look into whether or not forward off-line service is really something that CCSDS member agencies want to support and report back to the WG | EB | 2019-11-24 | Closed | 2019-12-10 | 24 Oct 2019: WG membership unanimously indicated no use or desire to retire current capabilty
2019-1110-01 | Webex-2019-11-19 | General | Update the inter-recommendation tracking spreadsheet with the revised XML Schema file convention per agreements at Nov 19, 2019 telecon | EB | 2020-11-20 | Closed | 2019-11-21
2019-1022-03 | 2019-Fall | PIF | Update prototype note for PIF Chandra output (NASA, not ISRO) | EB | 2019-11-05 | Closed | 2019-11-19
2018-0206-05 | WebEx-2018-02-06 | General | Create a swimlane diagram of the DDOR process presented at 6-Feb telecon (best effort) | EB | 2019-10-15 | Closed | 2019-10-24 | Adminstratively closed; please see DDOR GB and/or MB for description of DDOR process
2018-1019-04 | 2018-Fall | Concept | Develop a list of changes needed for the concept book | EB | 2019-10-14 | Closed | 2019-10-24 | See meeting summary as to what changes to the book look like
2015-1112-16 | 2015-Fall | EVSQ | Draft outline of EVSQ Book | EB | 2019-10-14 | Closed | 2019-10-24 | 28 Aug 2018: unlikely to occur prior to the Berlin mtgs -- what is the plan? 19-Oct-2018 -- some sort of draft to be produced, but it will not necessarily be complete; see new and improved AI on this topic - 2019-1022-01
2019-0806-01 | Webex-2019-08-06 | SACP | Review SACP Concept outline/draft produced by M. Gnat and provide comments (if any) | All | 2019-09-24 | Closed | 2019-10-24 | EB, CH, MG need to work on putting the concept paper into CMC-ease.
2017-0512-34 | 2017-Spring | General | Write a tech note to indicate registry update policy for the CSSM for example in the SoS,how is someone to know that they need to change the version number in section D2.8 or how does someone know to clone the section D2.8 and modify it for a different recommendations | EB | 2019-08-05 | Closed | 2019-08-06 | This is similar to Action 2011-0520-06: State policy for schema maintenance regarding SANA and provide writeup of policy. That action is for HD and due 9-Apr-18 (what?) 19-Oct-2018: see notes from Berlin meeting -- just need to write up a copy and paste type police with a template; 25-Jun-19: maybe OBE? Lots of recommendations going to agency review, do we still need this? 16-Jul-19: Check again afer the remainder of the books are out for agency review; Adminstratively closed as OBE -- 06-Aug-19
2019-0509-01 | 2019-Spring | SACP | Develop draft concept paper for project intiation -- capture concepts such as data format only, SA/CP are the data entities, based FRM, profiles used inside CSSA area, predefined cookie cutters for selected profiles, etc | MG | 2019-08-15 | Closed | 2019-08-06 | Concept paper sent to WG on 16-Jul-19.
2019-0509-02 | 2019-Spring | TGFT | Close out Yellow Book for TGFT | CH | 2019-07-15 | Closed | 2019-07-16
2019-0509-03 | 2019-Spring | General | Contact SANA to follow-up re consider Git hosted on SANA | CH, HD, EB | 2019-06-30 | Closed | 2019-07-16 | 25-Jun-19: E. Barkley to contact SANA and propose webex/telecon to discuss. 16-Jul-2019: interested parties contacted; telecon schedule negotation in progress.
2017-1109-06 | 2017-Fall | SPKG | Produce and Review Service Package XML Schema | WE, HD | 2018-04-02 | Closed | 2019-06-12 | 22-May-18 comment: in progress? Based on initial version sent from DLR? Check for input from W, E,. late in March. More discussion needed? ; 12-Jun: W. Eddy to post schema in CWE for service package drafts
2017-0512-13 | 2017-Spring | General | Look at SPDF, the SMURF, config profile and event sequence and propose how these can fit together (see notes) | EB | 2019-05-01 | Closed | 2019-05-09 | 28-Aug-2018: J. Pietras reports there is material that addresses this, except for EvtSeq, in the update configuration profile technote -- take a look 18-Oct-2018: At Berlin meeting, agreed that this is, in general, a standing cross-check type action; however specific action is for EB to develop some material that show how event sequence can express "simple" timing relationships such carrier b starting 2 minutes after carrier a
2017-0512-55 | 2017-Spring | General | Clean up the control architecture diagrams and further iterate with CSTS and CSSM | EB | 2019-05-01 | Closed | 2019-05-09
2018-0731-01 | Webex-2018-07-31 | SACP | Perform subsequent analysis to follow up on 2018-0411-18 - in particular in reference to latest config profile technote (see notes) | EB | 2019-05-01 | Closed | 2019-05-09 | Note: per 31-Jul-18 telecon, analysis should be done re latest configuration profile tech note material; diagram developed at Berlin meetings -- use this to update presentation and close out AI; 06-May-19: WTFO ? Need to revist -- what is the concern?
2018-1019-03 | 2018-Fall | General | Review State Machine Technote | EB, CH, AC, WE | 2019-05-03 | Closed | 2019-05-09 | To be reviewed at the Spring meetings
2018-0412-19 | 2018-Spring | EVSQ | Indicate the directives from the FR model that occur at various state transitions in the event sequence. | EB | 2019-07-15 | Closed | 2019-05-09 | Adminstratively closed: idea of relating FR directives to states is well understood now; the details will part of EVSQ book development no matter what.
2017-0512-08 | 2017-Spring | PIF | Complete inter-operations PIF testing | EB, CH, YFW, UMW | 2019-05-01 | Closed | 2019-05-09 | Adminstratvely closed; there is no value-added aspect for this AI -- we need to do the prototyping anyway
2017-0512-14 | 2017-Spring | General | OIDS/FRs vs Event Sequences | PP, EB | 2019-10-15 | Closed | 2019-05-09 | 19-Oct-2018: Partially OBE: A general approach of FR Type + Instance Number vs FR Nickname is possible -- which ever approach is finally choosen, it is what the EVSQ will likely have to follow -- re-vist in the future.; 09-May-19: Admin closed; will be part of EVSQ development now that concept between states and FRs is understood.
2019-0506-01 | 2019-Spring | SMURF | Check to see if SN still using "chaining" for requesting service | WE | 2019-05-09 | Closed | 2019-05-09 | SN no longer has any present users; support dropped in SGSS.
2019-0508-01 | 2019-Spring | General | Develop a list of roles to be used for CSSM recommendation vis a vis SANA Registry; e.g, SSF has SchedulePublisher, so SMURF has? | CH | 2019-05-31 | Closed | 2019-05-09 | See email of 08-May-19
2019-0205-02 | Webex-2019-02-05 | TGFT | Perform editorial updates as discussed at Berlin meetings -- cleaning up use case discussion, etc | CH | 2019-05-03 | Closed | 2019-05-03
2017-0512-52 | 2017-Spring | MgmtSvc | Draft high-level requirements for the Management Services book | AC, HD, CH | 2019-05-03 | Closed | 2019-05-03
2019-0326-01 | Webex 2019-03-26 | SACP | Update the outline of the book based on discussions (and input Erik owes you) from webex on 26 March | MG | 2019-05-03 | Closed | 2019-05-03
2019-0416-01 | Webex 2019-04-16 | PIF | Updated the PIF with suitable verbiage for indicating geocentric apperture ref re occulation start and stop events | CH | 2019-05-03 | Closed | 2019-05-03 | Opened as a resutl of closing 2019-0205-01; Closed via update to UML model/common data structure book
2018-1019-02 | 2018-Fall | CPSA | Review and provide comments if any on outline of CPSA book | EB, CH, WE | 2019-03-26 | Closed | 2019-04-16 | Activiites are underway re sturucturing of CSPA -- no further comments from assignees.
2019-0205-01 | Webex-2019-02-05 | PIF | Determine how to represent occultations that are earth-centered vs topographic- centered (is aperture made optional?) | EB, CH, AC | 2019-04-15 | Closed | 2019-04-16 | See email of 15 April; subsequent action pending for updating the book
2019-0326-02 | Webex 2019-03-26 | CPSA | Produce a suggested revision to the CSPA outline re definition of the profiles | EB | 2019-04-02 | Closed | 2019-04-16 | See email re AI -- outline development in progress
2018-1015-01 | 2018-Fall | Abs-Evt | Move epcoh definition to SANA | CH | 2018-12-14 | Closed | 2018-12-14
2018-1017-01 | 2018-Fall | SMURF | Update SMURF whitebook, XML Schema, UML model in line with changes agreed at Berlin meetings | CH | 2018-12-14 | Closed | 2018-12-14
2018-1018-01 | 2018-Fall | General | Update recommendations: SMURF, PIF, ABSTRACT Event, with latest diagram re book relationship from Marcin (and also found in the inter-rec spreadsheet) | CH | 2018-12-14 | Closed | 2018-12-14
2018-1211-01 | Webex-2018-12-11 | TGFT | Clarify constraints on presence of payload and metadata files in an XFDU packages | JVP | 2018-12-17 | Closed | 2018-12-14
2018-0412-20 | 2018-Spring | PIF | Update PIF Test Plan | EB | 2018-11-30 | Closed | 2018-12-11
2018-1019-01 | 2018-Fall | General | Define concept for version control of schema files | CH | 2018-12-31 | Closed | 2018-11-20
2018-0612-01 | WebEx-2018-06-12 | General | Identify the issues for schema management and propose a set of actions to be worked; Note this is to support closure of 2011-0520-06 | EB | 2018-10-10 | Closed | 2018-10-19 | A follow on action has been opened -- 2018-1019-01
2018-0731-02 | Webex-2018-07-31 | PIF | Follow up re further questions on Mars Relay Coordination data formats - see notes from 31-July-2018 telecon for details | EB | 2018-10-10 | Closed | 2018-10-19
2018-0411-17 | 2018-Spring | Inter-rec | Update inter recommendation with State Machine diagrams once final diagrams are completed | MG | 2018-09-10 | Closed | 2018-10-19
2017-1108-03 | 2017-Fall | CPSA | Develop outline of Service Agreement & Config Profile | MG | 2018-10-01 | Closed | 2018-10-19
2018-0411-14 | 2018-Spring | Inter-rec | Update Ref-Framework diagram and add to Interrecommendation Worksheet | MG | 2018-10-01 | Closed | 2018-10-19
2018-0710-01 | WebEx-2018-07-10 | General | Taking the results of the scenario Id analysis into account, develop a proposal as to how scenario can be properly tracked for the use cases identified by M. Gnatt (e.g, default scenario, updates, etc) | CH, EB | 2018-10-01 | Closed | 2018-10-19 | This is subsequent follow to AI 2018-0411-15; the closure for which identified this action.
2018-0411-16 | 2018-Spring | General | Create a draft Tech note for the State Machine for Inter Recommendation Spreadsheet | MG | 2018-10-05 | Closed | 2018-10-19
2017-0512-54 | 2017-Spring | MgmtSvc | Produce preliminary draft test plan for management services | MG, KT | 2018-11-12 | Closed | 2018-10-19 | Adminstratively closed: Good god what were we thinking?!
2017-0512-53 | 2017-Spring | MgmtSvc | Draft concept for extensible management services | AC,, HD, CH | 2018-10-01 | Closed | 2018-09-20 | Technote uploaded to CWE
2018-0410-09 | 2018-Spring | General | Remove schemas from the Appendix from all books CH is responsible for | CH | 2018-10-01 | Closed | 2018-09-20 | (SMURF and PIF updated)
2011-0520-06 | 2011-Fall | General | State policy for schema maintenance regarding SANA and provide writeup of policy. | HD | 2018-10-09 | Closed | 2018-09-20 | Closed adminstratvely -- working sessions scheduled for Berling meetings. Originally Fall meeting 2011. Need this for SoS Blue book. Run by XML SIG Noted that this will likely need to be discussed within the context of XSG as part of the overall CCSDS schema management set of considerations. Smaller initial steps agreed to as initial steps to closing the action. Waiting for written version. See Peter Shames SoS red book comments. We are going to discuss schema management at the Rome meeting. This was handed over from EB.
2018-0413-01 | 2018-Spring | General | Propose how to establish and maintain repositories for UML models and XML schemas | CH, EB, HD | 2018-10-01 | Closed | 2018-09-20 | Closed administratively -- to be discussed at Berlin meetings
2018-0410-06 | 2018-Spring | SPKG | Check external reference definition and recommend a modification or deletion for the Service Package book | WE | 2018-08-22 | Closed | 2018-09-17
2017-0512-49 | 2017-Spring | Concept | Revise next rev concept book per comments from Cleveland meeting and MG comments | EB | 2018-10-01 | Closed | 2018-09-02 | Closed administratively -- concept book update plan to be discussed at Berlin meetings
2018-0410-02 | 2018-Spring | SMURF | Move the time window set into the enhanced constraint in the SMURF | CH | 2018-09-27 | Closed | 2018-08-31
2018-0410-03 | 2018-Spring | SMURF | Update delete service package request to add optional delete Sevice Package in SMURF | CH | 2018-09-27 | Closed | 2018-08-31
2018-0410-04 | 2018-Spring | SMURF | Add an aperture constraint for the report request in SMURF | CH | 2018-09-27 | Closed | 2018-08-31
2018-0410-05 | 2018-Spring | SMURF | Correct/check Table 3-32 Class ReplaceSrvPackage ...in SMURF to see if it needs updating | CH | 2018-09-27 | Closed | 2018-08-31
2018-0410-07 | 2018-Spring | SMURF | Allow for an arbitrary planetary location to be specified in a request in the SMURF for planning information and reported back. | CH | 2018-09-27 | Closed | 2018-08-31
2018-0410-08 | 2018-Spring | SMURF | Update the SMURF to allow extensibility with respect to the inclusion of service package configuration profile and event sequence | CH | 2018-09-27 | Closed | 2018-08-31
2018-0508-01 | WebEx-2018-05-08 | TGFT | Provide approach to encryption/signature for files delivered via TGFT (ie supply secuirty section 3.3); also suggest approach for idenityfing file types in an encrypted environment | CH | 2018-08-31 | Closed | 2018-08-28 | Need conclusion discussion at Berlin meetings
2018-0411-18 | 2018-Spring | CPSA | Propose how an event sequence can reference information in configuration profiles for the following cases a) the carriers are all in one config profile b) the carriers are mapped one to one with the config profiles (note that both these cases apply to the configuration profile itself) | EB | 2018-07-30 | Closed | 2018-07-31 | Initial analysis per this AI deemed to be closed. Follow-up AI 2018-0731-01 opened.
2017-0808-01 | WebEx-2017-08-08 | General | Generate an example that synthesizes Mars relay coordination input along with the structuring discussion for the EventAssociation metadata | EB | 2018-07-30 | Closed | 2018-07-31 | Technically, an example was not generated, however the analysis done provides enough mapping information to guide updates to the PIF -- verified that current PIF format can accomdate Mars Relay examples.
2017-0512-50 | 2017-Spring | Concept | Update lifecycle diagram | EB | 2018-08-25 | Closed | 2018-07-31 | Adminstrattively closed -- to be part of general action of updating concept book.
2018-0410-10 | 2018-Spring | PIF | Send the updated PIF to the Nav group | CH | 2018-06-26 | Closed | 2018-07-10
2018-0412-21 | 2018-Spring | SMURF | Update the SMURF Test Plan | MG | 2018-07-10 | Closed | 2018-07-10
2018-0411-15 | 2018-Spring | General | Perform an exercise for the scenerio id in the SMURF and Service Package Result | MG | 2018-06-12 | Closed | 2018-06-12 | This action is a result of Marcin's presentation on State Machines
2017-0627-04 | WebEx-2017-06-17 | General | Review the latest config profile tech note | All | 2018-04-30 | Closed | 2018-05-22 | 22-May-18: JVP has a new one ready to go; OBE
2018-0411-13 | 2018-Spring | Inter-rec | Update the Document Model and add to Interrecommendation Worksheet | MG | 2018-05-04 | Closed | 2018-05-22 | 22-May-18: M. Gnat I added two versions of the diagram ready; WG decided which is the best one
2018-0409-01 | 2018-Spring | TGFT | Update the TGFT per discussions at meeting and issues raised in Claudia's emails | JVP | 2018-05-22 | Closed | 2018-05-08
2017-1108-01 | 2017-Fall | General | Update the inter recommendation document with new data discussed in the Fall 2017 meeting | KT | 2018-04-13 | Closed | 2018-04-12 | Status: Updates completed include: the SM information event tab (add abstract event and CSSA event); Update SM model tab (wait for CSSA and event doc - Doc model, ref framework - reference book); delete Common Class tab. Needs to be done: update SoS and PIF content tables after update to docs have been completed;
2018-206-01 | WebEx-2018-02-06 | General | Check how terms are added to the CCSDS glossary with Tom | EB | 2018-04-13 | Closed | 2018-04-11
2018-206-03 | WebEx-2018-02-06 | General | Check with SANA about the status and plan for service sites and aperture in registry | EB | 2018-04-13 | Closed | 2018-04-11
2018-0411-11 | 2018-Spring | admin | Create a "readme" file to describe the folders within CWE-private beta. Also say that the Draft Documents isn't used | KT | 2018-04-11 | Closed | 2018-04-11
2018-0411-12 | 2018-Spring | admin | See if we can rename CWE Private to CWE Private Archive | KT | 2018-04-11 | Closed | 2018-04-11
2018-206-02 | WebEx-2018-02-06 | PIF | Determine if Mars use case should be accomodated in the PIF | EB | 2018-04-13 | Closed | 2018-04-10
2017-0512-18 | 2017-Spring | CPSA | Develop Service Agreement/Config Profile service profiles | MG, AC | <unknown> | Closed | 2018-04-09 | Adminstrattively closed.
2017-0512-09 | 2017-Spring | PIF | Draft PIF test plan | KT | 2018-03-20 | Closed | 2018-04-04
2016-1017-4 | 2016-Spring | General | Check the Planning Event terminology with the CCSDS glossary | CH | 2018-02-06 | Closed | 2018-01-22 | Original date was 30-Dec-16
2017-0512-06 | 2017-Spring | PIF | Develop PIF Test case outline for test plan | EB | 2017-12-11 | Closed | 2017-12-11
2017-0512-17 | 2017-Spring | CPSA | Prepare strawman UML diagram of the configuration profile | MG, JVP | 2017-11-08 | Closed | 2017-11-08
2017-0512-16 | 2017-Spring | EVSQ | Provide strawman of proposed event sequence structuring | EB | 2017-11-06 | Closed | 2017-10-17
2017-0512-23 | 2017-Spring | SSF | Update SoS schema and send to SANA | CH | 2017-09-15 | Closed | 2017-09-19
2016-1021-20 | 2016-Fall | TGFT | Develop draft TGFT White book | CH, JVP | 2017-08-15 | Closed | 2017-08-08 | Original date was 8-May-17.
2019-1022-04 | 2019-Fall | MgmtSvc | Consider the implcations/considerations re CSSM mgmt services taking into account the REST services presentaion (types of URLs, level of RESTfulness etc) and the SMURF prototyping; produce a presentation and/or write-up of same | CH,MG | 2022-05-01 | Open |  | 06-Oct-20: Insufficient resources to complete in 2020. May be some discussion at the Spring 2020 virtual meetingsl 27-Apr-21: Postponned to fall 2021 meetings;210928: Deferred to spring 2022 virtual meetings; 05-Apr-22: Postponed to discussion at Spring '22 meetings
2017-0512-02 | 2017-Spring | PIF | Provide Planning Products for the Mars relay to Rover for the PIF | EB | 2017-07-30 | Closed | 2017-08-08
2017-0512-32 | 2017-Spring | SSF | Dispose SoS RIDs Update Books | CH | 2017-07-21 | Closed | 2017-08-08
2017-0512-51 | 2017-Spring |  | Put comments in master copy of concept book | MG | 2017-07-31 | Closed | 2017-08-01
2017-0512-19 | 2017-Spring | CPSA | Provide IOAG modulation recommendations and send to AC | EB | 2017-06-30 | Closed | 2017-06-30
2021-0831-01 | Telecon | SACP | Review DDOR configuration profile material developed | EB | 2022-03-15 | Closed | 2022-03-15 | 210928: Revised to fall meetings date; 211130: Postponed to January 2022; Ai is to check if there is "too much stuff" in the config profile for DDOR. Agreed that scan pattern is atttached to service package request, not a configuration profile.
2021-0622-01 | Telecon | SMURF/SPDF | review latest SMRUF test plan and also success criteria for SPDF and comment | EB, MG, CH, MU | 2021-10-15 | Closed |  | 31-aug-21: There was some discussion as to assessment of parameters really needed or not vs success criteria; EB and CH need to weigh in. 210928: Revied to fall meetings date; 211102 - EB send notes from review
2021-1102-01 | 2021-Fall | SMURF/SPDF | Update the SMURF/CDE/SPDF in line with Fall '21 mtg decisions | CH | 2021-11-22 | Closed | 2021-11-30
2021-1102-02 | 2021-Fall | SACP | Draft a list of service agreement parameters | MG, EB | 2022-05-09 | Open |  | 15-Mar-22: Agreed to have a splinter group telecon prior to the spring meetings -- early april.
2021-1102-03 | 2021-Fall | SMURF/SPDF | Produce proposed "final" DDOR Scan pattern to be sent to DDOR WG | EB | 2022-05-06 | Open |  | 211130: Postponed to January 2022
2021-1130-01 | Telecon | SACP | Abstract key aspects of network service agreement | EB, WE, MG | 2022-02-01 | Closed | 2022-02-01
2021-1130-02 | Telecon | SACP | Prepare first draft of service agreement XML structure | MG | 2022-05-09 | Open |  | 15-Mar-22: Revised closure date consistent with service agreement parameters development
2022-0111-01 | Telecon | General | Investigate if tools like XmlSpy and Oxygen support JSON Schema | EB | 2022-02-01 | Closed | 2022-02-01 | Yes, JSON and JSON Schema are supported
2022-0201-01 | Telecon | General | Develop proposed file naming convetions for XML schema given that XML Schema will be going into a GitHub controlled repository (current versioning via filenames will not really work) | CH, MG, EB | 2022-05-09 | Open |  | 05-Apr-22: postponed to Spring mtgs
2022-0222-01 | Telecon | CPIF | Contact secretariat, SIS AD to check on CPIF condition closure | EB | 2022-02-23 | Closed | 2022-03-15
2022-0222-02 | Telecon | General | Generate a spreadsheet to support analysis of FRM parameters with regard to configuration profile in a managed service context | MG | 2022-03-15 | Closed | 2022-03-15
2022-0222-03 | Telecon | SPDF | Develop a trial example for the SPDF ICS with conditional statements and iterate with CH, WE | EB | 2022-03-15 | Closed | 2022-03-15
2022-0315-01 | Telecon | General | Schedule splinter telecon re Svc Agr parameter list | EB | 2022-03-17 | Closed | 2022-04-05 | Include Colin on invitees
2022-0315-02 | Telecon | SPDF | Revise the SPDF ICS based on trial example done for AI 2022-0222-03 | EB | 2022-04-05 | Closed | 2022-04-05
2022-0315-03 | Telecon | SMURF | Revise the SMURF ICS based on the SPDF ICS approach | CH | 2022-05-03 | Open |  | 26-Apr-22: postponed to Spring mtgs
2022-0315-04 | Telecon | General | Remind H. Dreihahn about producing FRM examples considering configuration profile metadata | EB | 2022-03-23 | Closed | 2022-04-05
2022-0315-04 | Telecon | CPIF | Revise CPIF example in GitHub repository to include reference to CCSDS website; make repository public | EB | 2022-04-07 | Closed |  | 2022-04-05 -- Making repo public is pending CPIF 902.2 showing up on CCSDS publication list
2022-0405-01 | Telecon | SPDF | Send Coling email re SMURF review | EB | 2022-04-05 | Closed | 2022-04-05
6

## Legend
Project Identifiers | Project/Area
admin | Administration
Concept | Concept Book
SACP | Service Agreement/Configuration Profile Data Format
EVSQ | Event Sequence
General | General -- program of work as a whole
Inter-rec | Inter-recommendation tracking
MgmtSvc | Management Service
PIF | Planning Information Format
SMURF | Service Management Utliziation Request Format
SPKG | Service Package
TGFT | Terrestrial Generic File Transfer